{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":51,"n_cols":10,"rows_kept":51,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-08T18:56:03.560"]
["2010-03-23",144,15,{"v":2.70805020110221,"d":"2.708"},{"v":148.1899603566614,"d":"148.190"},{"v":964.8673061920598,"d":"964.867"},"Forecast Zero Critical Issues Date(s) ->","2010-08-15T12:27:45.539",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,16,{"v":2.772588722239781,"d":"2.773"},{"v":145.42842858812742,"d":"145.428"}]
["2010-03-25",146,17,{"v":2.833213344056216,"d":"2.833"},{"v":142.83436823238145,"d":"142.834"},"Date '0' ref",null,"2011-06-29T19:45:20.888",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,18,{"v":2.8903717578961645,"d":"2.890"},{"v":140.3886230731212,"d":"140.389"},"2010-03-08"]
["2010-03-27",137,19,{"v":2.9444389791664403,"d":"2.944"},{"v":138.07514661685167,"d":"138.075"}]
["2010-03-28",134,20,{"v":2.995732273553991,"d":"2.996"},{"v":135.88036341656652,"d":"135.880"}]
["2010-03-30",131,22,{"v":3.091042453358316,"d":"3.091"},{"v":131.8021464888299,"d":"131.802"}]
["2010-04-01",131,24,{"v":3.1780538303479458,"d":"3.178"},{"v":128.0790261330263,"d":"128.079"}]
["2010-04-02",128,25,{"v":3.2188758248682006,"d":"3.219"},{"v":126.33229824500566,"d":"126.332"}]
["2010-04-04",128,27,{"v":3.295836866004329,"d":"3.296"},{"v":123.0392206180201,"d":"123.039"}]
["2010-04-05",130,28,{"v":3.332204510175204,"d":"3.332"},{"v":121.48308944311245,"d":"121.483"}]
["2010-04-06",127,29,{"v":3.367295829986474,"d":"3.367"},{"v":119.9815707725491,"d":"119.982"}]
["2010-04-07",121,30,{"v":3.4011973816621555,"d":"3.401"},{"v":118.53096096146544,"d":"118.531"}]
["2010-04-08",120,31,{"v":3.4339872044851463,"d":"3.434"},{"v":117.12792079546483,"d":"117.128"}]
["2010-04-09",116,32,{"v":3.4657359027997265,"d":"3.466"},{"v":115.76942919293143,"d":"115.769"}]
["2010-04-11",110,34,{"v":3.5263605246161616,"d":"3.526"},{"v":113.17536883718549,"d":"113.175"}]
["2010-04-12",110,35,{"v":3.5553480614894135,"d":"3.555"},{"v":111.93502427155155,"d":"111.935"}]
["2010-04-13",109,36,{"v":3.58351893845611,"d":"3.584"},{"v":110.72962367792522,"d":"110.730"}]
["2010-04-14",110,37,{"v":3.6109179126442243,"d":"3.611"},{"v":109.55725194842066,"d":"109.557"}]
["2010-04-15",112,38,{"v":3.6375861597263857,"d":"3.638"},{"v":108.4161472216557,"d":"108.416"}]
["2010-04-18",112,41,{"v":3.713572066704308,"d":"3.714"},{"v":105.16479450421258,"d":"105.165"}]
["2010-04-19",115,42,{"v":3.7376696182833684,"d":"3.738"},{"v":104.13368698801133,"d":"104.134"}]
["2010-04-20",100,43,{"v":3.7612001156935624,"d":"3.761"},{"v":103.12684309102855,"d":"103.127"}]
["2010-04-22",95,45,{"v":3.8066624897703196,"d":"3.807"},{"v":101.18155850636435,"d":"101.182"}]
["2010-04-24",94,47,{"v":3.8501476017100584,"d":"3.850"},{"v":99.32087877644196,"d":"99.321"}]
["2010-04-27",97,50,{"v":3.912023005428146,"d":"3.912"},{"v":96.6732988498097,"d":"96.673"}]
["2010-04-28",90,51,{"v":3.9318256327243257,"d":"3.932"},{"v":95.8259663820844,"d":"95.826"}]
["2010-04-29",87,52,{"v":3.9512437185814275,"d":"3.951"},{"v":94.99508801621354,"d":"94.995"}]
["2010-04-30",85,53,{"v":3.970291913552122,"d":"3.970"},{"v":94.18003687129072,"d":"94.180"}]
["2010-05-02",86,55,{"v":4.007333185232471,"d":"4.007"},{"v":92.59508192207304,"d":"92.595"}]
["2010-05-06",86,59,{"v":4.07753744390572,"d":"4.078"},{"v":89.59111952573465,"d":"89.591"}]
["2010-05-07",84,60,{"v":4.0943445622221,"d":"4.094"},{"v":88.87196156626948,"d":"88.872"}]
["2010-05-08",89,61,{"v":4.110873864173311,"d":"4.111"},{"v":88.16469106106749,"d":"88.165"}]
["2010-05-10",86,63,{"v":4.143134726391533,"d":"4.143"},{"v":86.78428453291025,"d":"86.784"}]
["2010-05-12",84,65,{"v":4.174387269895637,"d":"4.174"},{"v":85.44702284465268,"d":"85.447"}]
["2010-05-13",86,66,{"v":4.189654742026425,"d":"4.190"},{"v":84.79374463853284,"d":"84.794"}]
["2010-05-14",82,67,{"v":4.204692619390966,"d":"4.205"},{"v":84.1502905379194,"d":"84.150"}]
["2010-05-16",80,69,{"v":4.23410650459726,"d":"4.234"},{"v":82.89170299978775,"d":"82.892"}]
["2010-05-18",78,71,{"v":4.2626798770413155,"d":"4.263"},{"v":81.66908007091376,"d":"81.669"}]
["2010-05-20",77,73,{"v":4.290459441148391,"d":"4.290"},{"v":80.4804233207197,"d":"80.480"}]
["2010-05-25",80,78,{"v":4.356708826689592,"d":"4.357"},{"v":77.64568556111246,"d":"77.646"}]
["2010-05-28",82,81,{"v":4.394449154672439,"d":"4.394"},{"v":76.03081876772302,"d":"76.031"}]
["2010-06-01",79,85,{"v":4.442651256490317,"d":"4.443"},{"v":73.96830427042866,"d":"73.968"}]
["2010-06-02",78,86,{"v":4.454347296253507,"d":"4.454"},{"v":73.46784369583261,"d":"73.468"}]
["2010-06-03",78,87,{"v":4.465908118654584,"d":"4.466"},{"v":72.97316892225206,"d":"72.973"}]
["2010-06-04",79,88,{"v":4.477336814478207,"d":"4.477"},{"v":72.48414769843794,"d":"72.484"}]
["2010-06-05",73,89,{"v":4.48863636973214,"d":"4.489"},{"v":72.00065225642857,"d":"72.001"}]
["2010-06-07",72,91,{"v":4.51085950651685,"d":"4.511"},{"v":71.0497488711986,"d":"71.050"}]
["2010-06-08",68,92,{"v":4.5217885770490405,"d":"4.522"},{"v":70.5821060596929,"d":"70.582"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}