{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":56,"n_cols":10,"rows_kept":56,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-13T21:42:55.560"]
["2010-03-23",144,{"v":16.760923763242317,"d":"17"},{"v":2.8190502106736064,"d":"2.819"},{"v":147.42033169267995,"d":"147.420"},{"v":997.4534701358508,"d":"997.453"},"Forecast Zero Critical Issues Date(s) ->","2010-08-20T07:59:01.651",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":17.760923763242317,"d":"18"},{"v":2.877000749907435,"d":"2.877"},{"v":144.82234657675485,"d":"144.822"}]
["2010-03-25",146,{"v":18.760923763242317,"d":"19"},{"v":2.9317761834767726,"d":"2.932"},{"v":142.36670486896531,"d":"142.367"},"Date '0' ref",null,"2011-05-16T11:05:33.367",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":19.760923763242317,"d":"20"},{"v":2.9837064403789535,"d":"2.984"},{"v":140.03861549686025,"d":"140.039"},"2010-03-06T05:44:16.187"]
["2010-03-27",137,{"v":20.760923763242317,"d":"21"},{"v":3.0330725545737214,"d":"3.033"},{"v":137.82547940520848,"d":"137.825"}]
["2010-03-28",134,{"v":21.760923763242317,"d":"22"},{"v":3.080115873441552,"d":"3.080"},{"v":135.71647673089,"d":"135.716"},"Min '0' Ref"]
["2010-03-30",131,{"v":23.760923763242317,"d":"24"},{"v":3.1680423726630185,"d":"3.168"},{"v":131.7746370294326,"d":"131.775"},"2010-03-22"]
["2010-04-01",131,{"v":25.760923763242317,"d":"26"},{"v":3.2488587609674986,"d":"3.249"},{"v":128.15155126157316,"d":"128.152"}]
["2010-04-02",128,{"v":26.760923763242317,"d":"27"},{"v":3.286942754964751,"d":"3.287"},{"v":126.4442047749319,"d":"126.444"}]
["2010-04-04",128,{"v":28.760923763242317,"d":"29"},{"v":3.359017652060326,"d":"3.359"},{"v":123.21300947697975,"d":"123.213"}]
["2010-04-05",130,{"v":29.760923763242317,"d":"30"},{"v":3.393196249914676,"d":"3.393"},{"v":121.68074610751387,"d":"121.681"}]
["2010-04-06",127,{"v":30.760923763242317,"d":"31"},{"v":3.426245175501282,"d":"3.426"},{"v":120.19912716303995,"d":"120.199"}]
["2010-04-07",121,{"v":31.760923763242317,"d":"32"},{"v":3.4582367217003585,"d":"3.458"},{"v":118.76491167584197,"d":"118.765"}]
["2010-04-08",120,{"v":32.76092376324232,"d":"33"},{"v":3.489236456488485,"d":"3.489"},{"v":117.37516016287995,"d":"117.375"}]
["2010-04-09",116,{"v":33.76092376324232,"d":"34"},{"v":3.5193040320086877,"d":"3.519"},{"v":116.02719835430645,"d":"116.027"}]
["2010-04-11",110,{"v":35.76092376324232,"d":"36"},{"v":3.576855782277099,"d":"3.577"},{"v":113.4470913773986,"d":"113.447"}]
["2010-04-12",110,{"v":36.76092376324232,"d":"37"},{"v":3.6044354267485206,"d":"3.604"},{"v":112.21066619850342,"d":"112.211"}]
["2010-04-13",109,{"v":37.76092376324232,"d":"38"},{"v":3.631274805046977,"d":"3.631"},{"v":111.00742794978373,"d":"111.007"}]
["2010-04-14",110,{"v":38.76092376324232,"d":"39"},{"v":3.657412619639555,"d":"3.657"},{"v":109.83564155793789,"d":"109.836"}]
["2010-04-15",112,{"v":39.76092376324232,"d":"40"},{"v":3.6828846150004297,"d":"3.683"},{"v":108.69370455967376,"d":"108.694"}]
["2010-04-18",112,{"v":42.76092376324232,"d":"43"},{"v":3.7556246893669525,"d":"3.756"},{"v":105.43268864793231,"d":"105.433"}]
["2010-04-19",115,{"v":43.76092376324232,"d":"44"},{"v":3.778741267654225,"d":"3.779"},{"v":104.39634753505456,"d":"104.396"}]
["2010-04-20",100,{"v":44.76092376324232,"d":"45"},{"v":3.801335521372904,"d":"3.801"},{"v":103.38342279539489,"d":"103.383"}]
["2010-04-22",95,{"v":46.76092376324232,"d":"47"},{"v":3.8450478918245214,"d":"3.845"},{"v":101.42375012769321,"d":"101.424"}]
["2010-04-24",94,{"v":48.76092376324232,"d":"49"},{"v":3.8869292495370256,"d":"3.887"},{"v":99.54616373401382,"d":"99.546"}]
["2010-04-27",97,{"v":51.76092376324232,"d":"52"},{"v":3.9466354970821196,"d":"3.947"},{"v":96.86946832270786,"d":"96.869"}]
["2010-04-28",90,{"v":52.76092376324232,"d":"53"},{"v":3.9657708364760174,"d":"3.966"},{"v":96.01161043923017,"d":"96.012"}]
["2010-04-29",87,{"v":53.76092376324232,"d":"54"},{"v":3.984546879163292,"d":"3.985"},{"v":95.1698602142549,"d":"95.170"}]
["2010-04-30",85,{"v":54.76092376324232,"d":"55"},{"v":4.002976869584798,"d":"4.003"},{"v":94.34362388522752,"d":"94.344"}]
["2010-05-02",86,{"v":56.76092376324232,"d":"57"},{"v":4.038848127057968,"d":"4.039"},{"v":92.73547676119847,"d":"92.735"}]
["2010-05-06",86,{"v":60.76092376324232,"d":"61"},{"v":4.106946881088668,"d":"4.107"},{"v":89.682536241164,"d":"89.683"}]
["2010-05-07",84,{"v":61.76092376324232,"d":"62"},{"v":4.123270862911046,"d":"4.123"},{"v":88.95071454687309,"d":"88.951"}]
["2010-05-08",89,{"v":62.76092376324232,"d":"63"},{"v":4.139332646737425,"d":"4.139"},{"v":88.23064747126287,"d":"88.231"}]
["2010-05-10",86,{"v":64.76092376324232,"d":"65"},{"v":4.170702393118482,"d":"4.171"},{"v":86.82430793989994,"d":"86.824"}]
["2010-05-12",84,{"v":66.76092376324232,"d":"67"},{"v":4.20111793577463,"d":"4.201"},{"v":85.46074638968523,"d":"85.461"}]
["2010-05-13",86,{"v":67.76092376324232,"d":"68"},{"v":4.215985683120446,"d":"4.216"},{"v":84.79420925608048,"d":"84.794"}]
["2010-05-14",82,{"v":68.76092376324232,"d":"69"},{"v":4.230635615026533,"d":"4.231"},{"v":84.1374370233363,"d":"84.137"}]
["2010-05-16",80,{"v":70.76092376324232,"d":"71"},{"v":4.259306924085431,"d":"4.259"},{"v":82.85207134470906,"d":"82.852"}]
["2010-05-18",78,{"v":72.76092376324232,"d":"73"},{"v":4.287179049600695,"d":"4.287"},{"v":81.60253392546821,"d":"81.603"}]
["2010-05-20",77,{"v":74.76092376324232,"d":"75"},{"v":4.314295338894682,"d":"4.314"},{"v":80.38688145844557,"d":"80.387"}]
["2010-05-25",80,{"v":79.76092376324232,"d":"80"},{"v":4.379033707372401,"d":"4.379"},{"v":77.48459064358786,"d":"77.485"}]
["2010-05-28",82,{"v":82.76092376324232,"d":"83"},{"v":4.415956014768193,"d":"4.416"},{"v":75.82932381901475,"d":"75.829"}]
["2010-06-01",79,{"v":86.76092376324232,"d":"87"},{"v":4.463156333242266,"d":"4.463"},{"v":73.71328268318032,"d":"73.713"}]
["2010-06-02",78,{"v":87.76092376324232,"d":"88"},{"v":4.474616341928467,"d":"4.475"},{"v":73.19951814554611,"d":"73.200"}]
["2010-06-03",78,{"v":88.76092376324232,"d":"89"},{"v":4.485946505437481,"d":"4.486"},{"v":72.69157470711414,"d":"72.692"}]
["2010-06-04",79,{"v":89.76092376324232,"d":"90"},{"v":4.497149733201401,"d":"4.497"},{"v":72.18932193490883,"d":"72.189"}]
["2010-06-05",73,{"v":90.76092376324232,"d":"91"},{"v":4.508228837947574,"d":"4.508"},{"v":71.69263373133245,"d":"71.693"}]
["2010-06-07",72,{"v":92.76092376324232,"d":"93"},{"v":4.530025470975544,"d":"4.530"},{"v":70.71546718667861,"d":"70.715"}]
["2010-06-08",68,{"v":93.76092376324232,"d":"94"},{"v":4.5407481782038275,"d":"4.541"},{"v":70.23475666784981,"d":"70.235"}]
["2010-06-09",67,{"v":94.76092376324232,"d":"95"},{"v":4.551357127694339,"d":"4.551"},{"v":69.75914603097999,"d":"69.759"}]
["2010-06-10",66,{"v":95.76092376324232,"d":"96"},{"v":4.561854707853589,"d":"4.562"},{"v":69.28852820123177,"d":"69.289"}]
["2010-06-11",67,{"v":96.76092376324232,"d":"97"},{"v":4.572243232649979,"d":"4.572"},{"v":68.82279944090845,"d":"68.823"}]
["2010-06-12",66,{"v":97.76092376324232,"d":"98"},{"v":4.58252494467531,"d":"4.583"},{"v":68.36185921220311,"d":"68.362"}]
["2010-06-13",67,{"v":98.76092376324232,"d":"99"},{"v":4.592702018050511,"d":"4.593"},{"v":67.90561004693191,"d":"67.906"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}