{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":60,"n_cols":10,"rows_kept":60,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-17T21:49:40.930"]
["2010-03-23",144,{"v":16.943155486100295,"d":"17"},{"v":2.829863946145033,"d":"2.830"},{"v":147.3464263125892,"d":"147.346"},{"v":1000.1785369452026,"d":"1000.179"},"Forecast Zero Critical Issues Date(s) ->","2010-08-24T21:07:20.209",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":17.943155486100295,"d":"18"},{"v":2.8872087322505995,"d":"2.887"},{"v":144.763628128441,"d":"144.764"}]
["2010-03-25",146,{"v":18.943155486100295,"d":"19"},{"v":2.9414426782157284,"d":"2.941"},{"v":142.32094158846405,"d":"142.321"},"Date '0' ref",null,"2011-05-15T03:14:32.578",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":19.943155486100295,"d":"20"},{"v":2.992886001065803,"d":"2.993"},{"v":140.0039441791595,"d":"140.004"},"2010-03-06T01:21:51.366"]
["2010-03-27",137,{"v":20.943155486100295,"d":"21"},{"v":3.041811885880368,"d":"3.042"},{"v":137.8003316968621,"d":"137.800"}]
["2010-03-28",134,{"v":21.943155486100295,"d":"22"},{"v":3.088455267937587,"d":"3.088"},{"v":135.6995227016356,"d":"135.700"},"Min '0' Ref"]
["2010-03-30",131,{"v":23.943155486100295,"d":"24"},{"v":3.1756824995516832,"d":"3.176"},{"v":131.77082489454253,"d":"131.771"},"2010-03-22"]
["2010-04-01",131,{"v":25.943155486100295,"d":"26"},{"v":3.2559078170606344,"d":"3.256"},{"v":128.15749195781515,"d":"128.157"}]
["2010-04-02",128,{"v":26.943155486100295,"d":"27"},{"v":3.2937292942677954,"d":"3.294"},{"v":126.45401986756048,"d":"126.454"}]
["2010-04-04",128,{"v":28.943155486100295,"d":"29"},{"v":3.3653337507155308,"d":"3.365"},{"v":123.2289688620572,"d":"123.229"}]
["2010-04-05",130,{"v":29.943155486100295,"d":"30"},{"v":3.3993007670952853,"d":"3.399"},{"v":121.69910094930472,"d":"121.699"}]
["2010-04-06",127,{"v":30.943155486100295,"d":"31"},{"v":3.4321518272134894,"d":"3.432"},{"v":120.21949549285671,"d":"120.219"}]
["2010-04-07",121,{"v":31.943155486100295,"d":"32"},{"v":3.463957932086764,"d":"3.464"},{"v":118.78695462052193,"d":"118.787"}]
["2010-04-08",120,{"v":32.943155486100295,"d":"33"},{"v":3.494783515125029,"d":"3.495"},{"v":117.39857626385717,"d":"117.399"}]
["2010-04-09",116,{"v":33.943155486100295,"d":"34"},{"v":3.52468722796821,"d":"3.525"},{"v":116.05171876423245,"d":"116.052"}]
["2010-04-11",110,{"v":35.943155486100295,"d":"36"},{"v":3.5819386762242105,"d":"3.582"},{"v":113.4731244989537,"d":"113.473"}]
["2010-04-12",110,{"v":36.943155486100295,"d":"37"},{"v":3.6093803930530135,"d":"3.609"},{"v":112.23715482832202,"d":"112.237"}]
["2010-04-13",109,{"v":37.943155486100295,"d":"38"},{"v":3.636089131478033,"d":"3.636"},{"v":111.03419836462476,"d":"111.034"}]
["2010-04-14",110,{"v":38.943155486100295,"d":"39"},{"v":3.662103031229505,"d":"3.662"},{"v":109.86253730171615,"d":"109.863"}]
["2010-04-15",112,{"v":39.943155486100295,"d":"40"},{"v":3.6874573305278853,"d":"3.687"},{"v":108.72058451689531,"d":"108.721"}]
["2010-04-18",112,{"v":42.943155486100295,"d":"43"},{"v":3.759877275686873,"d":"3.760"},{"v":105.45880405601073,"d":"105.459"}]
["2010-04-19",115,{"v":43.943155486100295,"d":"44"},{"v":3.7828968778987133,"d":"3.783"},{"v":104.42200558085202,"d":"104.422"}]
["2010-04-20",100,{"v":44.943155486100295,"d":"45"},{"v":3.80539847982624,"d":"3.805"},{"v":103.40853773929703,"d":"103.409"}]
["2010-04-22",95,{"v":46.943155486100295,"d":"47"},{"v":3.848937411983234,"d":"3.849"},{"v":101.44755257304632,"d":"101.448"}]
["2010-04-24",94,{"v":48.943155486100295,"d":"49"},{"v":3.8906595325624846,"d":"3.891"},{"v":99.56839625232129,"d":"99.568"}]
["2010-04-27",97,{"v":51.943155486100295,"d":"52"},{"v":3.9501499569133145,"d":"3.950"},{"v":96.88895893251566,"d":"96.889"}]
["2010-04-28",90,{"v":52.943155486100295,"d":"53"},{"v":3.969218799973544,"d":"3.969"},{"v":96.03010189293929,"d":"96.030"}]
["2010-04-29",87,{"v":53.943155486100295,"d":"54"},{"v":3.987930815928233,"d":"3.988"},{"v":95.18731627786082,"d":"95.187"}]
["2010-04-30",85,{"v":54.943155486100295,"d":"55"},{"v":4.0062991141488515,"d":"4.006"},{"v":94.36001164369983,"d":"94.360"}]
["2010-05-02",86,{"v":56.943155486100295,"d":"57"},{"v":4.042053498054116,"d":"4.042"},{"v":92.74964103989547,"d":"92.750"}]
["2010-05-06",86,{"v":60.943155486100295,"d":"61"},{"v":4.109941552428703,"d":"4.110"},{"v":89.69197607204211,"d":"89.692"}]
["2010-05-07",84,{"v":61.943155486100295,"d":"62"},{"v":4.12621711748542,"d":"4.126"},{"v":88.95892773880584,"d":"88.959"}]
["2010-05-08",89,{"v":62.943155486100295,"d":"63"},{"v":4.142232025207965,"d":"4.142"},{"v":88.23761936198247,"d":"88.238"}]
["2010-05-10",86,{"v":64.9431554861003,"d":"65"},{"v":4.17351235628725,"d":"4.174"},{"v":86.82875924063853,"d":"86.829"}]
["2010-05-12",84,{"v":66.9431554861003,"d":"67"},{"v":4.203843833693688,"d":"4.204"},{"v":85.46263530700554,"d":"85.463"}]
["2010-05-13",86,{"v":67.9431554861003,"d":"68"},{"v":4.218671406842299,"d":"4.219"},{"v":84.79480425200683,"d":"84.795"}]
["2010-05-14",82,{"v":68.9431554861003,"d":"69"},{"v":4.233282331525141,"d":"4.233"},{"v":84.13673100241621,"d":"84.137"}]
["2010-05-16",80,{"v":70.9431554861003,"d":"71"},{"v":4.261878929412049,"d":"4.262"},{"v":82.84874571009766,"d":"82.849"}]
["2010-05-18",78,{"v":72.9431554861003,"d":"73"},{"v":4.289680445839088,"d":"4.290"},{"v":81.59657073446633,"d":"81.597"}]
["2010-05-20",77,{"v":74.9431554861003,"d":"75"},{"v":4.316729899312544,"d":"4.317"},{"v":80.37826853023748,"d":"80.378"}]
["2010-05-25",80,{"v":79.9431554861003,"d":"80"},{"v":4.381315825685271,"d":"4.381"},{"v":77.46933077520043,"d":"77.469"}]
["2010-05-28",82,{"v":82.9431554861003,"d":"83"},{"v":4.418155499502054,"d":"4.418"},{"v":75.8100789216241,"d":"75.810"}]
["2010-06-01",79,{"v":86.9431554861003,"d":"87"},{"v":4.4652545198882,"d":"4.465"},{"v":73.68874806332161,"d":"73.689"}]
["2010-06-02",78,{"v":87.9431554861003,"d":"88"},{"v":4.476690645370684,"d":"4.477"},{"v":73.17366716171227,"d":"73.174"}]
["2010-06-03",78,{"v":88.9431554861003,"d":"89"},{"v":4.487997463271499,"d":"4.488"},{"v":72.66441024881769,"d":"72.664"}]
["2010-06-04",79,{"v":89.9431554861003,"d":"90"},{"v":4.499177865073354,"d":"4.499"},{"v":72.16084709281051,"d":"72.161"}]
["2010-06-05",73,{"v":90.9431554861003,"d":"91"},{"v":4.51023464634448,"d":"4.510"},{"v":71.66285178183287,"d":"71.663"}]
["2010-06-07",72,{"v":92.9431554861003,"d":"93"},{"v":4.5319880749429755,"d":"4.532"},{"v":70.68308152373547,"d":"70.683"}]
["2010-06-08",68,{"v":93.9431554861003,"d":"94"},{"v":4.542689870476477,"d":"4.543"},{"v":70.20107470239745,"d":"70.201"}]
["2010-06-09",67,{"v":94.9431554861003,"d":"95"},{"v":4.553278349205567,"d":"4.553"},{"v":69.72417164822892,"d":"69.724"}]
["2010-06-10",66,{"v":95.9431554861003,"d":"96"},{"v":4.5637558857363025,"d":"4.564"},{"v":69.25226540942785,"d":"69.252"}]
["2010-06-11",67,{"v":96.9431554861003,"d":"97"},{"v":4.574124780806589,"d":"4.574"},{"v":68.78525236119961,"d":"68.785"}]
["2010-06-12",66,{"v":97.9431554861003,"d":"98"},{"v":4.584387264318574,"d":"4.584"},{"v":68.32303206917845,"d":"68.323"}]
["2010-06-13",67,{"v":98.9431554861003,"d":"99"},{"v":4.594545498217013,"d":"4.595"},{"v":67.86550715978666,"d":"67.866"}]
["2010-06-14",68,{"v":99.9431554861003,"d":"100"},{"v":4.604601579222903,"d":"4.605"},{"v":67.41258319711204,"d":"67.413"}]
["2010-06-15",66,{"v":100.9431554861003,"d":"101"},{"v":4.614557541431033,"d":"4.615"},{"v":66.96416856591492,"d":"66.964"}]
["2010-06-16",67,{"v":101.9431554861003,"d":"102"},{"v":4.624415358779497,"d":"4.624"},{"v":66.52017436040154,"d":"66.520"}]
["2010-06-17",65,{"v":102.9431554861003,"d":"103"},{"v":4.634176947398668,"d":"4.634"},{"v":66.08051427842679,"d":"66.081"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}