{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":62,"n_cols":10,"rows_kept":62,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-19T22:32:20.390"]
["2010-03-23",144,{"v":17.22662464190944,"d":"17"},{"v":2.84645613128562,"d":"2.846"},{"v":147.23340697743743,"d":"147.233"},{"v":1001.9480763923236,"d":"1001.948"},"Forecast Zero Critical Issues Date(s) ->","2010-08-26T18:21:59.129",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":18.22662464190944,"d":"18"},{"v":2.9028834175106635,"d":"2.903"},{"v":144.67366193389358,"d":"144.674"}]
["2010-03-25",146,{"v":19.22662464190944,"d":"19"},{"v":2.9562960185525253,"d":"2.956"},{"v":142.25067387392534,"d":"142.251"},"Date '0' ref",null,"2011-05-10T18:32:49.380",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":20.22662464190944,"d":"20"},{"v":3.006999788119363,"d":"3.007"},{"v":139.95056817116162,"d":"139.951"},"2010-03-05T18:33:39.631"]
["2010-03-27",137,{"v":21.22662464190944,"d":"21"},{"v":3.055256273056515,"d":"3.055"},{"v":137.76148011819228,"d":"137.761"}]
["2010-03-28",134,{"v":22.22662464190944,"d":"22"},{"v":3.101290878476768,"d":"3.101"},{"v":135.67318452683543,"d":"135.673"},"Min '0' Ref"]
["2010-03-30",131,{"v":24.22662464190944,"d":"24"},{"v":3.187452220209599,"d":"3.187"},{"v":131.76459557633902,"d":"131.765"},"2010-03-22"]
["2010-04-01",131,{"v":26.22662464190944,"d":"26"},{"v":3.2667751024840057,"d":"3.267"},{"v":128.16622378982893,"d":"128.166"}]
["2010-04-02",128,{"v":27.22662464190944,"d":"27"},{"v":3.3041953416725196,"d":"3.304"},{"v":126.46870689332235,"d":"126.469"}]
["2010-04-04",128,{"v":29.22662464190944,"d":"29"},{"v":3.3750800966396897,"d":"3.375"},{"v":123.25311896895565,"d":"123.253"}]
["2010-04-05",130,{"v":30.22662464190944,"d":"30"},{"v":3.4087231466496557,"d":"3.409"},{"v":121.72694898500046,"d":"121.727"}]
["2010-04-06",127,{"v":31.22662464190944,"d":"31"},{"v":3.4412710848233536,"d":"3.441"},{"v":120.25045722026417,"d":"120.250"}]
["2010-04-07",121,{"v":32.22662464190944,"d":"32"},{"v":3.472792963129586,"d":"3.473"},{"v":118.82051122860736,"d":"118.821"}]
["2010-04-08",120,{"v":33.22662464190944,"d":"33"},{"v":3.5033515015801884,"d":"3.503"},{"v":117.43426580427652,"d":"117.434"}]
["2010-04-09",116,{"v":34.22662464190944,"d":"34"},{"v":3.5330038394973826,"d":"3.533"},{"v":116.08912890170936,"d":"116.089"}]
["2010-04-11",110,{"v":36.22662464190944,"d":"36"},{"v":3.589794335839018,"d":"3.590"},{"v":113.51290733841932,"d":"113.513"}]
["2010-04-12",110,{"v":37.22662464190944,"d":"37"},{"v":3.61702422145678,"d":"3.617"},{"v":112.2776616016609,"d":"112.278"}]
["2010-04-13",109,{"v":38.22662464190944,"d":"38"},{"v":3.6435322529893597,"d":"3.644"},{"v":111.075161767467,"d":"111.075"}]
["2010-04-14",110,{"v":39.22662464190944,"d":"39"},{"v":3.669355716293162,"d":"3.669"},{"v":109.9037164150285,"d":"109.904"}]
["2010-04-15",112,{"v":40.22662464190944,"d":"40"},{"v":3.694529080923235,"d":"3.695"},{"v":108.7617618811145,"d":"108.762"}]
["2010-04-18",112,{"v":43.22662464190944,"d":"43"},{"v":3.766456616563653,"d":"3.766"},{"v":105.49886966766317,"d":"105.499"}]
["2010-04-19",115,{"v":44.22662464190944,"d":"44"},{"v":3.7893269751972087,"d":"3.789"},{"v":104.46138778482307,"d":"104.461"}]
["2010-04-20",100,{"v":45.22662464190944,"d":"45"},{"v":3.811685954171988,"d":"3.812"},{"v":103.44710392610384,"d":"103.447"}]
["2010-04-22",95,{"v":47.22662464190944,"d":"47"},{"v":3.8549578149537878,"d":"3.855"},{"v":101.48413638732518,"d":"101.484"}]
["2010-04-24",94,{"v":49.22662464190944,"d":"49"},{"v":3.8964346283870452,"d":"3.896"},{"v":99.60259866487743,"d":"99.603"}]
["2010-04-27",97,{"v":52.22662464190944,"d":"52"},{"v":3.9555924154682853,"d":"3.956"},{"v":96.91898826291165,"d":"96.919"}]
["2010-04-28",90,{"v":53.22662464190944,"d":"53"},{"v":3.9745587343514477,"d":"3.975"},{"v":96.05860769167836,"d":"96.059"}]
["2010-04-29",87,{"v":54.22662464190944,"d":"54"},{"v":3.993172017387385,"d":"3.993"},{"v":95.21424209866899,"d":"95.214"}]
["2010-04-30",85,{"v":55.22662464190944,"d":"55"},{"v":4.011445167468473,"d":"4.011"},{"v":94.3853061621887,"d":"94.385"}]
["2010-05-02",86,{"v":57.22662464190944,"d":"57"},{"v":4.047019255857813,"d":"4.047"},{"v":92.77153731868918,"d":"92.772"}]
["2010-05-06",86,{"v":61.22662464190944,"d":"61"},{"v":4.114582138082893,"d":"4.115"},{"v":89.70664151254581,"d":"89.707"}]
["2010-05-07",84,{"v":62.22662464190944,"d":"62"},{"v":4.130782957063633,"d":"4.131"},{"v":88.97171398259323,"d":"88.972"}]
["2010-05-08",89,{"v":63.22662464190944,"d":"63"},{"v":4.1467254884205795,"d":"4.147"},{"v":88.24850331001662,"d":"88.249"}]
["2010-05-10",86,{"v":65.22662464190944,"d":"65"},{"v":4.177867738982566,"d":"4.178"},{"v":86.83577860085867,"d":"86.836"}]
["2010-05-12",84,{"v":67.22662464190944,"d":"67"},{"v":4.208069369091012,"d":"4.208"},{"v":85.46572382507665,"d":"85.466"}]
["2010-05-13",86,{"v":68.22662464190944,"d":"68"},{"v":4.222834879310649,"d":"4.223"},{"v":84.79590707278109,"d":"84.796"}]
["2010-05-14",82,{"v":69.22662464190944,"d":"69"},{"v":4.237385537787186,"d":"4.237"},{"v":84.13583676978845,"d":"84.136"}]
["2010-05-16",80,{"v":71.22662464190944,"d":"71"},{"v":4.265866690119046,"d":"4.266"},{"v":82.84382906583582,"d":"82.844"}]
["2010-05-18",78,{"v":73.22662464190944,"d":"73"},{"v":4.293559079451752,"d":"4.294"},{"v":81.5876024938973,"d":"81.588"}]
["2010-05-20",77,{"v":75.22662464190944,"d":"75"},{"v":4.320505219383718,"d":"4.321"},{"v":80.36522848394753,"d":"80.365"}]
["2010-05-25",80,{"v":80.22662464190944,"d":"80"},{"v":4.384855437858611,"d":"4.385"},{"v":77.44607068261126,"d":"77.446"}]
["2010-05-28",82,{"v":83.22662464190944,"d":"83"},{"v":4.421567304350872,"d":"4.422"},{"v":75.78068812428609,"d":"75.781"}]
["2010-06-01",79,{"v":87.22662464190944,"d":"87"},{"v":4.468509612773949,"d":"4.469"},{"v":73.65121585373856,"d":"73.651"}]
["2010-06-02",78,{"v":88.22662464190944,"d":"88"},{"v":4.4799087841484795,"d":"4.480"},{"v":73.13410836233643,"d":"73.134"}]
["2010-06-03",78,{"v":89.22662464190944,"d":"89"},{"v":4.4911794775815315,"d":"4.491"},{"v":72.62282909334064,"d":"72.623"}]
["2010-06-04",79,{"v":90.22662464190944,"d":"90"},{"v":4.502324556927107,"d":"4.502"},{"v":72.11724813201349,"d":"72.117"}]
["2010-06-05",73,{"v":91.22662464190944,"d":"91"},{"v":4.513346791338054,"d":"4.513"},{"v":71.61723985960293,"d":"71.617"}]
["2010-06-07",72,{"v":93.22662464190944,"d":"93"},{"v":4.535033353018526,"d":"4.535"},{"v":70.63345927246459,"d":"70.633"}]
["2010-06-08",68,{"v":94.22662464190944,"d":"94"},{"v":4.5457027811580115,"d":"4.546"},{"v":70.14945556389401,"d":"70.149"}]
["2010-06-09",67,{"v":95.22662464190944,"d":"95"},{"v":4.556259573305078,"d":"4.556"},{"v":69.67056142983262,"d":"69.671"}]
["2010-06-10",66,{"v":96.22662464190944,"d":"96"},{"v":4.56670608280914,"d":"4.567"},{"v":69.19667011387051,"d":"69.197"}]
["2010-06-11",67,{"v":97.22662464190944,"d":"97"},{"v":4.577044590027263,"d":"4.577"},{"v":68.7276781707937,"d":"68.728"}]
["2010-06-12",66,{"v":98.22662464190944,"d":"98"},{"v":4.587277305311908,"d":"4.587"},{"v":68.26348533104948,"d":"68.263"}]
["2010-06-13",67,{"v":99.22662464190944,"d":"99"},{"v":4.597406371847352,"d":"4.597"},{"v":67.80399437207575,"d":"67.804"}]
["2010-06-14",68,{"v":100.22662464190944,"d":"100"},{"v":4.607433868343906,"d":"4.607"},{"v":67.34911099608212,"d":"67.349"}]
["2010-06-15",66,{"v":101.22662464190944,"d":"101"},{"v":4.617361811598363,"d":"4.617"},{"v":66.89874371389831,"d":"66.899"}]
["2010-06-16",67,{"v":102.22662464190944,"d":"102"},{"v":4.627192158928618,"d":"4.627"},{"v":66.45280373453124,"d":"66.453"}]
["2010-06-17",65,{"v":103.22662464190944,"d":"103"},{"v":4.636926810489757,"d":"4.637"},{"v":66.01120486009887,"d":"66.011"}]
["2010-06-18",65,{"v":104.22662464190944,"d":"104"},{"v":4.646567611478516,"d":"4.647"},{"v":65.57386338582793,"d":"65.574"}]
["2010-06-19",64,{"v":105.22662464190944,"d":"105"},{"v":4.656116354232473,"d":"4.656"},{"v":65.14069800482707,"d":"65.141"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}