{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":64,"n_cols":10,"rows_kept":64,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-21T21:51:31.920"]
["2010-03-23",144,{"v":19.472597149506328,"d":"19"},{"v":2.9690082028613434,"d":"2.969"},{"v":146.4131376864399,"d":"146.413"},{"v":1102.5865847946773,"d":"1102.587"},"Forecast Zero Critical Issues Date(s) ->","2010-08-26T22:19:18.543",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":20.472597149506328,"d":"20"},{"v":3.0190872675169906,"d":"3.019"},{"v":144.0146522485424,"d":"144.015"}]
["2010-03-25",146,{"v":21.472597149506328,"d":"21"},{"v":3.0667775710166807,"d":"3.067"},{"v":141.73057407616747,"d":"141.731"},"Date '0' ref",null,"2011-04-06T03:03:13.595",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":22.472597149506328,"d":"22"},{"v":3.1122966624956248,"d":"3.112"},{"v":139.55048387661418,"d":"139.550"},"2010-03-03T12:39:27.606"]
["2010-03-27",137,{"v":23.472597149506328,"d":"23"},{"v":3.155833662006899,"d":"3.156"},{"v":137.46532393891223,"d":"137.465"}]
["2010-03-28",134,{"v":24.472597149506328,"d":"24"},{"v":3.197554007887374,"d":"3.198"},{"v":135.46717076359965,"d":"135.467"},"Min '0' Ref"]
["2010-03-30",131,{"v":26.472597149506328,"d":"26"},{"v":3.276110128143157,"d":"3.276"},{"v":131.70480595533496,"d":"131.705"},"2010-03-22"]
["2010-04-01",131,{"v":28.472597149506328,"d":"28"},{"v":3.348942121207482,"d":"3.349"},{"v":128.21659234793216,"d":"128.217"}]
["2010-04-02",128,{"v":29.472597149506328,"d":"29"},{"v":3.383460921455117,"d":"3.383"},{"v":126.56334981441154,"d":"126.563"}]
["2010-04-04",128,{"v":31.472597149506328,"d":"31"},{"v":3.449117235459656,"d":"3.449"},{"v":123.41880799581443,"d":"123.419"}]
["2010-04-05",130,{"v":32.47259714950633,"d":"32"},{"v":3.480396569041884,"d":"3.480"},{"v":121.92071639566208,"d":"121.921"}]
["2010-04-06",127,{"v":33.47259714950633,"d":"33"},{"v":3.51072710855299,"d":"3.511"},{"v":120.46806631441186,"d":"120.468"}]
["2010-04-07",121,{"v":34.47259714950633,"d":"34"},{"v":3.5401647229038784,"d":"3.540"},{"v":119.05818196787811,"d":"119.058"}]
["2010-04-08",120,{"v":35.47259714950633,"d":"35"},{"v":3.5687604871229426,"d":"3.569"},{"v":117.68861716996128,"d":"117.689"}]
["2010-04-09",116,{"v":36.47259714950633,"d":"36"},{"v":3.5965612155975264,"d":"3.597"},{"v":116.35712979359488,"d":"116.357"}]
["2010-04-11",110,{"v":38.47259714950633,"d":"38"},{"v":3.649946225520173,"d":"3.650"},{"v":113.80030949788988,"d":"113.800"}]
["2010-04-12",110,{"v":39.47259714950633,"d":"39"},{"v":3.6756066881055407,"d":"3.676"},{"v":112.57132796111557,"d":"112.571"}]
["2010-04-13",109,{"v":40.47259714950633,"d":"40"},{"v":3.7006251315137755,"d":"3.701"},{"v":111.37309527434061,"d":"111.373"}]
["2010-04-14",110,{"v":41.47259714950633,"d":"41"},{"v":3.725032899485771,"d":"3.725"},{"v":110.20411026124273,"d":"110.204"}]
["2010-04-15",112,{"v":42.47259714950633,"d":"42"},{"v":3.7488590950221043,"d":"3.749"},{"v":109.06297906345887,"d":"109.063"}]
["2010-04-18",112,{"v":45.47259714950633,"d":"45"},{"v":3.8171098840748194,"d":"3.817"},{"v":105.79417752346265,"d":"105.794"}]
["2010-04-19",115,{"v":46.47259714950633,"d":"46"},{"v":3.8388628302699734,"d":"3.839"},{"v":104.75234247643843,"d":"104.752"}]
["2010-04-20",100,{"v":47.47259714950633,"d":"47"},{"v":3.8601526424528854,"d":"3.860"},{"v":103.73268875791538,"d":"103.733"}]
["2010-04-22",95,{"v":49.47259714950633,"d":"49"},{"v":3.9014189233462315,"d":"3.901"},{"v":101.75628255944784,"d":"101.756"}]
["2010-04-24",94,{"v":51.47259714950633,"d":"51"},{"v":3.9410495718730005,"d":"3.941"},{"v":99.8582132955849,"d":"99.858"}]
["2010-04-27",97,{"v":54.47259714950633,"d":"54"},{"v":3.9976977706243657,"d":"3.998"},{"v":97.14510591783059,"d":"97.145"}]
["2010-04-28",90,{"v":55.47259714950633,"d":"55"},{"v":4.0158891537662225,"d":"4.016"},{"v":96.27384828031327,"d":"96.274"}]
["2010-04-29",87,{"v":56.47259714950633,"d":"56"},{"v":4.033755514295415,"d":"4.034"},{"v":95.41815726746876,"d":"95.418"}]
["2010-04-30",85,{"v":57.47259714950633,"d":"57"},{"v":4.051308262894171,"d":"4.051"},{"v":94.5774863763753,"d":"94.577"}]
["2010-05-02",86,{"v":59.47259714950633,"d":"59"},{"v":4.085515654355751,"d":"4.086"},{"v":92.93915844726519,"d":"92.939"}]
["2010-05-06",86,{"v":63.47259714950633,"d":"63"},{"v":4.150608271805396,"d":"4.151"},{"v":89.82161429700716,"d":"89.822"}]
["2010-05-07",84,{"v":64.47259714950633,"d":"64"},{"v":4.166240283131978,"d":"4.166"},{"v":89.07293514755293,"d":"89.073"}]
["2010-05-08",89,{"v":65.47259714950633,"d":"65"},{"v":4.181631690972843,"d":"4.182"},{"v":88.33577945527117,"d":"88.336"}]
["2010-05-10",86,{"v":67.47259714950633,"d":"67"},{"v":4.2117215472956415,"d":"4.212"},{"v":86.89465664846728,"d":"86.895"}]
["2010-05-12",84,{"v":69.47259714950633,"d":"69"},{"v":4.24093238920112,"d":"4.241"},{"v":85.49563333561639,"d":"85.496"}]
["2010-05-13",86,{"v":70.47259714950633,"d":"70"},{"v":4.255223941342748,"d":"4.255"},{"v":84.81115410397842,"d":"84.811"}]
["2010-05-14",82,{"v":71.47259714950633,"d":"71"},{"v":4.269314119588101,"d":"4.269"},{"v":84.13631946856259,"d":"84.136"}]
["2010-05-16",80,{"v":73.47259714950633,"d":"73"},{"v":4.2969125088033175,"d":"4.297"},{"v":82.81452292349354,"d":"82.815"}]
["2010-05-18",78,{"v":75.47259714950633,"d":"75"},{"v":4.323769638709915,"d":"4.324"},{"v":81.52822823273536,"d":"81.528"}]
["2010-05-20",77,{"v":77.47259714950633,"d":"77"},{"v":4.349924288665666,"d":"4.350"},{"v":80.2755780987217,"d":"80.276"}]
["2010-05-25",80,{"v":82.47259714950633,"d":"82"},{"v":4.4124660824011315,"d":"4.412"},{"v":77.2802030339922,"d":"77.280"}]
["2010-05-28",82,{"v":85.47259714950633,"d":"85"},{"v":4.448195823395872,"d":"4.448"},{"v":75.56896373539502,"d":"75.569"}]
["2010-06-01",79,{"v":89.47259714950633,"d":"89"},{"v":4.493932401298544,"d":"4.494"},{"v":73.37845724664308,"d":"73.378"}]
["2010-06-02",78,{"v":90.47259714950633,"d":"90"},{"v":4.505047010926436,"d":"4.505"},{"v":72.84613441825718,"d":"72.846"}]
["2010-06-03",78,{"v":91.47259714950633,"d":"91"},{"v":4.516039442722127,"d":"4.516"},{"v":72.31966317183239,"d":"72.320"}]
["2010-06-04",79,{"v":92.47259714950633,"d":"92"},{"v":4.526912353596195,"d":"4.527"},{"v":71.79891625736161,"d":"71.799"}]
["2010-06-05",73,{"v":93.47259714950633,"d":"93"},{"v":4.537668314723805,"d":"4.538"},{"v":71.28377053104751,"d":"71.284"}]
["2010-06-07",72,{"v":95.47259714950633,"d":"95"},{"v":4.558839265468419,"d":"4.559"},{"v":70.2698095592011,"d":"70.270"}]
["2010-06-08",68,{"v":96.47259714950633,"d":"96"},{"v":4.569259000655945,"d":"4.569"},{"v":69.77076702943586,"d":"69.771"}]
["2010-06-09",67,{"v":97.47259714950633,"d":"97"},{"v":4.579571283623619,"d":"4.580"},{"v":69.2768708135317,"d":"69.277"}]
["2010-06-10",66,{"v":98.47259714950633,"d":"98"},{"v":4.5897783079449646,"d":"4.590"},{"v":68.7880158525345,"d":"68.788"}]
["2010-06-11",67,{"v":99.47259714950633,"d":"99"},{"v":4.599882200700879,"d":"4.600"},{"v":68.30410027208634,"d":"68.304"}]
["2010-06-12",66,{"v":100.47259714950633,"d":"100"},{"v":4.609885025140181,"d":"4.610"},{"v":67.82502525500124,"d":"67.825"}]
["2010-06-13",67,{"v":101.47259714950633,"d":"101"},{"v":4.619788783208401,"d":"4.620"},{"v":67.35069492015128,"d":"67.351"}]
["2010-06-14",68,{"v":102.47259714950633,"d":"102"},{"v":4.629595417952584,"d":"4.630"},{"v":66.88101620729117,"d":"66.881"}]
["2010-06-15",66,{"v":103.47259714950633,"d":"103"},{"v":4.639306815809301,"d":"4.639"},{"v":66.41589876747616,"d":"66.416"}]
["2010-06-16",67,{"v":104.47259714950633,"d":"104"},{"v":4.648924808782641,"d":"4.649"},{"v":65.95525485874944,"d":"65.955"}]
["2010-06-17",65,{"v":105.47259714950633,"d":"105"},{"v":4.658451176518446,"d":"4.658"},{"v":65.49899924679863,"d":"65.499"}]
["2010-06-18",65,{"v":106.47259714950633,"d":"106"},{"v":4.667887648280684,"d":"4.668"},{"v":65.04704911029975,"d":"65.047"}]
["2010-06-19",64,{"v":107.47259714950633,"d":"107"},{"v":4.67723590483543,"d":"4.677"},{"v":64.59932395068535,"d":"64.599"}]
["2010-06-20",60,{"v":108.47259714950633,"d":"108"},{"v":4.686497580247613,"d":"4.686"},{"v":64.15574550609176,"d":"64.156"}]
["2010-06-21",55,{"v":109.47259714950633,"d":"109"},{"v":4.695674263595304,"d":"4.696"},{"v":63.716237669254554,"d":"63.716"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}