{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":65,"n_cols":10,"rows_kept":65,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-22T21:30:37.640"]
["2010-03-23",144,{"v":20.23316605976288,"d":"20"},{"v":3.0073231421356343,"d":"3.007"},{"v":146.16206588931453,"d":"146.162"},{"v":1120.129036707609,"d":"1120.129"},"Forecast Zero Critical Issues Date(s) ->","2010-08-27T08:41:30.987",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":21.23316605976288,"d":"21"},{"v":3.055564396002818,"d":"3.056"},{"v":143.81087512921994,"d":"143.811"}]
["2010-03-25",146,{"v":22.23316605976288,"d":"22"},{"v":3.1015851406762702,"d":"3.102"},{"v":141.56790793879833,"d":"141.568"},"Date '0' ref",null,"2011-03-27T18:32:35.613",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":23.23316605976288,"d":"23"},{"v":3.1455808293491883,"d":"3.146"},{"v":139.42363828576325,"d":"139.424"},"2010-03-02T18:24:14.452"]
["2010-03-27",137,{"v":24.23316605976288,"d":"24"},{"v":3.1877221932242756,"d":"3.188"},{"v":137.36974504257185,"d":"137.370"}]
["2010-03-28",134,{"v":25.23316605976288,"d":"25"},{"v":3.2281592426818366,"d":"3.228"},{"v":135.39891697678684,"d":"135.399"},"Min '0' Ref"]
["2010-03-30",131,{"v":27.23316605976288,"d":"27"},{"v":3.3044355709426148,"d":"3.304"},{"v":131.68134780426,"d":"131.681"},"2010-03-22"]
["2010-04-01",131,{"v":29.23316605976288,"d":"29"},{"v":3.375303888678704,"d":"3.375"},{"v":128.22735520482865,"d":"128.227"}]
["2010-04-02",128,{"v":30.23316605976288,"d":"30"},{"v":3.4089395356845182,"d":"3.409"},{"v":126.58801509423361,"d":"126.588"}]
["2010-04-04",128,{"v":32.23316605976288,"d":"32"},{"v":3.472995924318404,"d":"3.473"},{"v":123.4660234997433,"d":"123.466"}]
["2010-04-05",130,{"v":33.23316605976288,"d":"33"},{"v":3.5035483549799813,"d":"3.504"},{"v":121.97695373245028,"d":"121.977"}]
["2010-04-06",127,{"v":34.23316605976288,"d":"34"},{"v":3.533194941976847,"d":"3.533"},{"v":120.53203313384228,"d":"120.532"}]
["2010-04-07",121,{"v":35.23316605976288,"d":"35"},{"v":3.5619878566025704,"d":"3.562"},{"v":119.1287189701894,"d":"119.129"}]
["2010-04-08",120,{"v":36.23316605976288,"d":"36"},{"v":3.589974888882516,"d":"3.590"},{"v":117.76468204278609,"d":"117.765"}]
["2010-04-09",116,{"v":37.23316605976288,"d":"37"},{"v":3.617199924821203,"d":"3.617"},{"v":116.43778342778495,"d":"116.438"}]
["2010-04-11",110,{"v":39.23316605976288,"d":"39"},{"v":3.6695224620315865,"d":"3.670"},{"v":113.88767835853335,"d":"113.888"}]
["2010-04-12",110,{"v":40.23316605976288,"d":"40"},{"v":3.694691681840061,"d":"3.695"},{"v":112.66097647355744,"d":"112.661"}]
["2010-04-13",109,{"v":41.23316605976288,"d":"41"},{"v":3.719242933966151,"d":"3.719"},{"v":111.46439320674307,"d":"111.464"}]
["2010-04-14",110,{"v":42.23316605976288,"d":"42"},{"v":3.7432058379509714,"d":"3.743"},{"v":110.29648495565863,"d":"110.296"}]
["2010-04-15",112,{"v":43.23316605976288,"d":"43"},{"v":3.766607933558821,"d":"3.767"},{"v":109.15590948240262,"d":"109.156"}]
["2010-04-18",112,{"v":46.23316605976288,"d":"46"},{"v":3.833697420616489,"d":"3.834"},{"v":105.88609020067832,"d":"105.886"}]
["2010-04-19",115,{"v":47.23316605976288,"d":"47"},{"v":3.855096316591687,"d":"3.855"},{"v":104.84314702528675,"d":"104.843"}]
["2010-04-20",100,{"v":48.23316605976288,"d":"48"},{"v":3.8760468769556344,"d":"3.876"},{"v":103.82205491018266,"d":"103.822"}]
["2010-04-22",95,{"v":50.23316605976288,"d":"50"},{"v":3.916675487027068,"d":"3.917"},{"v":101.84189052933056,"d":"101.842"}]
["2010-04-24",94,{"v":52.23316605976288,"d":"52"},{"v":3.955717658259182,"d":"3.956"},{"v":99.93904628511362,"d":"99.939"}]
["2010-04-27",97,{"v":55.23316605976288,"d":"55"},{"v":4.011563607270315,"d":"4.012"},{"v":97.21721654857336,"d":"97.217"}]
["2010-04-28",90,{"v":56.23316605976288,"d":"56"},{"v":4.0295067262456525,"d":"4.030"},{"v":96.34270164358682,"d":"96.343"}]
["2010-04-29",87,{"v":57.23316605976288,"d":"57"},{"v":4.0471335565711115,"d":"4.047"},{"v":95.4836020707383,"d":"95.484"}]
["2010-04-30",85,{"v":58.23316605976288,"d":"58"},{"v":4.064455055996618,"d":"4.064"},{"v":94.63938376927459,"d":"94.639"}]
["2010-05-02",86,{"v":60.23316605976288,"d":"60"},{"v":4.0982231318331825,"d":"4.098"},{"v":92.9935893189128,"d":"92.994"}]
["2010-05-06",86,{"v":64.23316605976288,"d":"64"},{"v":4.162519682593598,"d":"4.163"},{"v":89.85989266023873,"d":"89.860"}]
["2010-05-07",84,{"v":65.23316605976288,"d":"65"},{"v":4.177968021496032,"d":"4.178"},{"v":89.10696878752569,"d":"89.107"}]
["2010-05-08",89,{"v":66.23316605976288,"d":"66"},{"v":4.193181335367039,"d":"4.193"},{"v":88.36549960634707,"d":"88.365"}]
["2010-05-10",86,{"v":68.23316605976288,"d":"68"},{"v":4.222930752502669,"d":"4.223"},{"v":86.9155672542555,"d":"86.916"}]
["2010-05-12",84,{"v":70.23316605976288,"d":"70"},{"v":4.2518206504557075,"d":"4.252"},{"v":85.50752630004916,"d":"85.508"}]
["2010-05-13",86,{"v":71.23316605976288,"d":"71"},{"v":4.265958525405702,"d":"4.266"},{"v":84.81847205114181,"d":"84.818"}]
["2010-05-14",82,{"v":72.23316605976288,"d":"72"},{"v":4.279899304132199,"d":"4.280"},{"v":84.13902391282221,"d":"84.139"}]
["2010-05-16",80,{"v":74.23316605976288,"d":"74"},{"v":4.3072110322441715,"d":"4.307"},{"v":82.80790007935218,"d":"82.808"}]
["2010-05-18",78,{"v":76.23316605976288,"d":"76"},{"v":4.333796618126861,"d":"4.334"},{"v":81.51216709423585,"d":"81.512"}]
["2010-05-20",77,{"v":78.23316605976288,"d":"78"},{"v":4.359693676049764,"d":"4.360"},{"v":80.24999170655624,"d":"80.250"}]
["2010-05-25",80,{"v":83.23316605976288,"d":"83"},{"v":4.42164589892112,"d":"4.422"},{"v":77.23055331501934,"d":"77.231"}]
["2010-05-28",82,{"v":86.23316605976288,"d":"86"},{"v":4.45705486074344,"d":"4.457"},{"v":75.50478507337303,"d":"75.505"}]
["2010-06-01",79,{"v":90.23316605976288,"d":"90"},{"v":4.50239705416132,"d":"4.502"},{"v":73.29488923401425,"d":"73.295"}]
["2010-06-02",78,{"v":91.23316605976288,"d":"91"},{"v":4.5134184939069435,"d":"4.513"},{"v":72.7577243550873,"d":"72.758"}]
["2010-06-03",78,{"v":92.23316605976288,"d":"92"},{"v":4.524319784531831,"d":"4.524"},{"v":72.22641532524932,"d":"72.226"}]
["2010-06-04",79,{"v":93.23316605976288,"d":"93"},{"v":4.535103517399077,"d":"4.535"},{"v":71.70083584618763,"d":"71.701"}]
["2010-06-05",73,{"v":94.23316605976288,"d":"94"},{"v":4.545772200930067,"d":"4.546"},{"v":71.18086366201726,"d":"71.181"}]
["2010-06-07",72,{"v":96.23316605976288,"d":"96"},{"v":4.566774059791055,"d":"4.567"},{"v":70.15727135169473,"d":"70.157"}]
["2010-06-08",68,{"v":97.23316605976288,"d":"97"},{"v":4.577111867872542,"d":"4.577"},{"v":69.65342543368143,"d":"69.653"}]
["2010-06-09",67,{"v":98.23316605976288,"d":"98"},{"v":4.587343898255252,"d":"4.587"},{"v":69.15473492785279,"d":"69.155"}]
["2010-06-10",66,{"v":99.23316605976288,"d":"99"},{"v":4.59747229369311,"d":"4.597"},{"v":68.66109540028913,"d":"68.661"}]
["2010-06-11",67,{"v":100.23316605976288,"d":"100"},{"v":4.607499132483241,"d":"4.607"},{"v":68.17240555857771,"d":"68.172"}]
["2010-06-12",66,{"v":101.23316605976288,"d":"101"},{"v":4.617426431025589,"d":"4.617"},{"v":67.68856712706159,"d":"67.689"}]
["2010-06-13",67,{"v":102.23316605976288,"d":"102"},{"v":4.62725614625672,"d":"4.627"},{"v":67.20948472822042,"d":"67.209"}]
["2010-06-14",68,{"v":103.23316605976288,"d":"103"},{"v":4.636990177965171,"d":"4.637"},{"v":66.73506576982456,"d":"66.735"}]
["2010-06-15",66,{"v":104.23316605976288,"d":"104"},{"v":4.646630370995194,"d":"4.647"},{"v":66.2652203375288,"d":"66.265"}]
["2010-06-16",67,{"v":105.23316605976288,"d":"105"},{"v":4.656178517345281,"d":"4.656"},{"v":65.79986109259369,"d":"65.800"}]
["2010-06-17",65,{"v":106.23316605976288,"d":"106"},{"v":4.665636358167461,"d":"4.666"},{"v":65.33890317444383,"d":"65.339"}]
["2010-06-18",65,{"v":107.23316605976288,"d":"107"},{"v":4.675005585672914,"d":"4.675"},{"v":64.88226410779157,"d":"64.882"}]
["2010-06-19",64,{"v":108.23316605976288,"d":"108"},{"v":4.6842878449491625,"d":"4.684"},{"v":64.4298637140704,"d":"64.430"}]
["2010-06-20",60,{"v":109.23316605976288,"d":"109"},{"v":4.693484735693676,"d":"4.693"},{"v":63.98162402694214,"d":"63.982"}]
["2010-06-21",55,{"v":110.23316605976288,"d":"110"},{"v":4.702597813868497,"d":"4.703"},{"v":63.537469211653786,"d":"63.537"}]
["2010-06-22",59,{"v":111.23316605976288,"d":"111"},{"v":4.7116285932801425,"d":"4.712"},{"v":63.09732548803558,"d":"63.097"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}