{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":67,"n_cols":10,"rows_kept":67,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-25T23:19:09.390"]
["2010-03-23",144,{"v":25.718491933010228,"d":"26"},{"v":3.2472102636305573,"d":"3.247"},{"v":144.65154392539816,"d":"144.652"},{"v":1473.2751547850944,"d":"1473.275"},"Forecast Zero Critical Issues Date(s) ->","2010-08-26T05:01:46.035",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":26.718491933010228,"d":"27"},{"v":3.2853559074428182,"d":"3.285"},{"v":142.56577909629345,"d":"142.566"}]
["2010-03-25",146,{"v":27.718491933010228,"d":"28"},{"v":3.322099769270715,"d":"3.322"},{"v":140.55666227385103,"d":"140.557"},"Date '0' ref",null,"2011-02-04T16:04:46.600",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":28.718491933010228,"d":"29"},{"v":3.357541233505061,"d":"3.358"},{"v":138.61875922112523,"d":"138.619"},"2010-02-25T06:45:22.297"]
["2010-03-27",137,{"v":29.718491933010228,"d":"30"},{"v":3.3917694760658232,"d":"3.392"},{"v":136.747193889926,"d":"136.747"}]
["2010-03-28",134,{"v":30.718491933010228,"d":"31"},{"v":3.424864816352159,"d":"3.425"},{"v":134.9375744975721,"d":"134.938"},"Min '0' Ref"]
["2010-03-30",131,{"v":32.71849193301023,"d":"33"},{"v":3.487940420605442,"d":"3.488"},{"v":131.48866490324147,"d":"131.489"},"2010-03-22"]
["2010-04-01",131,{"v":34.71849193301023,"d":"35"},{"v":3.5472724537396654,"d":"3.547"},{"v":128.24444995278202,"d":"128.244"}]
["2010-04-02",128,{"v":35.71849193301023,"d":"36"},{"v":3.575668535996392,"d":"3.576"},{"v":126.69178118811413,"d":"126.692"}]
["2010-04-04",128,{"v":37.71849193301023,"d":"38"},{"v":3.6301504763989456,"d":"3.630"},{"v":123.712764352737,"d":"123.713"}]
["2010-04-05",130,{"v":38.71849193301023,"d":"39"},{"v":3.6563173136387834,"d":"3.656"},{"v":122.28198842790601,"d":"122.282"}]
["2010-04-06",127,{"v":39.71849193301023,"d":"40"},{"v":3.6818168710093175,"d":"3.682"},{"v":120.88769868454867,"d":"120.888"}]
["2010-04-07",121,{"v":40.71849193301023,"d":"41"},{"v":3.7066823365125,"d":"3.707"},{"v":119.52808043662742,"d":"119.528"}]
["2010-04-08",120,{"v":41.71849193301023,"d":"42"},{"v":3.7309444821400803,"d":"3.731"},{"v":118.20145110307405,"d":"118.201"}]
["2010-04-09",116,{"v":42.71849193301023,"d":"43"},{"v":3.7546318928352567,"d":"3.755"},{"v":116.90624768840058,"d":"116.906"}]
["2010-04-11",110,{"v":44.71849193301023,"d":"45"},{"v":3.8003871058500147,"d":"3.800"},{"v":114.40439939022869,"d":"114.404"}]
["2010-04-12",110,{"v":45.71849193301023,"d":"46"},{"v":3.822502853540302,"d":"3.823"},{"v":113.19513290284729,"d":"113.195"}]
["2010-04-13",109,{"v":46.71849193301023,"d":"47"},{"v":3.844140059167882,"d":"3.844"},{"v":112.01203260651394,"d":"112.012"}]
["2010-04-14",110,{"v":47.71849193301023,"d":"48"},{"v":3.865318994320672,"d":"3.865"},{"v":110.85399007151338,"d":"110.854"}]
["2010-04-15",112,{"v":48.71849193301023,"d":"49"},{"v":3.8860586691666166,"d":"3.886"},{"v":109.7199658412857,"d":"109.720"}]
["2010-04-18",112,{"v":51.71849193301023,"d":"52"},{"v":3.9458153951840798,"d":"3.946"},{"v":106.45252911789214,"d":"106.453"}]
["2010-04-19",115,{"v":52.71849193301023,"d":"53"},{"v":3.964966284569072,"d":"3.965"},{"v":105.40537805335953,"d":"105.405"}]
["2010-04-20",100,{"v":53.71849193301023,"d":"54"},{"v":3.9837572985322156,"d":"3.984"},{"v":104.37790460919805,"d":"104.378"}]
["2010-04-22",95,{"v":55.71849193301023,"d":"56"},{"v":4.020312083452199,"d":"4.020"},{"v":102.3791263188948,"d":"102.379"}]
["2010-04-24",94,{"v":57.71849193301023,"d":"58"},{"v":4.055577606277621,"d":"4.056"},{"v":100.45084356264431,"d":"100.451"}]
["2010-04-27",97,{"v":60.71849193301023,"d":"61"},{"v":4.10624829636607,"d":"4.106"},{"v":97.6802220003735,"d":"97.680"}]
["2010-04-28",90,{"v":61.71849193301023,"d":"62"},{"v":4.122583593188185,"d":"4.123"},{"v":96.78702466040355,"d":"96.787"}]
["2010-04-29",87,{"v":62.71849193301023,"d":"63"},{"v":4.138656331317657,"d":"4.139"},{"v":95.9081837614832,"d":"95.908"}]
["2010-04-30",85,{"v":63.71849193301023,"d":"64"},{"v":4.1544748176715425,"d":"4.154"},{"v":95.04324508987526,"d":"95.043"}]
["2010-05-02",86,{"v":65.71849193301023,"d":"66"},{"v":4.185380346055666,"d":"4.185"},{"v":93.35336237493775,"d":"93.353"}]
["2010-05-06",86,{"v":69.71849193301023,"d":"70"},{"v":4.2444655900824,"d":"4.244"},{"v":90.122641600724,"d":"90.123"}]
["2010-05-07",84,{"v":70.71849193301023,"d":"71"},{"v":4.258707093625353,"d":"4.259"},{"v":89.34393073796713,"d":"89.344"}]
["2010-05-08",89,{"v":71.71849193301023,"d":"72"},{"v":4.272748621368762,"d":"4.273"},{"v":88.57615434760805,"d":"88.576"}]
["2010-05-10",86,{"v":73.71849193301023,"d":"74"},{"v":4.300253675905054,"d":"4.300"},{"v":87.07220606830373,"d":"87.072"}]
["2010-05-12",84,{"v":75.71849193301023,"d":"76"},{"v":4.327022409780008,"d":"4.327"},{"v":85.60851905044049,"d":"85.609"}]
["2010-05-13",86,{"v":76.71849193301023,"d":"77"},{"v":4.34014277361726,"d":"4.340"},{"v":84.89111096128923,"d":"84.891"}]
["2010-05-14",82,{"v":77.71849193301023,"d":"78"},{"v":4.35309322047397,"d":"4.353"},{"v":84.18299375902475,"d":"84.183"}]
["2010-05-16",80,{"v":79.71849193301023,"d":"80"},{"v":4.378501578118628,"d":"4.379"},{"v":82.79369072349687,"d":"82.794"}]
["2010-05-18",78,{"v":81.71849193301023,"d":"82"},{"v":4.403280315704378,"d":"4.403"},{"v":81.43881466948827,"d":"81.439"}]
["2010-05-20",77,{"v":83.71849193301023,"d":"84"},{"v":4.427459884193034,"d":"4.427"},{"v":80.11670056951974,"d":"80.117"}]
["2010-05-25",80,{"v":88.71849193301023,"d":"89"},{"v":4.485468344847713,"d":"4.485"},{"v":76.94485720990804,"d":"76.945"}]
["2010-05-28",82,{"v":91.71849193301023,"d":"92"},{"v":4.51872401578094,"d":"4.519"},{"v":75.12647110159676,"d":"75.126"}]
["2010-06-01",79,{"v":95.71849193301023,"d":"96"},{"v":4.561411507932884,"d":"4.561"},{"v":72.79236264582102,"d":"72.792"}]
["2010-06-02",78,{"v":96.71849193301023,"d":"97"},{"v":4.571804614094514,"d":"4.572"},{"v":72.22407821985172,"d":"72.224"}]
["2010-06-03",78,{"v":97.71849193301023,"d":"98"},{"v":4.582090813738838,"d":"4.582"},{"v":71.66163933301914,"d":"71.662"}]
["2010-06-04",79,{"v":98.71849193301023,"d":"99"},{"v":4.59227228383507,"d":"4.592"},{"v":71.10492695087095,"d":"71.105"}]
["2010-06-05",73,{"v":99.71849193301023,"d":"100"},{"v":4.602351135526665,"d":"4.602"},{"v":70.55382563823991,"d":"70.554"}]
["2010-06-07",72,{"v":101.71849193301023,"d":"102"},{"v":4.622209114775616,"d":"4.622"},{"v":69.46801162240095,"d":"69.468"}]
["2010-06-08",68,{"v":102.71849193301023,"d":"103"},{"v":4.631992158496362,"d":"4.632"},{"v":68.9330847873801,"d":"68.933"}]
["2010-06-09",67,{"v":103.71849193301023,"d":"104"},{"v":4.64168042077504,"d":"4.642"},{"v":68.40334050477051,"d":"68.403"}]
["2010-06-10",66,{"v":104.71849193301023,"d":"105"},{"v":4.651275720552669,"d":"4.651"},{"v":67.87867931673563,"d":"67.879"}]
["2010-06-11",67,{"v":105.71849193301023,"d":"106"},{"v":4.660779824906861,"d":"4.661"},{"v":67.35900460127723,"d":"67.359"}]
["2010-06-12",66,{"v":106.71849193301023,"d":"107"},{"v":4.6701944510049715,"d":"4.670"},{"v":66.84422246543875,"d":"66.844"}]
["2010-06-13",67,{"v":107.71849193301023,"d":"108"},{"v":4.6795212679661775,"d":"4.680"},{"v":66.33424164348895,"d":"66.334"}]
["2010-06-14",68,{"v":108.71849193301023,"d":"109"},{"v":4.688761898637506,"d":"4.689"},{"v":65.82897339981054,"d":"65.829"}]
["2010-06-15",66,{"v":109.71849193301023,"d":"110"},{"v":4.697917921288562,"d":"4.698"},{"v":65.32833143623407,"d":"65.328"}]
["2010-06-16",67,{"v":110.71849193301023,"d":"111"},{"v":4.706990871229364,"d":"4.707"},{"v":64.8322318035764,"d":"64.832"}]
["2010-06-17",65,{"v":111.71849193301023,"d":"112"},{"v":4.715982242355455,"d":"4.716"},{"v":64.34059281715565,"d":"64.341"}]
["2010-06-18",65,{"v":112.71849193301023,"d":"113"},{"v":4.724893488624154,"d":"4.725"},{"v":63.85333497607104,"d":"63.853"}]
["2010-06-19",64,{"v":113.71849193301023,"d":"114"},{"v":4.733726025465623,"d":"4.734"},{"v":63.370380886047656,"d":"63.370"}]
["2010-06-20",60,{"v":114.71849193301023,"d":"115"},{"v":4.74248123113215,"d":"4.742"},{"v":62.89165518565852,"d":"62.892"}]
["2010-06-21",55,{"v":115.71849193301023,"d":"116"},{"v":4.751160447988885,"d":"4.751"},{"v":62.41708447574871,"d":"62.417"}]
["2010-06-22",59,{"v":116.71849193301023,"d":"117"},{"v":4.759764983749038,"d":"4.760"},{"v":61.946597251896094,"d":"61.947"}]
["2010-06-24",54,{"v":118.71849193301023,"d":"119"},{"v":4.776755076617789,"d":"4.777"},{"v":61.01759633312088,"d":"61.018"}]
["2010-06-25",44,{"v":119.71849193301023,"d":"120"},{"v":4.785143086288139,"d":"4.785"},{"v":60.55894853462746,"d":"60.559"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}