{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":69,"n_cols":10,"rows_kept":69,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-28T22:38:22.290"]
["2010-03-23",144,{"v":35.751331898747594,"d":"36"},{"v":3.5765875243550562,"d":"3.577"},{"v":142.76208660712746,"d":"142.762"},{"v":1961.392243969347,"d":"1961.392"},"Forecast Zero Critical Issues Date(s) ->","2010-08-24T11:41:04.450",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":36.751331898747594,"d":"37"},{"v":3.6041744671449067,"d":"3.604"},{"v":140.96636608184474,"d":"140.966"}]
["2010-03-25",146,{"v":37.751331898747594,"d":"38"},{"v":3.6310207571586646,"d":"3.631"},{"v":139.21885696593307,"d":"139.219"},"Date '0' ref",null,"2010-12-16T06:18:26.384",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":38.751331898747594,"d":"39"},{"v":3.6571651267892498,"d":"3.657"},{"v":137.5170380466039,"d":"137.517"},"2010-02-15T05:58:04.924"]
["2010-03-27",137,{"v":39.751331898747594,"d":"40"},{"v":3.6826433474257296,"d":"3.683"},{"v":135.858580852085,"d":"135.859"}]
["2010-03-28",134,{"v":40.751331898747594,"d":"41"},{"v":3.7074885237845834,"d":"3.707"},{"v":134.24133049267667,"d":"134.241"},"Min '0' Ref"]
["2010-03-30",131,{"v":42.751331898747594,"d":"43"},{"v":3.7554003504237055,"d":"3.755"},{"v":131.12259960774108,"d":"131.123"},"2010-03-22"]
["2010-04-01",131,{"v":44.751331898747594,"d":"45"},{"v":3.801121207378457,"d":"3.801"},{"v":128.1464858030114,"d":"128.146"}]
["2010-04-02",128,{"v":45.751331898747594,"d":"46"},{"v":3.8232209038386995,"d":"3.823"},{"v":126.70794733071733,"d":"126.708"}]
["2010-04-04",128,{"v":47.751331898747594,"d":"48"},{"v":3.866006959705221,"d":"3.866"},{"v":123.92286892240335,"d":"123.923"}]
["2010-04-05",130,{"v":48.751331898747594,"d":"49"},{"v":3.886732518070595,"d":"3.887"},{"v":122.57377740334096,"d":"122.574"}]
["2010-04-06",127,{"v":49.751331898747594,"d":"50"},{"v":3.9070372350803653,"d":"3.907"},{"v":121.25207976644603,"d":"121.252"}]
["2010-04-07",121,{"v":50.751331898747594,"d":"51"},{"v":3.926937861887818,"d":"3.927"},{"v":119.95668562667632,"d":"119.957"}]
["2010-04-08",120,{"v":51.751331898747594,"d":"52"},{"v":3.9464501689881497,"d":"3.946"},{"v":118.68656843309674,"d":"118.687"}]
["2010-04-09",116,{"v":52.751331898747594,"d":"53"},{"v":3.9655890213027756,"d":"3.966"},{"v":117.44076058140638,"d":"117.441"}]
["2010-04-11",110,{"v":54.751331898747594,"d":"55"},{"v":4.00280169531848,"d":"4.003"},{"v":115.01847105698545,"d":"115.018"}]
["2010-04-12",110,{"v":55.751331898747594,"d":"56"},{"v":4.020901300615348,"d":"4.021"},{"v":113.84031104923497,"d":"113.840"}]
["2010-04-13",109,{"v":56.751331898747594,"d":"57"},{"v":4.038679125667561,"d":"4.039"},{"v":112.68309672562066,"d":"112.683"}]
["2010-04-14",110,{"v":57.751331898747594,"d":"58"},{"v":4.056146412317728,"d":"4.056"},{"v":111.5460963193907,"d":"111.546"}]
["2010-04-15",112,{"v":58.751331898747594,"d":"59"},{"v":4.073313823384274,"d":"4.073"},{"v":110.42861575429151,"d":"110.429"}]
["2010-04-18",112,{"v":61.751331898747594,"d":"62"},{"v":4.1231155444859615,"d":"4.123"},{"v":107.1868657184881,"d":"107.187"}]
["2010-04-19",115,{"v":62.751331898747594,"d":"63"},{"v":4.139179803264685,"d":"4.139"},{"v":106.14119279154744,"d":"106.141"}]
["2010-04-20",100,{"v":63.751331898747594,"d":"64"},{"v":4.154990076349664,"d":"4.155"},{"v":105.11205258905039,"d":"105.112"}]
["2010-04-22",95,{"v":65.7513318987476,"d":"66"},{"v":4.185879927867876,"d":"4.186"},{"v":103.10133538791871,"d":"103.101"}]
["2010-04-24",94,{"v":67.7513318987476,"d":"68"},{"v":4.215844118588679,"d":"4.216"},{"v":101.15087234782322,"d":"101.151"}]
["2010-04-27",97,{"v":70.7513318987476,"d":"71"},{"v":4.259171361770145,"d":"4.259"},{"v":98.33056636185154,"d":"98.331"}]
["2010-04-28",90,{"v":71.7513318987476,"d":"72"},{"v":4.273206417516186,"d":"4.273"},{"v":97.41698061700686,"d":"97.417"}]
["2010-04-29",87,{"v":72.7513318987476,"d":"73"},{"v":4.287047213770579,"d":"4.287"},{"v":96.51603983101245,"d":"96.516"}]
["2010-04-30",85,{"v":73.7513318987476,"d":"74"},{"v":4.300699054700891,"d":"4.301"},{"v":95.62739873898562,"d":"95.627"}]
["2010-05-02",86,{"v":75.7513318987476,"d":"76"},{"v":4.327456027056653,"d":"4.327"},{"v":93.88570358923016,"d":"93.886"}]
["2010-05-06",86,{"v":79.7513318987476,"d":"80"},{"v":4.37891344245023,"d":"4.379"},{"v":90.53617922532561,"d":"90.536"}]
["2010-05-07",84,{"v":80.7513318987476,"d":"81"},{"v":4.391374456068877,"d":"4.391"},{"v":89.7250528134108,"d":"89.725"}]
["2010-05-08",89,{"v":81.7513318987476,"d":"82"},{"v":4.403682101984064,"d":"4.404"},{"v":88.9239095857551,"d":"88.924"}]
["2010-05-10",86,{"v":83.7513318987476,"d":"84"},{"v":4.427852073847348,"d":"4.428"},{"v":87.35061040211474,"d":"87.351"}]
["2010-05-12",84,{"v":85.7513318987476,"d":"86"},{"v":4.451451618272334,"d":"4.451"},{"v":85.81444212735903,"d":"85.814"}]
["2010-05-13",86,{"v":86.7513318987476,"d":"87"},{"v":4.463045772008792,"d":"4.463"},{"v":85.05974234070851,"d":"85.060"}]
["2010-05-14",82,{"v":87.7513318987476,"d":"88"},{"v":4.474507040564092,"d":"4.475"},{"v":84.31369246677684,"d":"84.314"}]
["2010-05-16",80,{"v":89.7513318987476,"d":"90"},{"v":4.497042867355741,"d":"4.497"},{"v":82.84676490498589,"d":"82.847"}]
["2010-05-18",78,{"v":91.7513318987476,"d":"92"},{"v":4.519082003436918,"d":"4.519"},{"v":81.41216849747718,"d":"81.412"}]
["2010-05-20",77,{"v":93.7513318987476,"d":"94"},{"v":4.540645871669577,"d":"4.541"},{"v":80.00850876305657,"d":"80.009"}]
["2010-05-25",80,{"v":98.7513318987476,"d":"99"},{"v":4.592604891272528,"d":"4.593"},{"v":76.62633340983427,"d":"76.626"}]
["2010-05-28",82,{"v":101.7513318987476,"d":"102"},{"v":4.622531914151013,"d":"4.623"},{"v":74.67828974102758,"d":"74.678"}]
["2010-06-01",79,{"v":105.7513318987476,"d":"106"},{"v":4.661090412634285,"d":"4.661"},{"v":72.16839628607153,"d":"72.168"}]
["2010-06-02",78,{"v":106.7513318987476,"d":"107"},{"v":4.670502128834156,"d":"4.671"},{"v":71.55575819539979,"d":"71.556"}]
["2010-06-03",78,{"v":107.7513318987476,"d":"108"},{"v":4.679826089916719,"d":"4.680"},{"v":70.9488323602161,"d":"70.949"}]
["2010-06-04",79,{"v":108.7513318987476,"d":"109"},{"v":4.689063917238601,"d":"4.689"},{"v":70.34751324133845,"d":"70.348"}]
["2010-06-05",73,{"v":109.7513318987476,"d":"110"},{"v":4.69821718763333,"d":"4.698"},{"v":69.75169819773294,"d":"69.752"}]
["2010-06-07",72,{"v":111.7513318987476,"d":"112"},{"v":4.716276151979678,"d":"4.716"},{"v":68.57618363676397,"d":"68.576"}]
["2010-06-08",68,{"v":112.7513318987476,"d":"113"},{"v":4.725184791162219,"d":"4.725"},{"v":67.99629240509364,"d":"67.996"}]
["2010-06-09",67,{"v":113.7513318987476,"d":"114"},{"v":4.734014766762489,"d":"4.734"},{"v":67.42152163241548,"d":"67.422"}]
["2010-06-10",66,{"v":114.7513318987476,"d":"115"},{"v":4.742767455834057,"d":"4.743"},{"v":66.85178168199894,"d":"66.852"}]
["2010-06-11",67,{"v":115.7513318987476,"d":"116"},{"v":4.751444199584786,"d":"4.751"},{"v":66.28698525042279,"d":"66.287"}]
["2010-06-12",66,{"v":116.7513318987476,"d":"117"},{"v":4.760046304610253,"d":"4.760"},{"v":65.72704728728792,"d":"65.727"}]
["2010-06-13",67,{"v":117.7513318987476,"d":"118"},{"v":4.7685750440745736,"d":"4.769"},{"v":65.17188491835356,"d":"65.172"}]
["2010-06-14",68,{"v":118.7513318987476,"d":"119"},{"v":4.777031658841305,"d":"4.777"},{"v":64.62141737192377,"d":"64.621"}]
["2010-06-15",66,{"v":119.7513318987476,"d":"120"},{"v":4.785417358556918,"d":"4.785"},{"v":64.07556590832036,"d":"64.076"}]
["2010-06-16",67,{"v":120.7513318987476,"d":"121"},{"v":4.793733322689221,"d":"4.794"},{"v":63.53425375228886,"d":"63.534"}]
["2010-06-17",65,{"v":121.7513318987476,"d":"122"},{"v":4.801980701522965,"d":"4.802"},{"v":62.99740602819145,"d":"62.997"}]
["2010-06-18",65,{"v":122.7513318987476,"d":"123"},{"v":4.810160617114726,"d":"4.810"},{"v":62.46494969785067,"d":"62.465"}]
["2010-06-19",64,{"v":123.7513318987476,"d":"124"},{"v":4.818274164209043,"d":"4.818"},{"v":61.93681350091498,"d":"61.937"}]
["2010-06-20",60,{"v":124.7513318987476,"d":"125"},{"v":4.826322411117701,"d":"4.826"},{"v":61.41292789762383,"d":"61.413"}]
["2010-06-21",55,{"v":125.7513318987476,"d":"126"},{"v":4.834306400563897,"d":"4.834"},{"v":60.89322501385777,"d":"60.893"}]
["2010-06-22",59,{"v":126.7513318987476,"d":"127"},{"v":4.842227150492987,"d":"4.842"},{"v":60.37763858836479,"d":"60.378"}]
["2010-06-24",54,{"v":128.7513318987476,"d":"129"},{"v":4.8578828843349795,"d":"4.858"},{"v":59.35855782930469,"d":"59.359"}]
["2010-06-25",44,{"v":129.7513318987476,"d":"130"},{"v":4.8656197871089,"d":"4.866"},{"v":58.85493859106282,"d":"58.855"}]
["2010-06-27",45,{"v":131.7513318987476,"d":"132"},{"v":4.88091629665878,"d":"4.881"},{"v":57.85924086648532,"d":"57.859"}]
["2010-06-28",41,{"v":132.7513318987476,"d":"133"},{"v":4.8884776932072915,"d":"4.888"},{"v":57.367045878247666,"d":"57.367"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}