{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":70,"n_cols":10,"rows_kept":70,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-06-29T22:26:17.460"]
["2010-03-23",144,{"v":43.734131423821964,"d":"44"},{"v":3.778128836695687,"d":"3.778"},{"v":141.71822313733054,"d":"141.718"},{"v":2260.925292655269,"d":"2260.925"},"Forecast Zero Critical Issues Date(s) ->","2010-08-23T11:05:27.918",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":44.734131423821964,"d":"45"},{"v":3.800736776779367,"d":"3.801"},{"v":140.06498116811582,"d":"140.065"}]
["2010-03-25",146,{"v":45.734131423821964,"d":"46"},{"v":3.822844877429615,"d":"3.823"},{"v":138.4482907611469,"d":"138.448"},"Date '0' ref",null,"2010-11-23T08:29:55.773",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":46.734131423821964,"d":"47"},{"v":3.844474763329113,"d":"3.844"},{"v":136.866570576733,"d":"136.867"},"2010-02-07T06:22:51.045"]
["2010-03-27",137,{"v":47.734131423821964,"d":"48"},{"v":3.8656466854914684,"d":"3.866"},{"v":135.31833972694318,"d":"135.318"}]
["2010-03-28",134,{"v":48.734131423821964,"d":"49"},{"v":3.886379635199285,"d":"3.886"},{"v":133.80220944370154,"d":"133.802"},"Min '0' Ref"]
["2010-03-30",131,{"v":50.734131423821964,"d":"51"},{"v":3.9265988877229043,"d":"3.927"},{"v":130.86111193564102,"d":"130.861"},"2010-03-22"]
["2010-04-01",131,{"v":52.734131423821964,"d":"53"},{"v":3.9652629010102483,"d":"3.965"},{"v":128.03374379735334,"d":"128.034"}]
["2010-04-02",128,{"v":53.734131423821964,"d":"54"},{"v":3.9840483940947733,"d":"3.984"},{"v":126.66002441094412,"d":"126.660"}]
["2010-04-04",128,{"v":55.734131423821964,"d":"56"},{"v":4.020592731685382,"d":"4.021"},{"v":123.98766096614008,"d":"123.988"}]
["2010-04-05",130,{"v":56.734131423821964,"d":"57"},{"v":4.038375994772136,"d":"4.038"},{"v":122.68723125977198,"d":"122.687"}]
["2010-04-06",127,{"v":57.734131423821964,"d":"58"},{"v":4.055848531102934,"d":"4.056"},{"v":121.40952394704084,"d":"121.410"}]
["2010-04-07",121,{"v":58.734131423821964,"d":"59"},{"v":4.073021013115461,"d":"4.073"},{"v":120.15375858878122,"d":"120.154"}]
["2010-04-08",120,{"v":59.734131423821964,"d":"60"},{"v":4.089903572673341,"d":"4.090"},{"v":118.91919427617484,"d":"118.919"}]
["2010-04-09",116,{"v":60.734131423821964,"d":"61"},{"v":4.106505836968585,"d":"4.107"},{"v":117.70512700532663,"d":"117.705"}]
["2010-04-11",110,{"v":62.734131423821964,"d":"63"},{"v":4.138905660354775,"d":"4.139"},{"v":115.33583782555479,"d":"115.336"}]
["2010-04-12",110,{"v":63.734131423821964,"d":"64"},{"v":4.15472023421109,"d":"4.155"},{"v":114.17937168455597,"d":"114.179"}]
["2010-04-13",109,{"v":64.73413142382196,"d":"65"},{"v":4.170288596008407,"d":"4.170"},{"v":113.04091019624798,"d":"113.041"}]
["2010-04-14",110,{"v":65.73413142382196,"d":"66"},{"v":4.185618294762754,"d":"4.186"},{"v":111.91990132669605,"d":"111.920"}]
["2010-04-15",112,{"v":66.73413142382196,"d":"67"},{"v":4.200716537539429,"d":"4.201"},{"v":110.8158180476621,"d":"110.816"}]
["2010-04-18",112,{"v":69.73413142382196,"d":"70"},{"v":4.24468988834945,"d":"4.245"},{"v":107.60019606631187,"d":"107.600"}]
["2010-04-19",115,{"v":70.73413142382196,"d":"71"},{"v":4.258928220537026,"d":"4.259"},{"v":106.55899513172898,"d":"106.559"}]
["2010-04-20",100,{"v":71.73413142382196,"d":"72"},{"v":4.272966665354403,"d":"4.273"},{"v":105.53241128248453,"d":"105.532"}]
["2010-04-22",95,{"v":73.73413142382196,"d":"74"},{"v":4.300465804933543,"d":"4.300"},{"v":103.52149248575853,"d":"103.521"}]
["2010-04-24",94,{"v":75.73413142382196,"d":"76"},{"v":4.327228936290024,"d":"4.327"},{"v":101.56439547371889,"d":"101.564"}]
["2010-04-27",97,{"v":78.73413142382196,"d":"79"},{"v":4.36607675167149,"d":"4.366"},{"v":98.72358651176893,"d":"98.724"}]
["2010-04-28",90,{"v":79.73413142382196,"d":"80"},{"v":4.378697742854367,"d":"4.379"},{"v":97.80065623862635,"d":"97.801"}]
["2010-04-29",87,{"v":80.73413142382196,"d":"81"},{"v":4.391161427915918,"d":"4.391"},{"v":96.88922922853334,"d":"96.889"}]
["2010-04-30",85,{"v":81.73413142382196,"d":"82"},{"v":4.403471679911795,"d":"4.403"},{"v":95.98902225806796,"d":"95.989"}]
["2010-05-02",86,{"v":83.73413142382196,"d":"84"},{"v":4.427646677215964,"d":"4.428"},{"v":94.22118670998293,"d":"94.221"}]
["2010-05-06",86,{"v":87.73413142382196,"d":"88"},{"v":4.4743110075177634,"d":"4.474"},{"v":90.8087825265552,"d":"90.809"}]
["2010-05-07",84,{"v":88.73413142382196,"d":"89"},{"v":4.485644611510402,"d":"4.486"},{"v":89.97999451164821,"d":"89.980"}]
["2010-05-08",89,{"v":89.73413142382196,"d":"90"},{"v":4.496851203087673,"d":"4.497"},{"v":89.16049448383421,"d":"89.160"}]
["2010-05-10",86,{"v":91.73413142382196,"d":"92"},{"v":4.518894517467571,"d":"4.519"},{"v":87.54854167705241,"d":"87.549"}]
["2010-05-12",84,{"v":93.73413142382196,"d":"94"},{"v":4.5404623857110495,"d":"4.540"},{"v":85.97135663345125,"d":"85.971"}]
["2010-05-13",86,{"v":94.73413142382196,"d":"95"},{"v":4.551074351559917,"d":"4.551"},{"v":85.19533956810676,"d":"85.195"}]
["2010-05-14",82,{"v":95.73413142382196,"d":"96"},{"v":4.561574885071022,"d":"4.562"},{"v":84.42747117162975,"d":"84.427"}]
["2010-05-16",80,{"v":97.73413142382196,"d":"98"},{"v":4.582250847311952,"d":"4.582"},{"v":82.91550818853244,"d":"82.916"}]
["2010-05-18",78,{"v":99.73413142382196,"d":"100"},{"v":4.602507959644399,"d":"4.603"},{"v":81.43417427844867,"d":"81.434"}]
["2010-05-20",77,{"v":101.73413142382196,"d":"102"},{"v":4.622362855637587,"d":"4.622"},{"v":79.98225308488412,"d":"79.982"}]
["2010-05-25",80,{"v":106.73413142382196,"d":"107"},{"v":4.670340989291489,"d":"4.670"},{"v":76.4737749189108,"d":"76.474"}]
["2010-05-28",82,{"v":109.73413142382196,"d":"110"},{"v":4.698060453107949,"d":"4.698"},{"v":74.44674455807831,"d":"74.447"}]
["2010-06-01",79,{"v":113.73413142382196,"d":"114"},{"v":4.733863544133076,"d":"4.734"},{"v":71.82858596020225,"d":"71.829"}]
["2010-06-02",78,{"v":114.73413142382196,"d":"115"},{"v":4.742617551132393,"d":"4.743"},{"v":71.18843512308467,"d":"71.188"}]
["2010-06-03",78,{"v":115.73413142382196,"d":"116"},{"v":4.75129559003747,"d":"4.751"},{"v":70.55383957500516,"d":"70.554"}]
["2010-06-04",79,{"v":116.73413142382196,"d":"117"},{"v":4.7598989680291055,"d":"4.760"},{"v":69.92470372626605,"d":"69.925"}]
["2010-06-05",73,{"v":117.73413142382196,"d":"118"},{"v":4.768428958836754,"d":"4.768"},{"v":69.30093443335284,"d":"69.301"}]
["2010-06-07",72,{"v":119.73413142382196,"d":"120"},{"v":4.785273713304162,"d":"4.785"},{"v":68.06913467877291,"d":"68.069"}]
["2010-06-08",68,{"v":120.73413142382196,"d":"121"},{"v":4.793590867116798,"d":"4.794"},{"v":67.46092943333389,"d":"67.461"}]
["2010-06-09",67,{"v":121.73413142382196,"d":"122"},{"v":4.801839416086706,"d":"4.802"},{"v":66.857741027327,"d":"66.858"}]
["2010-06-10",66,{"v":122.73413142382196,"d":"123"},{"v":4.810020482748145,"d":"4.810"},{"v":66.25948737362955,"d":"66.259"}]
["2010-06-11",67,{"v":123.73413142382196,"d":"124"},{"v":4.818135162307902,"d":"4.818"},{"v":65.66608838348435,"d":"65.666"}]
["2010-06-12",66,{"v":124.73413142382196,"d":"125"},{"v":4.826184523525183,"d":"4.826"},{"v":65.077465902156,"d":"65.077"}]
["2010-06-13",67,{"v":125.73413142382196,"d":"126"},{"v":4.834169609556376,"d":"4.834"},{"v":64.49354364715634,"d":"64.494"}]
["2010-06-14",68,{"v":126.73413142382196,"d":"127"},{"v":4.842091438766354,"d":"4.842"},{"v":63.914247148916786,"d":"63.914"}]
["2010-06-15",66,{"v":127.73413142382196,"d":"128"},{"v":4.849951005507892,"d":"4.850"},{"v":63.3395036937917,"d":"63.340"}]
["2010-06-16",67,{"v":128.73413142382196,"d":"129"},{"v":4.857749280870697,"d":"4.858"},{"v":62.76924226928497,"d":"62.769"}]
["2010-06-17",65,{"v":129.73413142382196,"d":"130"},{"v":4.865487213401452,"d":"4.865"},{"v":62.203393511395234,"d":"62.203"}]
["2010-06-18",65,{"v":130.73413142382196,"d":"131"},{"v":4.873165729796221,"d":"4.873"},{"v":61.64188965398279,"d":"61.642"}]
["2010-06-19",64,{"v":131.73413142382196,"d":"132"},{"v":4.880785735566467,"d":"4.881"},{"v":61.08466448006601,"d":"61.085"}]
["2010-06-20",60,{"v":132.73413142382196,"d":"133"},{"v":4.888348115679887,"d":"4.888"},{"v":60.53165327495907,"d":"60.532"}]
["2010-06-21",55,{"v":133.73413142382196,"d":"134"},{"v":4.8958537351772025,"d":"4.896"},{"v":59.98279278116843,"d":"59.983"}]
["2010-06-22",59,{"v":134.73413142382196,"d":"135"},{"v":4.90330343976597,"d":"4.903"},{"v":59.438021154969135,"d":"59.438"}]
["2010-06-24",54,{"v":136.73413142382196,"d":"137"},{"v":4.9180383937924,"d":"4.918"},{"v":58.360503949917415,"d":"58.361"}]
["2010-06-25",44,{"v":137.73413142382196,"d":"138"},{"v":4.925325243022023,"d":"4.925"},{"v":57.82764138370561,"d":"57.828"}]
["2010-06-27",45,{"v":139.73413142382196,"d":"140"},{"v":4.9397415558478555,"d":"4.940"},{"v":56.77342532878072,"d":"56.773"}]
["2010-06-28",41,{"v":140.73413142382196,"d":"141"},{"v":4.946872517671447,"d":"4.947"},{"v":56.251962279781424,"d":"56.252"}]
["2010-06-29",39,{"v":141.73413142382196,"d":"142"},{"v":4.9539529887139,"d":"4.954"},{"v":55.7341914503354,"d":"55.734"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}