{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":72,"n_cols":10,"rows_kept":72,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-01T21:52:37.730"]
["2010-03-23",144,{"v":68.10019742980512,"d":"68"},{"v":4.220980112267346,"d":"4.221"},{"v":139.73578835469544,"d":"139.736"},{"v":2819.6663742236424,"d":"2819.666"},"Forecast Zero Critical Issues Date(s) ->","2010-08-21T13:31:17.360",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":69.10019742980512,"d":"69"},{"v":4.235557587930254,"d":"4.236"},{"v":138.32266586995036,"d":"138.323"}]
["2010-03-25",146,{"v":70.10019742980512,"d":"70"},{"v":4.249925610438934,"d":"4.250"},{"v":136.9298475152607,"d":"136.930"},"Date '0' ref",null,"2010-10-18T08:32:18.717",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":71.10019742980512,"d":"71"},{"v":4.264090113595848,"d":"4.264"},{"v":135.55675807514535,"d":"135.557"},"2010-01-13T21:35:42.942"]
["2010-03-27",137,{"v":72.10019742980512,"d":"72"},{"v":4.278056782564618,"d":"4.278"},{"v":134.20284643686495,"d":"134.203"}]
["2010-03-28",134,{"v":73.10019742980512,"d":"73"},{"v":4.291831067570213,"d":"4.292"},{"v":132.86758426234314,"d":"132.868"},"Min '0' Ref"]
["2010-03-30",131,{"v":75.10019742980512,"d":"75"},{"v":4.318823187658846,"d":"4.319"},{"v":130.25100148146834,"d":"130.251"},"2010-03-22"]
["2010-04-01",131,{"v":77.10019742980512,"d":"77"},{"v":4.345105841263867,"d":"4.345"},{"v":127.70319350518577,"d":"127.703"}]
["2010-04-02",128,{"v":78.10019742980512,"d":"78"},{"v":4.357992584752882,"d":"4.358"},{"v":126.45396850899482,"d":"126.454"}]
["2010-04-04",128,{"v":80.10019742980512,"d":"80"},{"v":4.383278318862851,"d":"4.383"},{"v":124.00280067717324,"d":"124.003"}]
["2010-04-05",130,{"v":81.10019742980512,"d":"81"},{"v":4.395685395517974,"d":"4.396"},{"v":122.80007399137793,"d":"122.800"}]
["2010-04-06",127,{"v":82.10019742980512,"d":"82"},{"v":4.407940421203422,"d":"4.408"},{"v":121.61208693877046,"d":"121.612"}]
["2010-04-07",121,{"v":83.10019742980512,"d":"83"},{"v":4.420047077668509,"d":"4.420"},{"v":120.43848261511994,"d":"120.438"}]
["2010-04-08",120,{"v":84.10019742980512,"d":"84"},{"v":4.432008914536255,"d":"4.432"},{"v":119.27891692435526,"d":"119.279"}]
["2010-04-09",116,{"v":85.10019742980512,"d":"85"},{"v":4.443829355550846,"d":"4.444"},{"v":118.13305797294419,"d":"118.133"}]
["2010-04-11",110,{"v":87.10019742980512,"d":"87"},{"v":4.467059150558588,"d":"4.467"},{"v":115.88119033820783,"d":"115.881"}]
["2010-04-12",110,{"v":88.10019742980512,"d":"88"},{"v":4.478474773913574,"d":"4.478"},{"v":114.77457391069015,"d":"114.775"}]
["2010-04-13",109,{"v":89.10019742980512,"d":"89"},{"v":4.489761550297037,"d":"4.490"},{"v":113.68044774944099,"d":"113.680"}]
["2010-04-14",110,{"v":90.10019742980512,"d":"90"},{"v":4.500922355841693,"d":"4.501"},{"v":112.5985330457072,"d":"112.599"}]
["2010-04-15",112,{"v":91.10019742980512,"d":"91"},{"v":4.5119599714403495,"d":"4.512"},{"v":111.52856022317513,"d":"111.529"}]
["2010-04-18",112,{"v":94.10019742980512,"d":"94"},{"v":4.5443601446742035,"d":"4.544"},{"v":108.3877274503999,"d":"108.388"}]
["2010-04-19",115,{"v":95.10019742980512,"d":"95"},{"v":4.554931045572377,"d":"4.555"},{"v":107.36299737444921,"d":"107.363"}]
["2010-04-20",100,{"v":96.10019742980512,"d":"96"},{"v":4.565391370394585,"d":"4.565"},{"v":106.34898640671963,"d":"106.349"}]
["2010-04-22",95,{"v":98.10019742980512,"d":"98"},{"v":4.585989379105532,"d":"4.586"},{"v":104.3522408848267,"d":"104.352"}]
["2010-04-24",94,{"v":100.10019742980512,"d":"100"},{"v":4.606171658644955,"d":"4.606"},{"v":102.39579563531493,"d":"102.396"}]
["2010-04-27",97,{"v":103.10019742980512,"d":"103"},{"v":4.635701305956145,"d":"4.636"},{"v":99.53322809982507,"d":"99.533"}]
["2010-04-28",90,{"v":104.10019742980512,"d":"104"},{"v":4.645353872159039,"d":"4.645"},{"v":98.59752025491281,"d":"98.598"}]
["2010-04-29",87,{"v":105.10019742980512,"d":"105"},{"v":4.654914156375956,"d":"4.655"},{"v":97.67075811173498,"d":"97.671"}]
["2010-04-30",85,{"v":106.10019742980512,"d":"106"},{"v":4.664383906408076,"d":"4.664"},{"v":96.75277224060414,"d":"96.753"}]
["2010-05-02",86,{"v":108.10019742980512,"d":"108"},{"v":4.6830585510061695,"d":"4.683"},{"v":94.94247526008252,"d":"94.942"}]
["2010-05-06",86,{"v":112.10019742980512,"d":"112"},{"v":4.719393091270186,"d":"4.719"},{"v":91.42024980711165,"d":"91.420"}]
["2010-05-07",84,{"v":113.10019742980512,"d":"113"},{"v":4.728274128742171,"d":"4.728"},{"v":90.55933300438579,"d":"90.559"}]
["2010-05-08",89,{"v":114.10019742980512,"d":"114"},{"v":4.737076987189102,"d":"4.737"},{"v":89.70599477978226,"d":"89.706"}]
["2010-05-10",86,{"v":116.10019742980512,"d":"116"},{"v":4.754453589217517,"d":"4.754"},{"v":88.02152844263026,"d":"88.022"}]
["2010-05-12",84,{"v":118.10019742980512,"d":"118"},{"v":4.771533394919151,"d":"4.772"},{"v":86.36583317479528,"d":"86.366"}]
["2010-05-13",86,{"v":119.10019742980512,"d":"119"},{"v":4.7799651340408635,"d":"4.780"},{"v":85.54847079917397,"d":"85.548"}]
["2010-05-14",82,{"v":120.10019742980512,"d":"120"},{"v":4.788326372963064,"d":"4.788"},{"v":84.73794262581191,"d":"84.738"}]
["2010-05-16",80,{"v":122.10019742980512,"d":"122"},{"v":4.804841998067072,"d":"4.805"},{"v":83.13693832823799,"d":"83.137"}]
["2010-05-18",78,{"v":124.10019742980512,"d":"124"},{"v":4.8210892831021654,"d":"4.821"},{"v":81.56194658549254,"d":"81.562"}]
["2010-05-20",77,{"v":126.10019742980512,"d":"126"},{"v":4.837076808630275,"d":"4.837"},{"v":80.01213560850056,"d":"80.012"}]
["2010-05-25",80,{"v":131.10019742980512,"d":"131"},{"v":4.8759618967166904,"d":"4.876"},{"v":76.24266320004898,"d":"76.243"}]
["2010-05-28",82,{"v":134.10019742980512,"d":"134"},{"v":4.898587262544604,"d":"4.899"},{"v":74.04938818341759,"d":"74.049"}]
["2010-06-01",79,{"v":138.10019742980512,"d":"138"},{"v":4.927979490029034,"d":"4.928"},{"v":71.20014195619359,"d":"71.200"}]
["2010-06-02",78,{"v":139.10019742980512,"d":"139"},{"v":4.935194518265594,"d":"4.935"},{"v":70.50072603090439,"d":"70.501"}]
["2010-06-03",78,{"v":140.10019742980512,"d":"140"},{"v":4.9423578625482865,"d":"4.942"},{"v":69.80632028426334,"d":"69.806"}]
["2010-06-04",79,{"v":141.10019742980512,"d":"141"},{"v":4.949470258076819,"d":"4.949"},{"v":69.11685344691898,"d":"69.117"}]
["2010-06-05",73,{"v":142.10019742980512,"d":"142"},{"v":4.956532424474399,"d":"4.957"},{"v":68.4322557594864,"d":"68.432"}]
["2010-06-07",72,{"v":144.10019742980512,"d":"144"},{"v":4.970508873093401,"d":"4.971"},{"v":67.07739609399232,"d":"67.077"}]
["2010-06-08",68,{"v":145.10019742980512,"d":"145"},{"v":4.977424520535703,"d":"4.977"},{"v":66.40700177310498,"d":"66.407"}]
["2010-06-09",67,{"v":146.10019742980512,"d":"146"},{"v":4.9842926700891095,"d":"4.984"},{"v":65.74121183889804,"d":"65.741"}]
["2010-06-10",66,{"v":147.10019742980512,"d":"147"},{"v":4.991113969753365,"d":"4.991"},{"v":65.07996347507662,"d":"65.080"}]
["2010-06-11",67,{"v":148.10019742980512,"d":"148"},{"v":4.997889054357302,"d":"4.998"},{"v":64.423195142118,"d":"64.423"}]
["2010-06-12",66,{"v":149.10019742980512,"d":"149"},{"v":5.004618545913378,"d":"5.005"},{"v":63.77084654290263,"d":"63.771"}]
["2010-06-13",67,{"v":150.10019742980512,"d":"150"},{"v":5.011303053960371,"d":"5.011"},{"v":63.12285858949451,"d":"63.123"}]
["2010-06-14",68,{"v":151.10019742980512,"d":"151"},{"v":5.017943175894684,"d":"5.018"},{"v":62.47917337102399,"d":"62.479"}]
["2010-06-15",66,{"v":152.10019742980512,"d":"152"},{"v":5.0245394972907365,"d":"5.025"},{"v":61.839734122630375,"d":"61.840"}]
["2010-06-16",67,{"v":153.10019742980512,"d":"153"},{"v":5.031092592210848,"d":"5.031"},{"v":61.20448519542134,"d":"61.204"}]
["2010-06-17",65,{"v":154.10019742980512,"d":"154"},{"v":5.037603023505036,"d":"5.038"},{"v":60.57337202741144,"d":"60.573"}]
["2010-06-18",65,{"v":155.10019742980512,"d":"155"},{"v":5.044071343101123,"d":"5.044"},{"v":59.946341115399264,"d":"59.946"}]
["2010-06-19",64,{"v":156.10019742980512,"d":"156"},{"v":5.050498092285514,"d":"5.050"},{"v":59.32333998774948,"d":"59.323"}]
["2010-06-20",60,{"v":157.10019742980512,"d":"157"},{"v":5.0568838019750135,"d":"5.057"},{"v":58.70431717804257,"d":"58.704"}]
["2010-06-21",55,{"v":158.10019742980512,"d":"158"},{"v":5.063228992980018,"d":"5.063"},{"v":58.08922219956224,"d":"58.089"}]
["2010-06-22",59,{"v":159.10019742980512,"d":"159"},{"v":5.069534176259408,"d":"5.070"},{"v":57.47800552058567,"d":"57.478"}]
["2010-06-24",54,{"v":161.10019742980512,"d":"161"},{"v":5.082026515693072,"d":"5.082"},{"v":56.26701356635476,"d":"56.267"}]
["2010-06-25",44,{"v":162.10019742980512,"d":"162"},{"v":5.088214646691568,"d":"5.088"},{"v":55.6671437909057,"d":"55.667"}]
["2010-06-27",45,{"v":164.10019742980512,"d":"164"},{"v":5.100477201201995,"d":"5.100"},{"v":54.478426903304296,"d":"54.478"}]
["2010-06-28",41,{"v":165.10019742980512,"d":"165"},{"v":5.1065525467449016,"d":"5.107"},{"v":53.88949041060812,"d":"53.889"}]
["2010-06-29",39,{"v":166.10019742980512,"d":"166"},{"v":5.112591205238682,"d":"5.113"},{"v":53.30411031513859,"d":"53.304"}]
["2010-06-30",38,{"v":167.10019742980512,"d":"167"},{"v":5.118593617107563,"d":"5.119"},{"v":52.722243922715165,"d":"52.722"}]
["2010-07-01",36,{"v":168.10019742980512,"d":"168"},{"v":5.124560214892197,"d":"5.125"},{"v":52.14384930338127,"d":"52.144"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}