{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":75,"n_cols":10,"rows_kept":75,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-06T22:05:47.960"]
["2010-03-23",144,{"v":108.53996360173915,"d":"109"},{"v":4.68711843329099,"d":"4.687"},{"v":138.10455486303283,"d":"138.105"},{"v":3139.3457771301732,"d":"3139.346"},"Forecast Zero Critical Issues Date(s) ->","2010-08-20T16:13:46.072",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":109.53996360173915,"d":"110"},{"v":4.696289447072693,"d":"4.696"},{"v":136.8626426302793,"d":"136.863"}]
["2010-03-25",146,{"v":110.53996360173915,"d":"111"},{"v":4.705377117128232,"d":"4.705"},{"v":135.6320165645201,"d":"135.632"},"Date '0' ref",null,"2010-09-24T22:12:55.731",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":111.53996360173915,"d":"112"},{"v":4.71438294463662,"d":"4.714"},{"v":134.4124733804232,"d":"134.412"},"2009-12-04T11:02:27.145"]
["2010-03-27",137,{"v":112.53996360173915,"d":"113"},{"v":4.723308390579979,"d":"4.723"},{"v":133.20381523600383,"d":"133.204"}]
["2010-03-28",134,{"v":113.53996360173915,"d":"114"},{"v":4.732154877165985,"d":"4.732"},{"v":132.005849540001,"d":"132.006"},"Min '0' Ref"]
["2010-03-30",131,{"v":115.53996360173915,"d":"116"},{"v":4.749616475325713,"d":"4.750"},{"v":129.64125028476315,"d":"129.641"},"2010-03-22"]
["2010-04-01",131,{"v":117.53996360173915,"d":"118"},{"v":4.766778391517442,"d":"4.767"},{"v":127.31723309720633,"d":"127.317"}]
["2010-04-02",128,{"v":118.53996360173915,"d":"119"},{"v":4.775250149304973,"d":"4.775"},{"v":126.17001209419686,"d":"126.170"}]
["2010-04-04",128,{"v":120.53996360173915,"d":"121"},{"v":4.791981346094832,"d":"4.792"},{"v":123.90432168564178,"d":"123.904"}]
["2010-04-05",130,{"v":121.53996360173915,"d":"122"},{"v":4.800243127231593,"d":"4.800"},{"v":122.78553511500695,"d":"122.786"}]
["2010-04-06",127,{"v":122.53996360173915,"d":"123"},{"v":4.808437210265795,"d":"4.808"},{"v":121.67591602614743,"d":"121.676"}]
["2010-04-07",121,{"v":123.53996360173915,"d":"124"},{"v":4.816564695640375,"d":"4.817"},{"v":120.57531540025434,"d":"120.575"}]
["2010-04-08",120,{"v":124.53996360173915,"d":"125"},{"v":4.8246266571826535,"d":"4.825"},{"v":119.48358782272976,"d":"119.484"}]
["2010-04-09",116,{"v":125.53996360173915,"d":"126"},{"v":4.83262414295577,"d":"4.833"},{"v":118.40059136788625,"d":"118.401"}]
["2010-04-11",110,{"v":127.53996360173915,"d":"128"},{"v":4.848429755500062,"d":"4.848"},{"v":116.26024090804071,"d":"116.260"}]
["2010-04-12",110,{"v":128.53996360173915,"d":"129"},{"v":4.856239856776297,"d":"4.856"},{"v":115.20261952125895,"d":"115.203"}]
["2010-04-13",109,{"v":129.53996360173915,"d":"130"},{"v":4.863989432773869,"d":"4.864"},{"v":114.15319429313001,"d":"114.153"}]
["2010-04-14",110,{"v":130.53996360173915,"d":"131"},{"v":4.871679414378621,"d":"4.872"},{"v":113.11183916577829,"d":"113.112"}]
["2010-04-15",112,{"v":131.53996360173915,"d":"132"},{"v":4.879310711164479,"d":"4.879"},{"v":112.0784309673262,"d":"112.078"}]
["2010-04-18",112,{"v":134.53996360173915,"d":"135"},{"v":4.9018612820588405,"d":"4.902"},{"v":109.02469770338143,"d":"109.025"}]
["2010-04-19",115,{"v":135.53996360173915,"d":"136"},{"v":4.909266531165354,"d":"4.909"},{"v":108.02190022963725,"d":"108.022"}]
["2010-04-20",100,{"v":136.53996360173915,"d":"137"},{"v":4.9166173454142905,"d":"4.917"},{"v":107.02647416729008,"d":"107.026"}]
["2010-04-22",95,{"v":138.53996360173915,"d":"139"},{"v":4.931158829866975,"d":"4.931"},{"v":105.05730828726348,"d":"105.057"}]
["2010-04-24",94,{"v":140.53996360173915,"d":"141"},{"v":4.945491886775397,"d":"4.945"},{"v":103.11636706407683,"d":"103.116"}]
["2010-04-27",97,{"v":143.53996360173915,"d":"144"},{"v":4.96661348842616,"d":"4.967"},{"v":100.25614069327344,"d":"100.256"}]
["2010-04-28",90,{"v":144.53996360173915,"d":"145"},{"v":4.973556034033433,"d":"4.974"},{"v":99.31600119273935,"d":"99.316"}]
["2010-04-29",87,{"v":145.53996360173915,"d":"146"},{"v":4.980450712827794,"d":"4.980"},{"v":98.38234367793916,"d":"98.382"}]
["2010-04-30",85,{"v":146.53996360173915,"d":"147"},{"v":4.987298180347313,"d":"4.987"},{"v":97.45507937779848,"d":"97.455"}]
["2010-05-02",86,{"v":148.53996360173915,"d":"149"},{"v":5.000854037200991,"d":"5.001"},{"v":95.61938434421063,"d":"95.619"}]
["2010-05-06",86,{"v":152.53996360173915,"d":"153"},{"v":5.027426618121531,"d":"5.027"},{"v":92.02100208391039,"d":"92.021"}]
["2010-05-07",84,{"v":153.53996360173915,"d":"154"},{"v":5.0339608823392785,"d":"5.034"},{"v":91.1361508714682,"d":"91.136"}]
["2010-05-08",89,{"v":154.53996360173915,"d":"155"},{"v":5.0404527269789385,"d":"5.040"},{"v":90.25704399593246,"d":"90.257"}]
["2010-05-10",86,{"v":156.53996360173915,"d":"157"},{"v":5.053311335859347,"d":"5.053"},{"v":88.51576827169004,"d":"88.516"}]
["2010-05-12",84,{"v":158.53996360173915,"d":"159"},{"v":5.066006697824898,"d":"5.066"},{"v":86.79659897377599,"d":"86.797"}]
["2010-05-13",86,{"v":159.53996360173915,"d":"160"},{"v":5.07229444633791,"d":"5.072"},{"v":85.9451302070006,"d":"85.945"}]
["2010-05-14",82,{"v":160.53996360173915,"d":"161"},{"v":5.078542905979468,"d":"5.079"},{"v":85.09898182586971,"d":"85.099"}]
["2010-05-16",80,{"v":162.53996360173915,"d":"163"},{"v":5.090923901390858,"d":"5.091"},{"v":83.42238313993755,"d":"83.422"}]
["2010-05-18",78,{"v":164.53996360173915,"d":"165"},{"v":5.103153480528526,"d":"5.103"},{"v":81.76628880903615,"d":"81.766"}]
["2010-05-20",77,{"v":166.53996360173915,"d":"167"},{"v":5.115235302251982,"d":"5.115"},{"v":80.13020336096486,"d":"80.130"}]
["2010-05-25",80,{"v":171.53996360173915,"d":"172"},{"v":5.144816263376985,"d":"5.145"},{"v":76.12443493097521,"d":"76.124"}]
["2010-05-28",82,{"v":174.53996360173915,"d":"175"},{"v":5.162153733196924,"d":"5.162"},{"v":73.77664477746646,"d":"73.777"}]
["2010-06-01",79,{"v":178.53996360173915,"d":"179"},{"v":5.184812461885054,"d":"5.185"},{"v":70.70826509706819,"d":"70.708"}]
["2010-06-02",78,{"v":179.53996360173915,"d":"180"},{"v":5.190397821597872,"d":"5.190"},{"v":69.95191179559163,"d":"69.952"}]
["2010-06-03",78,{"v":180.53996360173915,"d":"181"},{"v":5.195952158262251,"d":"5.196"},{"v":69.19975954584959,"d":"69.200"}]
["2010-06-04",79,{"v":181.53996360173915,"d":"182"},{"v":5.201475814601266,"d":"5.201"},{"v":68.45176193727184,"d":"68.452"}]
["2010-06-05",73,{"v":182.53996360173915,"d":"183"},{"v":5.20696912768989,"d":"5.207"},{"v":67.7078733241375,"d":"67.708"}]
["2010-06-07",72,{"v":184.53996360173915,"d":"185"},{"v":5.217866044912605,"d":"5.218"},{"v":66.23224422572832,"d":"66.232"}]
["2010-06-08",68,{"v":185.53996360173915,"d":"186"},{"v":5.2232702960503685,"d":"5.223"},{"v":65.50041612508255,"d":"65.500"}]
["2010-06-09",67,{"v":186.53996360173915,"d":"187"},{"v":5.22864549817561,"d":"5.229"},{"v":64.77252175792125,"d":"64.773"}]
["2010-06-10",66,{"v":187.53996360173915,"d":"188"},{"v":5.2339919619088064,"d":"5.234"},{"v":64.04851906091562,"d":"64.049"}]
["2010-06-11",67,{"v":188.53996360173915,"d":"189"},{"v":5.2393099929147295,"d":"5.239"},{"v":63.32836664182378,"d":"63.328"}]
["2010-06-12",66,{"v":189.53996360173915,"d":"190"},{"v":5.244599892007311,"d":"5.245"},{"v":62.61202376529093,"d":"62.612"}]
["2010-06-13",67,{"v":190.53996360173915,"d":"191"},{"v":5.249861955251739,"d":"5.250"},{"v":61.89945033902302,"d":"61.899"}]
["2010-06-14",68,{"v":191.53996360173915,"d":"192"},{"v":5.255096474063901,"d":"5.255"},{"v":61.19060690032154,"d":"61.191"}]
["2010-06-15",66,{"v":192.53996360173915,"d":"193"},{"v":5.260303735307209,"d":"5.260"},{"v":60.48545460297032,"d":"60.485"}]
["2010-06-16",67,{"v":193.53996360173915,"d":"194"},{"v":5.265484021386948,"d":"5.265"},{"v":59.783955204460426,"d":"59.784"}]
["2010-06-17",65,{"v":194.53996360173915,"d":"195"},{"v":5.270637610342167,"d":"5.271"},{"v":59.08607105354588,"d":"59.086"}]
["2010-06-18",65,{"v":195.53996360173915,"d":"196"},{"v":5.27576477593523,"d":"5.276"},{"v":58.39176507811692,"d":"58.392"}]
["2010-06-19",64,{"v":196.53996360173915,"d":"197"},{"v":5.280865787739082,"d":"5.281"},{"v":57.70100077338293,"d":"57.701"}]
["2010-06-20",60,{"v":197.53996360173915,"d":"198"},{"v":5.285940911222291,"d":"5.286"},{"v":57.013742190356425,"d":"57.014"}]
["2010-06-21",55,{"v":198.53996360173915,"d":"199"},{"v":5.2909904078319485,"d":"5.291"},{"v":56.3299539246259,"d":"56.330"}]
["2010-06-22",59,{"v":199.53996360173915,"d":"200"},{"v":5.296014535074495,"d":"5.296"},{"v":55.649601105412216,"d":"55.650"}]
["2010-06-24",54,{"v":201.53996360173915,"d":"202"},{"v":5.305987692251561,"d":"5.306"},{"v":54.299064927821746,"d":"54.299"}]
["2010-06-25",44,{"v":202.53996360173915,"d":"203"},{"v":5.310937218195122,"d":"5.311"},{"v":53.62881440133117,"d":"53.629"}]
["2010-06-27",45,{"v":204.53996360173915,"d":"205"},{"v":5.3207633774260525,"d":"5.321"},{"v":52.298184261594315,"d":"52.298"}]
["2010-06-28",41,{"v":205.53996360173915,"d":"206"},{"v":5.32564048511089,"d":"5.326"},{"v":51.63774040681142,"d":"51.638"}]
["2010-06-29",39,{"v":206.53996360173915,"d":"207"},{"v":5.330493922014615,"d":"5.330"},{"v":50.980501980929034,"d":"50.981"}]
["2010-06-30",38,{"v":207.53996360173915,"d":"208"},{"v":5.33532391679762,"d":"5.335"},{"v":50.32643801941617,"d":"50.326"}]
["2010-07-01",36,{"v":208.53996360173915,"d":"209"},{"v":5.340130694822922,"d":"5.340"},{"v":49.67551800426327,"d":"49.676"}]
["2010-07-02",36,{"v":209.53996360173915,"d":"210"},{"v":5.344914478219255,"d":"5.345"},{"v":49.02771185543804,"d":"49.028"}]
["2010-07-05",41,{"v":212.53996360173915,"d":"213"},{"v":5.359130034690837,"d":"5.359"},{"v":47.10268220248099,"d":"47.103"}]
["2010-07-06",40,{"v":213.53996360173915,"d":"214"},{"v":5.363823998298419,"d":"5.364"},{"v":46.467039190365426,"d":"46.467"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}