{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":77,"n_cols":10,"rows_kept":77,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-08T22:14:08.180"]
["2010-03-23",144,{"v":122.57852586270019,"d":"123"},{"v":4.80875185206506,"d":"4.809"},{"v":137.75121874261822,"d":"137.751"},{"v":3172.608316904686,"d":"3172.608"},"Forecast Zero Critical Issues Date(s) ->","2010-08-21T01:18:18.045",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":123.57852586270019,"d":"124"},{"v":4.816876790954309,"d":"4.817"},{"v":136.54358185967374,"d":"136.544"}]
["2010-03-25",146,{"v":124.57852586270019,"d":"125"},{"v":4.824936246899194,"d":"4.825"},{"v":135.3456779260962,"d":"135.346"},"Date '0' ref",null,"2010-09-20T16:16:38.088",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":125.57852586270019,"d":"126"},{"v":4.8329312669859155,"d":"4.833"},{"v":134.15735130995597,"d":"134.157"},"2009-11-20T10:06:55.365"]
["2010-03-27",137,{"v":126.57852586270019,"d":"127"},{"v":4.840862873385051,"d":"4.841"},{"v":132.9784500826164,"d":"132.978"}]
["2010-03-28",134,{"v":127.57852586270019,"d":"128"},{"v":4.848732064135832,"d":"4.849"},{"v":131.80882590216333,"d":"131.809"},"Min '0' Ref"]
["2010-03-30",131,{"v":129.5785258627002,"d":"130"},{"v":4.8642870746853015,"d":"4.864"},{"v":129.49683258009838,"d":"129.497"},"2010-03-22"]
["2010-04-01",131,{"v":131.5785258627002,"d":"132"},{"v":4.879603828241242,"d":"4.880"},{"v":127.22025219306295,"d":"127.220"}]
["2010-04-02",128,{"v":132.5785258627002,"d":"133"},{"v":4.887175117900172,"d":"4.887"},{"v":126.09490604976111,"d":"126.095"}]
["2010-04-04",128,{"v":134.5785258627002,"d":"135"},{"v":4.902147864086718,"d":"4.902"},{"v":123.86945663034885,"d":"123.869"}]
["2010-04-05",130,{"v":135.5785258627002,"d":"136"},{"v":4.9095509991210236,"d":"4.910"},{"v":122.76910387216674,"d":"122.769"}]
["2010-04-06",127,{"v":136.5785258627002,"d":"137"},{"v":4.916899730259732,"d":"4.917"},{"v":121.67683734722232,"d":"121.677"}]
["2010-04-07",121,{"v":137.5785258627002,"d":"138"},{"v":4.924194851275965,"d":"4.924"},{"v":120.5925390743572,"d":"120.593"}]
["2010-04-08",120,{"v":138.5785258627002,"d":"139"},{"v":4.931437138696418,"d":"4.931"},{"v":119.51609363580792,"d":"119.516"}]
["2010-04-09",116,{"v":139.5785258627002,"d":"140"},{"v":4.938627352297386,"d":"4.939"},{"v":118.4473881034786,"d":"118.447"}]
["2010-04-11",110,{"v":141.5785258627002,"d":"142"},{"v":4.952854516247059,"d":"4.953"},{"v":116.33275706938457,"d":"116.333"}]
["2010-04-12",110,{"v":142.5785258627002,"d":"143"},{"v":4.959892906617239,"d":"4.960"},{"v":115.28661753240442,"d":"115.287"}]
["2010-04-13",109,{"v":143.5785258627002,"d":"144"},{"v":4.966882104085603,"d":"4.967"},{"v":114.2477897012011,"d":"114.248"}]
["2010-04-14",110,{"v":144.5785258627002,"d":"145"},{"v":4.973822791522801,"d":"4.974"},{"v":113.21617207842223,"d":"113.216"}]
["2010-04-15",112,{"v":145.5785258627002,"d":"146"},{"v":4.980715637678548,"d":"4.981"},{"v":112.19166526555796,"d":"112.192"}]
["2010-04-18",112,{"v":148.5785258627002,"d":"149"},{"v":5.001113612168857,"d":"5.001"},{"v":109.159845990652,"d":"109.160"}]
["2010-04-19",115,{"v":149.5785258627002,"d":"150"},{"v":5.007821511538466,"d":"5.008"},{"v":108.16282843812144,"d":"108.163"}]
["2010-04-20",100,{"v":150.5785258627002,"d":"151"},{"v":5.014484714645675,"d":"5.014"},{"v":107.17245424078897,"d":"107.172"}]
["2010-04-22",95,{"v":152.5785258627002,"d":"153"},{"v":5.027679387209593,"d":"5.028"},{"v":105.21128585986139,"d":"105.211"}]
["2010-04-24",94,{"v":154.5785258627002,"d":"155"},{"v":5.040702225229451,"d":"5.041"},{"v":103.27565782280601,"d":"103.276"}]
["2010-04-27",97,{"v":157.5785258627002,"d":"158"},{"v":5.059923910923551,"d":"5.060"},{"v":100.41867429185572,"d":"100.419"}]
["2010-04-28",90,{"v":158.5785258627002,"d":"159"},{"v":5.066249901942175,"d":"5.066"},{"v":99.47842105679763,"d":"99.478"}]
["2010-04-29",87,{"v":159.5785258627002,"d":"160"},{"v":5.072536126230626,"d":"5.073"},{"v":98.54407848405037,"d":"98.544"}]
["2010-04-30",85,{"v":160.5785258627002,"d":"161"},{"v":5.078783080634068,"d":"5.079"},{"v":97.6155727258531,"d":"97.616"}]
["2010-05-02",86,{"v":162.5785258627002,"d":"163"},{"v":5.091161121126994,"d":"5.091"},{"v":95.77578310508227,"d":"95.776"}]
["2010-05-06",86,{"v":166.5785258627002,"d":"167"},{"v":5.115466825042538,"d":"5.115"},{"v":92.16314491611342,"d":"92.163"}]
["2010-05-07",84,{"v":167.5785258627002,"d":"168"},{"v":5.121452052528119,"d":"5.121"},{"v":91.27354050641566,"d":"91.274"}]
["2010-05-08",89,{"v":168.5785258627002,"d":"169"},{"v":5.127401670093449,"d":"5.127"},{"v":90.38922891844618,"d":"90.389"}]
["2010-05-10",86,{"v":170.5785258627002,"d":"171"},{"v":5.13919575294191,"d":"5.139"},{"v":88.63623487843552,"d":"88.636"}]
["2010-05-12",84,{"v":172.5785258627002,"d":"173"},{"v":5.1508523552816,"d":"5.151"},{"v":86.90367502695722,"d":"86.904"}]
["2010-05-13",86,{"v":173.5785258627002,"d":"174"},{"v":5.1566300956273246,"d":"5.157"},{"v":86.04491012586914,"d":"86.045"}]
["2010-05-14",82,{"v":174.5785258627002,"d":"175"},{"v":5.162374645364464,"d":"5.162"},{"v":85.19107845611245,"d":"85.191"}]
["2010-05-16",80,{"v":176.5785258627002,"d":"177"},{"v":5.173765683169817,"d":"5.174"},{"v":83.4979903509253,"d":"83.498"}]
["2010-05-18",78,{"v":178.5785258627002,"d":"179"},{"v":5.18502842528235,"d":"5.185"},{"v":81.82397126430999,"d":"81.824"}]
["2010-05-20",77,{"v":180.5785258627002,"d":"181"},{"v":5.196165729498467,"d":"5.196"},{"v":80.16859643241389,"d":"80.169"}]
["2010-05-25",80,{"v":185.5785258627002,"d":"186"},{"v":5.223478112487407,"d":"5.223"},{"v":76.10906546139404,"d":"76.109"}]
["2010-05-28",82,{"v":188.5785258627002,"d":"189"},{"v":5.239514502967526,"d":"5.240"},{"v":73.72552302777444,"d":"73.726"}]
["2010-06-01",79,{"v":192.5785258627002,"d":"193"},{"v":5.260503997107901,"d":"5.261"},{"v":70.6057842058857,"d":"70.606"}]
["2010-06-02",78,{"v":193.5785258627002,"d":"194"},{"v":5.265683248559704,"d":"5.266"},{"v":69.83597471383928,"d":"69.836"}]
["2010-06-03",78,{"v":194.5785258627002,"d":"195"},{"v":5.270835813522593,"d":"5.271"},{"v":69.07013172403083,"d":"69.070"}]
["2010-06-04",79,{"v":195.5785258627002,"d":"196"},{"v":5.27596196559578,"d":"5.276"},{"v":68.30821457049342,"d":"68.308"}]
["2010-06-05",73,{"v":196.5785258627002,"d":"197"},{"v":5.28106197419237,"d":"5.281"},{"v":67.55018320945442,"d":"67.550"}]
["2010-06-07",72,{"v":198.5785258627002,"d":"199"},{"v":5.291184618185308,"d":"5.291"},{"v":66.0456207253028,"d":"66.046"}]
["2010-06-08",68,{"v":199.5785258627002,"d":"200"},{"v":5.296207772231375,"d":"5.296"},{"v":65.29901251354522,"d":"65.299"}]
["2010-06-09",67,{"v":200.5785258627002,"d":"201"},{"v":5.301205820259739,"d":"5.301"},{"v":64.5561358932955,"d":"64.556"}]
["2010-06-10",66,{"v":201.5785258627002,"d":"202"},{"v":5.306179011985518,"d":"5.306"},{"v":63.8169537485594,"d":"63.817"}]
["2010-06-11",67,{"v":202.5785258627002,"d":"203"},{"v":5.311127593416597,"d":"5.311"},{"v":63.08142951436082,"d":"63.081"}]
["2010-06-12",66,{"v":203.5785258627002,"d":"204"},{"v":5.316051806926655,"d":"5.316"},{"v":62.349527165887935,"d":"62.350"}]
["2010-06-13",67,{"v":204.5785258627002,"d":"205"},{"v":5.320951891326393,"d":"5.321"},{"v":61.62121120790641,"d":"61.621"}]
["2010-06-14",68,{"v":205.5785258627002,"d":"206"},{"v":5.325828081933034,"d":"5.326"},{"v":60.89644666442916,"d":"60.896"}]
["2010-06-15",66,{"v":206.5785258627002,"d":"207"},{"v":5.330680610638128,"d":"5.331"},{"v":60.17519906863845,"d":"60.175"}]
["2010-06-16",67,{"v":207.5785258627002,"d":"208"},{"v":5.335509705973726,"d":"5.336"},{"v":59.4574344530497,"d":"59.457"}]
["2010-06-17",65,{"v":208.5785258627002,"d":"209"},{"v":5.340315593176962,"d":"5.340"},{"v":58.743119339913505,"d":"58.743"}]
["2010-06-18",65,{"v":209.5785258627002,"d":"210"},{"v":5.345098494253093,"d":"5.345"},{"v":58.032220731844745,"d":"58.032"}]
["2010-06-19",64,{"v":210.5785258627002,"d":"211"},{"v":5.34985862803703,"d":"5.350"},{"v":57.32470610267774,"d":"57.325"}]
["2010-06-20",60,{"v":211.5785258627002,"d":"212"},{"v":5.3545962102534235,"d":"5.355"},{"v":56.62054338853477,"d":"56.621"}]
["2010-06-21",55,{"v":212.5785258627002,"d":"213"},{"v":5.359311453575325,"d":"5.359"},{"v":55.91970097910814,"d":"55.920"}]
["2010-06-22",59,{"v":213.5785258627002,"d":"214"},{"v":5.3640045676814685,"d":"5.364"},{"v":55.22214770914502,"d":"55.222"}]
["2010-06-24",54,{"v":215.5785258627002,"d":"216"},{"v":5.373325232324259,"d":"5.373"},{"v":53.836786102169185,"d":"53.837"}]
["2010-06-25",44,{"v":216.5785258627002,"d":"217"},{"v":5.3779531877438815,"d":"5.378"},{"v":53.14891758604358,"d":"53.149"}]
["2010-06-27",45,{"v":218.5785258627002,"d":"219"},{"v":5.387145336071243,"d":"5.387"},{"v":51.782657789516634,"d":"51.783"}]
["2010-06-28",41,{"v":219.5785258627002,"d":"220"},{"v":5.391709917343393,"d":"5.392"},{"v":51.10420878521222,"d":"51.104"}]
["2010-06-29",39,{"v":220.5785258627002,"d":"221"},{"v":5.3962537578504115,"d":"5.396"},{"v":50.428842550303784,"d":"50.429"}]
["2010-06-30",38,{"v":221.5785258627002,"d":"222"},{"v":5.400777045225826,"d":"5.401"},{"v":49.75653119619187,"d":"49.757"}]
["2010-07-01",36,{"v":222.5785258627002,"d":"223"},{"v":5.4052799645684555,"d":"5.405"},{"v":49.08724721101896,"d":"49.087"}]
["2010-07-02",36,{"v":223.5785258627002,"d":"224"},{"v":5.409762698487857,"d":"5.410"},{"v":48.42096345291475,"d":"48.421"}]
["2010-07-05",41,{"v":226.5785258627002,"d":"227"},{"v":5.423091577389666,"d":"5.423"},{"v":46.43984753443999,"d":"46.440"}]
["2010-07-06",40,{"v":227.5785258627002,"d":"228"},{"v":5.427495347461273,"d":"5.427"},{"v":45.78530043753619,"d":"45.785"}]
["2010-07-07",40,{"v":228.5785258627002,"d":"229"},{"v":5.4318798093398115,"d":"5.432"},{"v":45.13362318204395,"d":"45.134"}]
["2010-07-08",43,{"v":229.5785258627002,"d":"230"},{"v":5.436245131598791,"d":"5.436"},{"v":44.48479071231827,"d":"44.485"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}