{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":80,"n_cols":10,"rows_kept":80,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-12T22:27:38.200"]
["2010-03-23",144,{"v":98.23809132345195,"d":"98"},{"v":4.587394035499302,"d":"4.587"},{"v":138.4158521085858,"d":"138.416"},{"v":3325.4166274857766,"d":"3325.417"},"Forecast Zero Critical Issues Date(s) ->","2010-08-23T20:59:59.504",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":99.23809132345195,"d":"99"},{"v":4.597521925702853,"d":"4.598"},{"v":137.14294343045412,"d":"137.143"}]
["2010-03-25",146,{"v":100.23809132345195,"d":"100"},{"v":4.60754826933961,"d":"4.608"},{"v":135.88279748014702,"d":"135.883"},"Date '0' ref",null,"2010-09-30T07:14:33.825",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":101.23809132345195,"d":"101"},{"v":4.617475082510779,"d":"4.617"},{"v":134.63516086701077,"d":"134.635"},"2009-12-14T18:17:08.910"]
["2010-03-27",137,{"v":102.23809132345195,"d":"102"},{"v":4.627304321865879,"d":"4.627"},{"v":133.3997876724875,"d":"133.400"}]
["2010-03-28",134,{"v":103.23809132345195,"d":"103"},{"v":4.63703788691752,"d":"4.637"},{"v":132.1764391591862,"d":"132.176"},"Min '0' Ref"]
["2010-03-30",131,{"v":105.23809132345195,"d":"105"},{"v":4.656225319590407,"d":"4.656"},{"v":129.764895484293,"d":"129.765"},"2010-03-22"]
["2010-04-01",131,{"v":107.23809132345195,"d":"107"},{"v":4.675051515031935,"d":"4.675"},{"v":127.39875336860109,"d":"127.399"}]
["2010-04-02",128,{"v":108.23809132345195,"d":"108"},{"v":4.684333349962156,"d":"4.684"},{"v":126.23217987755731,"d":"126.232"}]
["2010-04-04",128,{"v":110.23809132345195,"d":"110"},{"v":4.702642493286108,"d":"4.703"},{"v":123.93102268116058,"d":"123.931"}]
["2010-04-05",130,{"v":111.23809132345195,"d":"111"},{"v":4.711672871033123,"d":"4.712"},{"v":122.79605320874737,"d":"122.796"}]
["2010-04-06",127,{"v":112.23809132345195,"d":"112"},{"v":4.72062243033468,"d":"4.721"},{"v":121.67124128134196,"d":"121.671"}]
["2010-04-07",121,{"v":113.23809132345195,"d":"113"},{"v":4.729492604957283,"d":"4.729"},{"v":120.55640669815341,"d":"120.556"}]
["2010-04-08",120,{"v":114.23809132345195,"d":"114"},{"v":4.738284790848864,"d":"4.738"},{"v":119.45137401156114,"d":"119.451"}]
["2010-04-09",116,{"v":115.23809132345195,"d":"115"},{"v":4.747000347457264,"d":"4.747"},{"v":118.35597236140404,"d":"118.356"}]
["2010-04-11",110,{"v":117.23809132345195,"d":"117"},{"v":4.764206835630436,"d":"4.764"},{"v":116.19340072253272,"d":"116.193"}]
["2010-04-12",110,{"v":118.23809132345195,"d":"118"},{"v":4.772700314676604,"d":"4.773"},{"v":115.12591055744304,"d":"115.126"}]
["2010-04-13",109,{"v":119.23809132345195,"d":"119"},{"v":4.7811222616660904,"d":"4.781"},{"v":114.06741079152698,"d":"114.067"}]
["2010-04-14",110,{"v":120.23809132345195,"d":"120"},{"v":4.789473871428608,"d":"4.789"},{"v":113.01775125440531,"d":"113.018"}]
["2010-04-15",112,{"v":121.23809132345195,"d":"121"},{"v":4.79775630910504,"d":"4.798"},{"v":111.97678550709509,"d":"111.977"}]
["2010-04-18",112,{"v":124.23809132345195,"d":"124"},{"v":4.822199815904103,"d":"4.822"},{"v":108.90464004509249,"d":"108.905"}]
["2010-04-19",115,{"v":125.23809132345195,"d":"125"},{"v":4.830216656190779,"d":"4.830"},{"v":107.89705550704832,"d":"107.897"}]
["2010-04-20",100,{"v":126.23809132345195,"d":"126"},{"v":4.838169737555602,"d":"4.838"},{"v":106.8974844133943,"d":"106.897"}]
["2010-04-22",95,{"v":128.23809132345195,"d":"128"},{"v":4.853888624561807,"d":"4.854"},{"v":104.92187969428358,"d":"104.922"}]
["2010-04-24",94,{"v":130.23809132345195,"d":"130"},{"v":4.869364247075068,"d":"4.869"},{"v":102.9768493078252,"d":"102.977"}]
["2010-04-27",97,{"v":133.23809132345195,"d":"133"},{"v":4.892137688121192,"d":"4.892"},{"v":100.11460355318923,"d":"100.115"}]
["2010-04-28",90,{"v":134.23809132345195,"d":"134"},{"v":4.8996150242287495,"d":"4.900"},{"v":99.1748257880945,"d":"99.175"}]
["2010-04-29",87,{"v":135.23809132345195,"d":"135"},{"v":4.907036864485522,"d":"4.907"},{"v":98.24202293570568,"d":"98.242"}]
["2010-04-30",85,{"v":136.23809132345195,"d":"136"},{"v":4.914404026592849,"d":"4.914"},{"v":97.3160922244573,"d":"97.316"}]
["2010-05-02",86,{"v":138.23809132345195,"d":"138"},{"v":4.928977497983084,"d":"4.929"},{"v":95.48444734775524,"d":"95.484"}]
["2010-05-06",86,{"v":142.23809132345195,"d":"142"},{"v":4.957502352970923,"d":"4.958"},{"v":91.89934376480574,"d":"91.899"}]
["2010-05-07",84,{"v":143.23809132345195,"d":"143"},{"v":4.9645082200166835,"d":"4.965"},{"v":91.0188218810614,"d":"91.019"}]
["2010-05-08",89,{"v":144.23809132345195,"d":"144"},{"v":4.971465346163666,"d":"4.971"},{"v":90.14442592401929,"d":"90.144"}]
["2010-05-10",86,{"v":146.23809132345195,"d":"146"},{"v":4.985236055948429,"d":"4.985"},{"v":88.4136749347449,"d":"88.414"}]
["2010-05-12",84,{"v":148.23809132345195,"d":"148"},{"v":4.998819706310376,"d":"4.999"},{"v":86.70643422824833,"d":"86.706"}]
["2010-05-13",86,{"v":149.23809132345195,"d":"149"},{"v":5.005542958961684,"d":"5.006"},{"v":85.86143231046276,"d":"85.861"}]
["2010-05-14",82,{"v":150.23809132345195,"d":"150"},{"v":5.012221311195628,"d":"5.012"},{"v":85.02207363423747,"d":"85.022"}]
["2010-05-16",80,{"v":152.23809132345195,"d":"152"},{"v":5.025445685622465,"d":"5.025"},{"v":83.35998798436708,"d":"83.360"}]
["2010-05-18",78,{"v":154.23809132345195,"d":"154"},{"v":5.038497456067384,"d":"5.038"},{"v":81.71959580688315,"d":"81.720"}]
["2010-05-20",77,{"v":156.23809132345195,"d":"156"},{"v":5.051381070182052,"d":"5.051"},{"v":80.10033810536197,"d":"80.100"}]
["2010-05-25",80,{"v":161.23809132345195,"d":"161"},{"v":5.082882100691007,"d":"5.083"},{"v":76.1411783693211,"d":"76.141"}]
["2010-05-28",82,{"v":164.23809132345195,"d":"164"},{"v":5.101317151378246,"d":"5.101"},{"v":73.82419669495835,"d":"73.824"}]
["2010-06-01",79,{"v":168.23809132345195,"d":"168"},{"v":5.12538018636725,"d":"5.125"},{"v":70.7998702613096,"d":"70.800"}]
["2010-06-02",78,{"v":169.23809132345195,"d":"169"},{"v":5.131306547860191,"d":"5.131"},{"v":70.05502441261888,"d":"70.055"}]
["2010-06-03",78,{"v":170.23809132345195,"d":"170"},{"v":5.137197994409577,"d":"5.137"},{"v":69.314566796201,"d":"69.315"}]
["2010-06-04",79,{"v":171.23809132345195,"d":"171"},{"v":5.143054935007267,"d":"5.143"},{"v":68.5784460085282,"d":"68.578"}]
["2010-06-05",73,{"v":172.23809132345195,"d":"172"},{"v":5.148877771500582,"d":"5.149"},{"v":67.84661154402306,"d":"67.847"}]
["2010-06-07",72,{"v":174.23809132345195,"d":"174"},{"v":5.160422704828577,"d":"5.160"},{"v":66.39560392779663,"d":"66.396"}]
["2010-06-08",68,{"v":175.23809132345195,"d":"175"},{"v":5.166145571100556,"d":"5.166"},{"v":65.67633407050346,"d":"65.676"}]
["2010-06-09",67,{"v":176.23809132345195,"d":"176"},{"v":5.17183587245049,"d":"5.172"},{"v":64.96115708655702,"d":"64.961"}]
["2010-06-10",66,{"v":177.23809132345195,"d":"177"},{"v":5.177493977391855,"d":"5.177"},{"v":64.2500266598945,"d":"64.250"}]
["2010-06-11",67,{"v":178.23809132345195,"d":"178"},{"v":5.183120248218006,"d":"5.183"},{"v":63.54289725621902,"d":"63.543"}]
["2010-06-12",66,{"v":179.23809132345195,"d":"179"},{"v":5.188715041141382,"d":"5.189"},{"v":62.83972410550507,"d":"62.840"}]
["2010-06-13",67,{"v":180.23809132345195,"d":"180"},{"v":5.194278706428837,"d":"5.194"},{"v":62.1404631849889,"d":"62.140"}]
["2010-06-14",68,{"v":181.23809132345195,"d":"181"},{"v":5.199811588533221,"d":"5.200"},{"v":61.445071202631084,"d":"61.445"}]
["2010-06-15",66,{"v":182.23809132345195,"d":"182"},{"v":5.205314026221352,"d":"5.205"},{"v":60.753505581032414,"d":"60.754"}]
["2010-06-16",67,{"v":183.23809132345195,"d":"183"},{"v":5.210786352698476,"d":"5.211"},{"v":60.06572444179187,"d":"60.066"}]
["2010-06-17",65,{"v":184.23809132345195,"d":"184"},{"v":5.216228895729349,"d":"5.216"},{"v":59.381686590288155,"d":"59.382"}]
["2010-06-18",65,{"v":185.23809132345195,"d":"185"},{"v":5.2216419777560334,"d":"5.222"},{"v":58.70135150087435,"d":"58.701"}]
["2010-06-19",64,{"v":186.23809132345195,"d":"186"},{"v":5.227025916012528,"d":"5.227"},{"v":58.02467930247167,"d":"58.025"}]
["2010-06-20",60,{"v":187.23809132345195,"d":"187"},{"v":5.232381022636333,"d":"5.232"},{"v":57.35163076454694,"d":"57.352"}]
["2010-06-21",55,{"v":188.23809132345195,"d":"188"},{"v":5.23770760477703,"d":"5.238"},{"v":56.682167283466015,"d":"56.682"}]
["2010-06-22",59,{"v":189.23809132345195,"d":"189"},{"v":5.243005964702,"d":"5.243"},{"v":56.016250869206715,"d":"56.016"}]
["2010-06-24",54,{"v":191.23809132345195,"d":"191"},{"v":5.253519203178144,"d":"5.254"},{"v":54.69491027184711,"d":"54.695"}]
["2010-06-25",44,{"v":192.23809132345195,"d":"192"},{"v":5.2587346627660025,"d":"5.259"},{"v":54.0394130620233,"d":"54.039"}]
["2010-06-27",45,{"v":194.23809132345195,"d":"194"},{"v":5.2690846814402965,"d":"5.269"},{"v":52.738586500464066,"d":"52.739"}]
["2010-06-28",41,{"v":195.23809132345195,"d":"195"},{"v":5.2742197949183645,"d":"5.274"},{"v":52.093187470848534,"d":"52.093"}]
["2010-06-29",39,{"v":196.23809132345195,"d":"196"},{"v":5.279328673666957,"d":"5.279"},{"v":51.451085713828434,"d":"51.451"}]
["2010-06-30",38,{"v":197.23809132345195,"d":"197"},{"v":5.2844115843848085,"d":"5.284"},{"v":50.812247709773715,"d":"50.812"}]
["2010-07-01",36,{"v":198.23809132345195,"d":"198"},{"v":5.289468789724372,"d":"5.289"},{"v":50.176640447604996,"d":"50.177"}]
["2010-07-02",36,{"v":199.23809132345195,"d":"199"},{"v":5.29450054837327,"d":"5.295"},{"v":49.54423141455675,"d":"49.544"}]
["2010-07-05",41,{"v":202.23809132345195,"d":"202"},{"v":5.309445673233241,"d":"5.309"},{"v":47.665875829367906,"d":"47.666"}]
["2010-07-06",40,{"v":203.23809132345195,"d":"203"},{"v":5.314378155436855,"d":"5.314"},{"v":47.04594420732985,"d":"47.046"}]
["2010-07-07",40,{"v":204.23809132345195,"d":"204"},{"v":5.3192864276264,"d":"5.319"},{"v":46.42905538457046,"d":"46.429"}]
["2010-07-08",43,{"v":205.23809132345195,"d":"205"},{"v":5.324170726300703,"d":"5.324"},{"v":45.81517963708973,"d":"45.815"}]
["2010-07-09",43,{"v":206.23809132345195,"d":"206"},{"v":5.32903128451002,"d":"5.329"},{"v":45.20428767431599,"d":"45.204"}]
["2010-07-11",50,{"v":208.23809132345195,"d":"208"},{"v":5.338682094890616,"d":"5.339"},{"v":43.99134005762903,"d":"43.991"}]
["2010-07-12",53,{"v":209.23809132345195,"d":"209"},{"v":5.343472796512096,"d":"5.343"},{"v":43.38922791524192,"d":"43.389"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}