{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":35,"n_cols":6,"rows_kept":35,"merged":[[0,5,0,6],[1,4,2,4],[1,5,2,6]],"flags":["formulas_cached_only"]}
["Date","Date\n(1/1/2010 ref)","# of Critical Issues",null,"Today's Date ->","2010-05-10T21:05:39.030"]
["2010-03-23",81,144,null,"Forecasted Zero Critical Issues Date ->","2010-07-06T23:17:20.912"]
["2010-03-24",82,141]
["2010-03-25",83,146]
["2010-03-26",84,140]
["2010-03-27",85,137]
["2010-03-28",86,134]
["2010-03-30",88,131]
["2010-04-01",90,131]
["2010-04-02",91,128]
["2010-04-04",93,128]
["2010-04-05",94,130]
["2010-04-06",95,127]
["2010-04-07",96,121]
["2010-04-08",97,120]
["2010-04-09",98,116]
["2010-04-11",100,110]
["2010-04-12",101,110]
["2010-04-13",102,109]
["2010-04-14",103,110]
["2010-04-15",104,112]
["2010-04-18",107,112]
["2010-04-19",108,115]
["2010-04-20",109,100]
["2010-04-22",111,95]
["2010-04-24",113,94]
["2010-04-27",116,97]
["2010-04-28",117,90]
["2010-04-29",118,87]
["2010-04-30",119,85]
["2010-05-02",121,86]
["2010-05-06",125,86]
["2010-05-07",126,84]
["2010-05-08",127,89]
["2010-05-10",129,86]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}