{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":82,"n_cols":10,"rows_kept":82,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-14T23:15:02.060"]
["2010-03-23",144,{"v":88.7387296618399,"d":"89"},{"v":4.485696430565899,"d":"4.486"},{"v":138.7540030153965,"d":"138.754"},{"v":3368.3113873846755,"d":"3368.311"},"Forecast Zero Critical Issues Date(s) ->","2010-08-25T16:21:03.808",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":89.7387296618399,"d":"90"},{"v":4.496902444684772,"d":"4.497"},{"v":137.44655212882935,"d":"137.447"}]
["2010-03-25",146,{"v":90.7387296618399,"d":"91"},{"v":4.507984274378507,"d":"4.508"},{"v":136.15359034026096,"d":"136.154"},"Date '0' ref",null,"2010-10-05T14:26:39.367",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":91.7387296618399,"d":"92"},{"v":4.518944641916405,"d":"4.519"},{"v":134.874800031547,"d":"134.875"},"2009-12-24T06:16:13.757"]
["2010-03-27",137,{"v":92.7387296618399,"d":"93"},{"v":4.529786181024339,"d":"4.530"},{"v":133.60987391526203,"d":"133.610"}]
["2010-03-28",134,{"v":93.7387296618399,"d":"94"},{"v":4.5405114406835105,"d":"4.541"},{"v":132.3585145914833,"d":"132.359"},"Min '0' Ref"]
["2010-03-30",131,{"v":95.7387296618399,"d":"96"},{"v":4.561622915251307,"d":"4.562"},{"v":129.8953536631103,"d":"129.895"},"2010-03-22"]
["2010-04-01",131,{"v":97.7387296618399,"d":"98"},{"v":4.582297894641113,"d":"4.582"},{"v":127.4831203885301,"d":"127.483"}]
["2010-04-02",128,{"v":98.7387296618399,"d":"99"},{"v":4.592477267261222,"d":"4.592"},{"v":126.29545190840179,"d":"126.295"}]
["2010-04-04",128,{"v":100.7387296618399,"d":"101"},{"v":4.612530330170893,"d":"4.613"},{"v":123.95578013916133,"d":"123.956"}]
["2010-04-05",130,{"v":101.7387296618399,"d":"102"},{"v":4.622408053193607,"d":"4.622"},{"v":122.80330633479934,"d":"122.803"}]
["2010-04-06",127,{"v":102.7387296618399,"d":"103"},{"v":4.632189160370894,"d":"4.632"},{"v":121.66210509099449,"d":"121.662"}]
["2010-04-07",121,{"v":103.7387296618399,"d":"104"},{"v":4.641875523444769,"d":"4.642"},{"v":120.53195802405298,"d":"120.532"}]
["2010-04-08",120,{"v":104.7387296618399,"d":"105"},{"v":4.651468960286669,"d":"4.651"},{"v":119.41265303557861,"d":"119.413"}]
["2010-04-09",116,{"v":105.7387296618399,"d":"106"},{"v":4.660971236945086,"d":"4.661"},{"v":118.30398407356745,"d":"118.304"}]
["2010-04-11",110,{"v":107.7387296618399,"d":"108"},{"v":4.679709126407304,"d":"4.680"},{"v":116.11775889752437,"d":"116.118"}]
["2010-04-12",110,{"v":108.7387296618399,"d":"109"},{"v":4.688948029304859,"d":"4.689"},{"v":115.0398188149777,"d":"115.040"}]
["2010-04-13",109,{"v":109.7387296618399,"d":"110"},{"v":4.698102355673906,"d":"4.698"},{"v":113.9717466173015,"d":"113.972"}]
["2010-04-14",110,{"v":110.7387296618399,"d":"111"},{"v":4.7071736399712485,"d":"4.707"},{"v":112.91336327322836,"d":"112.913"}]
["2010-04-15",112,{"v":111.7387296618399,"d":"112"},{"v":4.716163375269761,"d":"4.716"},{"v":111.86449457992126,"d":"111.864"}]
["2010-04-18",112,{"v":114.7387296618399,"d":"115"},{"v":4.742657627662548,"d":"4.743"},{"v":108.77330324173215,"d":"108.773"}]
["2010-04-19",115,{"v":115.7387296618399,"d":"116"},{"v":4.75133532029351,"d":"4.751"},{"v":107.76084182562522,"d":"107.761"}]
["2010-04-20",100,{"v":116.7387296618399,"d":"117"},{"v":4.759938357943609,"d":"4.760"},{"v":106.75709070738878,"d":"106.757"}]
["2010-04-22",95,{"v":118.7387296618399,"d":"119"},{"v":4.776925530299869,"d":"4.777"},{"v":104.77512876071796,"d":"104.775"}]
["2010-04-24",94,{"v":120.7387296618399,"d":"121"},{"v":4.793628952042763,"d":"4.794"},{"v":102.82627314311969,"d":"102.826"}]
["2010-04-27",97,{"v":123.7387296618399,"d":"124"},{"v":4.818172323861685,"d":"4.818"},{"v":99.96269891381792,"d":"99.963"}]
["2010-04-28",90,{"v":124.7387296618399,"d":"125"},{"v":4.826221387158353,"d":"4.826"},{"v":99.02358221883355,"d":"99.024"}]
["2010-04-29",87,{"v":125.7387296618399,"d":"126"},{"v":4.834206180007745,"d":"4.834"},{"v":98.09196421628167,"d":"98.092"}]
["2010-04-30",85,{"v":126.7387296618399,"d":"127"},{"v":4.8421277206625595,"d":"4.842"},{"v":97.16772610251087,"d":"97.168"}]
["2010-05-02",86,{"v":128.7387296618399,"d":"129"},{"v":4.857784999105224,"d":"4.858"},{"v":95.34092824522338,"d":"95.341"}]
["2010-05-06",86,{"v":132.7387296618399,"d":"133"},{"v":4.888382757548736,"d":"4.888"},{"v":91.77096429733206,"d":"91.771"}]
["2010-05-07",84,{"v":133.7387296618399,"d":"134"},{"v":4.8958881180151455,"d":"4.896"},{"v":90.895283605543,"d":"90.895"}]
["2010-05-08",89,{"v":134.7387296618399,"d":"135"},{"v":4.903337567418007,"d":"4.903"},{"v":90.02612628315433,"d":"90.026"}]
["2010-05-10",86,{"v":136.7387296618399,"d":"137"},{"v":4.918072022270195,"d":"4.918"},{"v":88.30699797801219,"d":"88.307"}]
["2010-05-12",84,{"v":138.7387296618399,"d":"139"},{"v":4.932592521664984,"d":"4.933"},{"v":86.61283271945342,"d":"86.613"}]
["2010-05-13",86,{"v":139.7387296618399,"d":"140"},{"v":4.939774462356205,"d":"4.940"},{"v":85.7748867179223,"d":"85.775"}]
["2010-05-14",82,{"v":140.7387296618399,"d":"141"},{"v":4.946905190363234,"d":"4.947"},{"v":84.94291590691319,"d":"84.943"}]
["2010-05-16",80,{"v":142.7387296618399,"d":"143"},{"v":4.961015893838473,"d":"4.961"},{"v":83.29656319192623,"d":"83.297"}]
["2010-05-18",78,{"v":144.7387296618399,"d":"145"},{"v":4.974930252709124,"d":"4.975"},{"v":81.67311879426063,"d":"81.673"}]
["2010-05-20",77,{"v":146.7387296618399,"d":"147"},{"v":4.988653656180364,"d":"4.989"},{"v":80.07195393360132,"d":"80.072"}]
["2010-05-25",80,{"v":151.7387296618399,"d":"152"},{"v":5.022160158066791,"d":"5.022"},{"v":76.16261515065321,"d":"76.163"}]
["2010-05-28",82,{"v":154.7387296618399,"d":"155"},{"v":5.04173807958677,"d":"5.042"},{"v":73.87838004467312,"d":"73.878"}]
["2010-06-01",79,{"v":158.7387296618399,"d":"159"},{"v":5.067259640996463,"d":"5.067"},{"v":70.90067648855472,"d":"70.901"}]
["2010-06-02",78,{"v":159.7387296618399,"d":"160"},{"v":5.073539540921249,"d":"5.074"},{"v":70.16797522322372,"d":"70.168"}]
["2010-06-03",78,{"v":160.7387296618399,"d":"161"},{"v":5.079780249691503,"d":"5.080"},{"v":69.43984654803899,"d":"69.440"}]
["2010-06-04",79,{"v":161.7387296618399,"d":"162"},{"v":5.085982253437746,"d":"5.086"},{"v":68.71623374419107,"d":"68.716"}]
["2010-06-05",73,{"v":162.7387296618399,"d":"163"},{"v":5.092146029301213,"d":"5.092"},{"v":67.99708114168641,"d":"67.997"}]
["2010-06-07",72,{"v":164.7387296618399,"d":"165"},{"v":5.104360762313284,"d":"5.104"},{"v":66.57193895139437,"d":"66.572"}]
["2010-06-08",68,{"v":165.7387296618399,"d":"166"},{"v":5.110412630747139,"d":"5.110"},{"v":65.86584304027951,"d":"65.866"}]
["2010-06-09",67,{"v":166.7387296618399,"d":"167"},{"v":5.116428094276702,"d":"5.116"},{"v":65.16399463625214,"d":"65.164"}]
["2010-06-10",66,{"v":167.7387296618399,"d":"168"},{"v":5.122407588270404,"d":"5.122"},{"v":64.46634294312048,"d":"64.466"}]
["2010-06-11",67,{"v":168.7387296618399,"d":"169"},{"v":5.1283515403331785,"d":"5.128"},{"v":63.7728380704915,"d":"63.773"}]
["2010-06-12",66,{"v":169.7387296618399,"d":"170"},{"v":5.134260370489959,"d":"5.134"},{"v":63.083431012361416,"d":"63.083"}]
["2010-06-13",67,{"v":170.7387296618399,"d":"171"},{"v":5.140134491363782,"d":"5.140"},{"v":62.39807362633519,"d":"62.398"}]
["2010-06-14",68,{"v":171.7387296618399,"d":"172"},{"v":5.145974308348692,"d":"5.146"},{"v":61.71671861345408,"d":"61.717"}]
["2010-06-15",66,{"v":172.7387296618399,"d":"173"},{"v":5.151780219777628,"d":"5.152"},{"v":61.03931949860669,"d":"61.039"}]
["2010-06-16",67,{"v":173.7387296618399,"d":"174"},{"v":5.157552617085462,"d":"5.158"},{"v":60.365830611506794,"d":"60.366"}]
["2010-06-17",65,{"v":174.7387296618399,"d":"175"},{"v":5.1632918849673635,"d":"5.163"},{"v":59.69620706821672,"d":"59.696"}]
["2010-06-18",65,{"v":175.7387296618399,"d":"176"},{"v":5.168998401532637,"d":"5.169"},{"v":59.03040475319813,"d":"59.030"}]
["2010-06-19",64,{"v":176.7387296618399,"d":"177"},{"v":5.174672538454204,"d":"5.175"},{"v":58.3683803018713,"d":"58.368"}]
["2010-06-20",60,{"v":177.7387296618399,"d":"178"},{"v":5.180314661113863,"d":"5.180"},{"v":57.710091083667635,"d":"57.710"}]
["2010-06-21",55,{"v":178.7387296618399,"d":"179"},{"v":5.1859251287434756,"d":"5.186"},{"v":57.0554951855562,"d":"57.055"}]
["2010-06-22",59,{"v":179.7387296618399,"d":"180"},{"v":5.191504294562211,"d":"5.192"},{"v":56.40455139603114,"d":"56.405"}]
["2010-06-24",54,{"v":181.7387296618399,"d":"182"},{"v":5.202570104377249,"d":"5.203"},{"v":55.11345871135495,"d":"55.113"}]
["2010-06-25",44,{"v":182.7387296618399,"d":"183"},{"v":5.208057425931121,"d":"5.208"},{"v":54.473230762828166,"d":"54.473"}]
["2010-06-27",45,{"v":184.7387296618399,"d":"185"},{"v":5.218942554783996,"d":"5.219"},{"v":53.203218855104296,"d":"53.203"}]
["2010-06-28",41,{"v":185.7387296618399,"d":"186"},{"v":5.224341006989058,"d":"5.224"},{"v":52.57335965211519,"d":"52.573"}]
["2010-06-29",39,{"v":186.7387296618399,"d":"187"},{"v":5.229710472322134,"d":"5.230"},{"v":51.94688246445048,"d":"51.947"}]
["2010-06-30",38,{"v":187.7387296618399,"d":"188"},{"v":5.235051260410188,"d":"5.235"},{"v":51.32375116668311,"d":"51.324"}]
["2010-07-01",36,{"v":188.7387296618399,"d":"189"},{"v":5.240363675945549,"d":"5.240"},{"v":50.70393020912934,"d":"50.704"}]
["2010-07-02",36,{"v":189.7387296618399,"d":"190"},{"v":5.245648018790215,"d":"5.246"},{"v":50.08738460567986,"d":"50.087"}]
["2010-07-05",41,{"v":192.7387296618399,"d":"193"},{"v":5.261335539459426,"d":"5.261"},{"v":48.25705826578553,"d":"48.257"}]
["2010-07-06",40,{"v":193.7387296618399,"d":"194"},{"v":5.266510497054268,"d":"5.267"},{"v":47.65327508083237,"d":"47.653"}]
["2010-07-07",40,{"v":194.7387296618399,"d":"195"},{"v":5.271658812276996,"d":"5.272"},{"v":47.052600368942876,"d":"47.053"}]
["2010-07-08",43,{"v":195.7387296618399,"d":"196"},{"v":5.276780758050385,"d":"5.277"},{"v":46.4550022871158,"d":"46.455"}]
["2010-07-09",43,{"v":196.7387296618399,"d":"197"},{"v":5.281876603124861,"d":"5.282"},{"v":45.86044947915423,"d":"45.860"}]
["2010-07-11",50,{"v":198.7387296618399,"d":"199"},{"v":5.291991045822639,"d":"5.292"},{"v":44.68035663507408,"d":"44.680"}]
["2010-07-12",53,{"v":199.7387296618399,"d":"200"},{"v":5.297010160836017,"d":"5.297"},{"v":44.0947562329676,"d":"44.095"}]
["2010-07-13",48,{"v":200.7387296618399,"d":"201"},{"v":5.302004210089452,"d":"5.302"},{"v":43.51208035422076,"d":"43.512"}]
["2010-07-14",47,{"v":201.7387296618399,"d":"202"},{"v":5.30697344269916,"d":"5.307"},{"v":42.93229993343948,"d":"42.932"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}