{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":84,"n_cols":10,"rows_kept":84,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-21T21:16:42.460"]
["2010-03-23",144,{"v":81.15782268958719,"d":"81"},{"v":4.396395687214648,"d":"4.396"},{"v":139.0685882329375,"d":"139.069"},{"v":3411.0408522945404,"d":"3411.041"},"Forecast Zero Critical Issues Date(s) ->","2010-08-27T15:19:40.836",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":82.15782268958719,"d":"82"},{"v":4.4086420644121285,"d":"4.409"},{"v":137.72816524340942,"d":"137.728"}]
["2010-03-25",146,{"v":83.15782268958719,"d":"83"},{"v":4.420740280463157,"d":"4.421"},{"v":136.4039591810311,"d":"136.404"},"Date '0' ref",null,"2010-10-10T17:13:04.048",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":84.15782268958719,"d":"84"},{"v":4.4326938775709355,"d":"4.433"},{"v":135.09558233517345,"d":"135.096"},"2009-12-31T20:12:44.120"]
["2010-03-27",137,{"v":85.15782268958719,"d":"85"},{"v":4.444506272408472,"d":"4.445"},{"v":133.8026607350717,"d":"133.803"}]
["2010-03-28",134,{"v":86.15782268958719,"d":"86"},{"v":4.45618076198086,"d":"4.456"},{"v":132.52483350817113,"d":"132.525"},"Min '0' Ref"]
["2010-03-30",131,{"v":88.15782268958719,"d":"88"},{"v":4.479128647839949,"d":"4.479"},{"v":130.01308058152472,"d":"130.013"},"2010-03-22"]
["2010-04-01",131,{"v":90.15782268958719,"d":"90"},{"v":4.5015617200342755,"d":"4.502"},{"v":127.55767640687594,"d":"127.558"}]
["2010-04-02",128,{"v":91.15782268958719,"d":"91"},{"v":4.512592319598905,"d":"4.513"},{"v":126.35032593854726,"d":"126.350"}]
["2010-04-04",128,{"v":93.15782268958719,"d":"93"},{"v":4.534295073012523,"d":"4.534"},{"v":123.97485855398418,"d":"123.975"}]
["2010-04-05",130,{"v":94.15782268958719,"d":"94"},{"v":4.544972339167115,"d":"4.545"},{"v":122.80618207210438,"d":"122.806"}]
["2010-04-06",127,{"v":95.15782268958719,"d":"95"},{"v":4.555536804651632,"d":"4.556"},{"v":121.64985214863651,"d":"121.650"}]
["2010-04-07",121,{"v":96.15782268958719,"d":"96"},{"v":4.565990827951382,"d":"4.566"},{"v":120.50561063638503,"d":"120.506"}]
["2010-04-08",120,{"v":97.15782268958719,"d":"97"},{"v":4.576336694347955,"d":"4.576"},{"v":119.3732074006424,"d":"119.373"}]
["2010-04-09",116,{"v":98.15782268958719,"d":"98"},{"v":4.586576618917724,"d":"4.587"},{"v":118.25239999098858,"d":"118.252"}]
["2010-04-11",110,{"v":100.15782268958719,"d":"100"},{"v":4.606747168792696,"d":"4.607"},{"v":116.04463941593491,"d":"116.045"}]
["2010-04-12",110,{"v":101.15782268958719,"d":"101"},{"v":4.616681898137819,"d":"4.617"},{"v":114.95723704426194,"d":"114.957"}]
["2010-04-13",109,{"v":102.15782268958719,"d":"102"},{"v":4.626518898748409,"d":"4.627"},{"v":113.88053153749797,"d":"113.881"}]
["2010-04-14",110,{"v":103.15782268958719,"d":"103"},{"v":4.636260074640612,"d":"4.636"},{"v":112.81431449221282,"d":"112.814"}]
["2010-04-15",112,{"v":104.15782268958719,"d":"104"},{"v":4.64590727472399,"d":"4.646"},{"v":111.75838353664852,"d":"111.758"}]
["2010-04-18",112,{"v":107.15782268958719,"d":"107"},{"v":4.674302726157065,"d":"4.674"},{"v":108.650369200233,"d":"108.650"}]
["2010-04-19",115,{"v":108.15782268958719,"d":"108"},{"v":4.683591481633335,"d":"4.684"},{"v":107.6336716754289,"d":"107.634"}]
["2010-04-20",100,{"v":109.15782268958719,"d":"109"},{"v":4.692794749594925,"d":"4.693"},{"v":106.62633115703943,"d":"106.626"}]
["2010-04-22",95,{"v":111.15782268958719,"d":"111"},{"v":4.710951017507114,"d":"4.711"},{"v":104.63904311902809,"d":"104.639"}]
["2010-04-24",94,{"v":113.15782268958719,"d":"113"},{"v":4.728783505258394,"d":"4.729"},{"v":102.68719432678188,"d":"102.687"}]
["2010-04-27",97,{"v":116.15782268958719,"d":"116"},{"v":4.754949806837343,"d":"4.755"},{"v":99.82317081829797,"d":"99.823"}]
["2010-04-28",90,{"v":117.15782268958719,"d":"117"},{"v":4.7635219377102604,"d":"4.764"},{"v":98.88491119212324,"d":"98.885"}]
["2010-04-29",87,{"v":118.15782268958719,"d":"118"},{"v":4.7720212112556775,"d":"4.772"},{"v":97.95462613958478,"d":"97.955"}]
["2010-04-30",85,{"v":119.15782268958719,"d":"119"},{"v":4.780448855519594,"d":"4.780"},{"v":97.03218124533134,"d":"97.032"}]
["2010-05-02",86,{"v":121.15782268958719,"d":"121"},{"v":4.797094015459328,"d":"4.797"},{"v":95.21029100891269,"d":"95.210"}]
["2010-05-06",86,{"v":125.15782268958719,"d":"125"},{"v":4.8295755224332195,"d":"4.830"},{"v":91.65503887350746,"d":"91.655"}]
["2010-05-07",84,{"v":126.15782268958719,"d":"126"},{"v":4.837533684179819,"d":"4.838"},{"v":90.78398102615324,"d":"90.784"}]
["2010-05-08",89,{"v":127.15782268958719,"d":"127"},{"v":4.845429013291315,"d":"4.845"},{"v":89.91980050318887,"d":"89.920"}]
["2010-05-10",86,{"v":129.1578226895872,"d":"129"},{"v":4.861035088281179,"d":"4.861"},{"v":88.21164295133622,"d":"88.212"}]
["2010-05-12",84,{"v":131.1578226895872,"d":"131"},{"v":4.876401351423801,"d":"4.876"},{"v":86.52973392245656,"d":"86.530"}]
["2010-05-13",86,{"v":132.1578226895872,"d":"132"},{"v":4.8839968348305645,"d":"4.884"},{"v":85.69837290761711,"d":"85.698"}]
["2010-05-14",82,{"v":133.1578226895872,"d":"133"},{"v":4.8915350614886375,"d":"4.892"},{"v":84.87327891044436,"d":"84.873"}]
["2010-05-16",80,{"v":135.1578226895872,"d":"135"},{"v":4.906443152583361,"d":"4.906"},{"v":83.24151894493741,"d":"83.242"}]
["2010-05-18",78,{"v":137.1578226895872,"d":"137"},{"v":4.921132253231242,"d":"4.921"},{"v":81.63372850320889,"d":"81.634"}]
["2010-05-20",77,{"v":139.1578226895872,"d":"139"},{"v":4.935608704067543,"d":"4.936"},{"v":80.04921357321462,"d":"80.049"}]
["2010-05-25",80,{"v":144.1578226895872,"d":"144"},{"v":4.970908690316358,"d":"4.971"},{"v":76.1854657615213,"d":"76.185"}]
["2010-05-28",82,{"v":147.1578226895872,"d":"147"},{"v":4.9915056345956375,"d":"4.992"},{"v":73.9310343341067,"d":"73.931"}]
["2010-06-01",79,{"v":151.1578226895872,"d":"151"},{"v":5.018324474365821,"d":"5.018"},{"v":70.99558748311324,"d":"70.996"}]
["2010-06-02",78,{"v":152.1578226895872,"d":"152"},{"v":5.024918289346561,"d":"5.025"},{"v":70.27386374013577,"d":"70.274"}]
["2010-06-03",78,{"v":153.1578226895872,"d":"153"},{"v":5.031468910587357,"d":"5.031"},{"v":69.55686775305651,"d":"69.557"}]
["2010-06-04",79,{"v":154.1578226895872,"d":"154"},{"v":5.037976900301046,"d":"5.038"},{"v":68.84453798506308,"d":"68.845"}]
["2010-06-05",73,{"v":155.1578226895872,"d":"155"},{"v":5.0444428097947,"d":"5.044"},{"v":68.13681409303047,"d":"68.137"}]
["2010-06-07",72,{"v":157.1578226895872,"d":"157"},{"v":5.0572505404939285,"d":"5.057"},{"v":66.73494834970984,"d":"66.735"}]
["2010-06-08",68,{"v":158.1578226895872,"d":"158"},{"v":5.063593412262716,"d":"5.064"},{"v":66.04069150938801,"d":"66.041"}]
["2010-06-09",67,{"v":159.1578226895872,"d":"159"},{"v":5.069896305455022,"d":"5.070"},{"v":65.35081051035718,"d":"65.351"}]
["2010-06-10",66,{"v":160.1578226895872,"d":"160"},{"v":5.076159720879018,"d":"5.076"},{"v":64.66525053683165,"d":"64.665"}]
["2010-06-11",67,{"v":161.1578226895872,"d":"161"},{"v":5.082384149991048,"d":"5.082"},{"v":63.983957796626896,"d":"63.984"}]
["2010-06-12",66,{"v":162.1578226895872,"d":"162"},{"v":5.0885700751270315,"d":"5.089"},{"v":63.30687949583137,"d":"63.307"}]
["2010-06-13",67,{"v":163.1578226895872,"d":"163"},{"v":5.094717969726751,"d":"5.095"},{"v":62.63396381425707,"d":"62.634"}]
["2010-06-14",68,{"v":164.1578226895872,"d":"164"},{"v":5.100828298551288,"d":"5.101"},{"v":61.96515988164015,"d":"61.965"}]
["2010-06-15",66,{"v":165.1578226895872,"d":"165"},{"v":5.10690151789386,"d":"5.107"},{"v":61.30041775456391,"d":"61.300"}]
["2010-06-16",67,{"v":166.1578226895872,"d":"166"},{"v":5.112938075784284,"d":"5.113"},{"v":60.6396883940796,"d":"60.640"}]
["2010-06-17",65,{"v":167.1578226895872,"d":"167"},{"v":5.118938412187318,"d":"5.119"},{"v":59.98292364399629,"d":"59.983"}]
["2010-06-18",65,{"v":168.1578226895872,"d":"168"},{"v":5.124902959195074,"d":"5.125"},{"v":59.33007620982107,"d":"59.330"}]
["2010-06-19",64,{"v":169.1578226895872,"d":"169"},{"v":5.130832141213738,"d":"5.131"},{"v":58.68109963832137,"d":"58.681"}]
["2010-06-20",60,{"v":170.1578226895872,"d":"170"},{"v":5.136726375144785,"d":"5.137"},{"v":58.035948297690084,"d":"58.036"}]
["2010-06-21",55,{"v":171.1578226895872,"d":"171"},{"v":5.142586070560876,"d":"5.143"},{"v":57.39457735829285,"d":"57.395"}]
["2010-06-22",59,{"v":172.1578226895872,"d":"172"},{"v":5.148411629876643,"d":"5.148"},{"v":56.7569427739752,"d":"56.757"}]
["2010-06-24",54,{"v":174.1578226895872,"d":"174"},{"v":5.159961915065801,"d":"5.160"},{"v":55.49271029497413,"d":"55.493"}]
["2010-06-25",44,{"v":175.1578226895872,"d":"175"},{"v":5.165687411447097,"d":"5.166"},{"v":54.86602806461394,"d":"54.866"}]
["2010-06-27",45,{"v":177.1578226895872,"d":"177"},{"v":5.177040988900377,"d":"5.177"},{"v":53.623326162953276,"d":"53.623"}]
["2010-06-28",41,{"v":178.1578226895872,"d":"178"},{"v":5.182669801778718,"d":"5.183"},{"v":53.007226392040366,"d":"53.007"}]
["2010-06-29",39,{"v":179.1578226895872,"d":"179"},{"v":5.188267108382841,"d":"5.188"},{"v":52.39457512949821,"d":"52.395"}]
["2010-06-30",38,{"v":180.1578226895872,"d":"180"},{"v":5.193833259451937,"d":"5.194"},{"v":51.78533398528975,"d":"51.785"}]
["2010-07-01",36,{"v":181.1578226895872,"d":"181"},{"v":5.199368599900769,"d":"5.199"},{"v":51.179465206888494,"d":"51.179"}]
["2010-07-02",36,{"v":182.1578226895872,"d":"182"},{"v":5.204873468947923,"d":"5.205"},{"v":50.57693166524109,"d":"50.577"}]
["2010-07-05",41,{"v":185.1578226895872,"d":"185"},{"v":5.221208557018468,"d":"5.221"},{"v":48.788980238248655,"d":"48.789"}]
["2010-07-06",40,{"v":186.1578226895872,"d":"186"},{"v":5.226594823016674,"d":"5.227"},{"v":48.199428352390214,"d":"48.199"}]
["2010-07-07",40,{"v":187.1578226895872,"d":"187"},{"v":5.2319522325128816,"d":"5.232"},{"v":47.61303494499873,"d":"47.613"}]
["2010-07-08",43,{"v":188.1578226895872,"d":"188"},{"v":5.237281093053107,"d":"5.237"},{"v":47.02976635373102,"d":"47.030"}]
["2010-07-09",43,{"v":189.1578226895872,"d":"189"},{"v":5.242581707292784,"d":"5.243"},{"v":46.449589451541215,"d":"46.450"}]
["2010-07-11",50,{"v":191.1578226895872,"d":"191"},{"v":5.253099383655487,"d":"5.253"},{"v":45.298380815252926,"d":"45.298"}]
["2010-07-12",53,{"v":192.1578226895872,"d":"192"},{"v":5.258317027551343,"d":"5.258"},{"v":44.72728540341018,"d":"44.727"}]
["2010-07-13",48,{"v":193.1578226895872,"d":"193"},{"v":5.263507588885418,"d":"5.264"},{"v":44.15915430402015,"d":"44.159"}]
["2010-07-14",47,{"v":194.1578226895872,"d":"194"},{"v":5.268671347354578,"d":"5.269"},{"v":43.593956902958894,"d":"43.594"}]
["2010-07-15",46,{"v":195.1578226895872,"d":"195"},{"v":5.2738085783450614,"d":"5.274"},{"v":43.031663057920696,"d":"43.032"}]
["2010-07-21",45,{"v":201.1578226895872,"d":"201"},{"v":5.304089787471013,"d":"5.304"},{"v":39.71724376406769,"d":"39.717"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}