{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":85,"n_cols":10,"rows_kept":85,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-22T22:46:49.080"]
["2010-03-23",144,{"v":80.57072313581739,"d":"81"},{"v":4.389135346997895,"d":"4.389"},{"v":139.09490087038205,"d":"139.095"},{"v":3411.6692855171095,"d":"3411.669"},"Forecast Zero Critical Issues Date(s) ->","2010-08-28T09:09:34.214",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":81.57072313581739,"d":"82"},{"v":4.401470412491011,"d":"4.401"},{"v":137.7516827616713,"d":"137.752"}]
["2010-03-25",146,{"v":82.57072313581739,"d":"83"},{"v":4.413655176242718,"d":"4.414"},{"v":136.42483165327712,"d":"136.425"},"Date '0' ref",null,"2010-10-11T08:17:40.664",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":83.57072313581739,"d":"84"},{"v":4.425693257031039,"d":"4.426"},{"v":135.11395348096255,"d":"135.114"},"2010-01-01T10:18:09.521"]
["2010-03-27",137,{"v":84.57072313581739,"d":"85"},{"v":4.437588144494447,"d":"4.438"},{"v":133.81866824304922,"d":"133.819"}]
["2010-03-28",134,{"v":85.57072313581739,"d":"86"},{"v":4.449343205204322,"d":"4.449"},{"v":132.53860933916178,"d":"132.539"},"Min '0' Ref"]
["2010-03-30",131,{"v":87.57072313581739,"d":"88"},{"v":4.472446731303137,"d":"4.472"},{"v":130.02276743720188,"d":"130.023"},"2010-03-22"]
["2010-04-01",131,{"v":89.57072313581739,"d":"90"},{"v":4.495028515869914,"d":"4.495"},{"v":127.56374020511868,"d":"127.564"}]
["2010-04-02",128,{"v":90.57072313581739,"d":"91"},{"v":4.506131016630321,"d":"4.506"},{"v":126.35474134883566,"d":"126.355"}]
["2010-04-04",128,{"v":92.57072313581739,"d":"93"},{"v":4.5279729268215085,"d":"4.528"},{"v":123.97628220615735,"d":"123.976"}]
["2010-04-05",130,{"v":93.57072313581739,"d":"94"},{"v":4.538717547544988,"d":"4.539"},{"v":122.80625443978175,"d":"122.806"}]
["2010-04-06",127,{"v":94.57072313581739,"d":"95"},{"v":4.549347947564934,"d":"4.549"},{"v":121.64866465498488,"d":"121.649"}]
["2010-04-07",121,{"v":95.57072313581739,"d":"96"},{"v":4.5598665298060945,"d":"4.560"},{"v":120.50325118700005,"d":"120.503"}]
["2010-04-08",120,{"v":96.57072313581739,"d":"97"},{"v":4.5702756221543455,"d":"4.570"},{"v":119.36976054236447,"d":"119.370"}]
["2010-04-09",116,{"v":97.57072313581739,"d":"98"},{"v":4.580577480548962,"d":"4.581"},{"v":118.2479470621891,"d":"118.248"}]
["2010-04-11",110,{"v":99.57072313581739,"d":"100"},{"v":4.60086817696092,"d":"4.601"},{"v":116.03840623128679,"d":"116.038"}]
["2010-04-12",110,{"v":100.57072313581739,"d":"101"},{"v":4.610861192803586,"d":"4.611"},{"v":114.95022393926774,"d":"114.950"}]
["2010-04-13",109,{"v":101.57072313581739,"d":"102"},{"v":4.620755335506821,"d":"4.621"},{"v":113.87280836684369,"d":"113.873"}]
["2010-04-14",110,{"v":102.57072313581739,"d":"103"},{"v":4.6305525424633025,"d":"4.631"},{"v":112.80594854302865,"d":"112.806"}]
["2010-04-15",112,{"v":103.57072313581739,"d":"104"},{"v":4.640254694673713,"d":"4.640"},{"v":111.7494396376025,"d":"111.749"}]
["2010-04-18",112,{"v":106.57072313581739,"d":"107"},{"v":4.668808831757533,"d":"4.669"},{"v":108.64005736225073,"d":"108.640"}]
["2010-04-19",115,{"v":107.57072313581739,"d":"108"},{"v":4.678148520888711,"d":"4.678"},{"v":107.62301861383645,"d":"107.623"}]
["2010-04-20",100,{"v":108.57072313581739,"d":"109"},{"v":4.687401786770694,"d":"4.687"},{"v":106.6153908631502,"d":"106.615"}]
["2010-04-22",95,{"v":110.57072313581739,"d":"111"},{"v":4.705655344605434,"d":"4.706"},{"v":104.62768277633825,"d":"104.628"}]
["2010-04-24",94,{"v":112.57072313581739,"d":"113"},{"v":4.723581674222933,"d":"4.724"},{"v":102.675607971516,"d":"102.676"}]
["2010-04-27",97,{"v":115.57072313581739,"d":"116"},{"v":4.7498826640917455,"d":"4.750"},{"v":99.81158054591992,"d":"99.812"}]
["2010-04-28",90,{"v":116.57072313581739,"d":"117"},{"v":4.758498154359505,"d":"4.758"},{"v":98.87340291325677,"d":"98.873"}]
["2010-04-29",87,{"v":117.57072313581739,"d":"118"},{"v":4.76704005154388,"d":"4.767"},{"v":97.94323914661925,"d":"97.943"}]
["2010-04-30",85,{"v":118.57072313581739,"d":"119"},{"v":4.77550960226067,"d":"4.776"},{"v":97.02095349667388,"d":"97.021"}]
["2010-05-02",86,{"v":120.57072313581739,"d":"121"},{"v":4.792236494754241,"d":"4.792"},{"v":95.19949053708422,"d":"95.199"}]
["2010-05-06",86,{"v":124.57072313581739,"d":"125"},{"v":4.824873611937083,"d":"4.825"},{"v":91.64549507264383,"d":"91.645"}]
["2010-05-07",84,{"v":125.57072313581739,"d":"126"},{"v":4.832869130810582,"d":"4.833"},{"v":90.77482878024227,"d":"90.775"}]
["2010-05-08",89,{"v":126.57072313581739,"d":"127"},{"v":4.840801228115186,"d":"4.841"},{"v":89.91106873409194,"d":"89.911"}]
["2010-05-10",86,{"v":128.5707231358174,"d":"129"},{"v":4.856479127532525,"d":"4.856"},{"v":88.20383512307717,"d":"88.204"}]
["2010-05-12",84,{"v":130.5707231358174,"d":"131"},{"v":4.871915019704507,"d":"4.872"},{"v":86.52295471744947,"d":"86.523"}]
["2010-05-13",86,{"v":131.5707231358174,"d":"132"},{"v":4.879544525568597,"d":"4.880"},{"v":85.69214514915973,"d":"85.692"}]
["2010-05-14",82,{"v":132.5707231358174,"d":"133"},{"v":4.887116262542938,"d":"4.887"},{"v":84.86762628268059,"d":"84.868"}]
["2010-05-16",80,{"v":134.5707231358174,"d":"135"},{"v":4.902089883416781,"d":"4.902"},{"v":83.23708457846828,"d":"83.237"}]
["2010-05-18",78,{"v":136.5707231358174,"d":"137"},{"v":4.916842598659235,"d":"4.917"},{"v":81.63059823452659,"d":"81.631"}]
["2010-05-20",77,{"v":138.5707231358174,"d":"139"},{"v":4.931380831656705,"d":"4.931"},{"v":80.04746778080039,"d":"80.047"}]
["2010-05-25",80,{"v":143.5707231358174,"d":"144"},{"v":4.966827757943923,"d":"4.967"},{"v":76.18750016946501,"d":"76.188"}]
["2010-05-28",82,{"v":146.5707231358174,"d":"147"},{"v":4.987508063750293,"d":"4.988"},{"v":73.93553310303196,"d":"73.936"}]
["2010-06-01",79,{"v":150.5707231358174,"d":"151"},{"v":5.014432894978778,"d":"5.014"},{"v":71.00357292006674,"d":"71.004"}]
["2010-06-02",78,{"v":151.5707231358174,"d":"152"},{"v":5.021052335401488,"d":"5.021"},{"v":70.2827537034783,"d":"70.283"}]
["2010-06-03",78,{"v":152.5707231358174,"d":"153"},{"v":5.027628246812491,"d":"5.028"},{"v":69.56667454739534,"d":"69.567"}]
["2010-06-04",79,{"v":153.5707231358174,"d":"154"},{"v":5.034161197961687,"d":"5.034"},{"v":68.85527351820588,"d":"68.855"}]
["2010-06-05",73,{"v":154.5707231358174,"d":"155"},{"v":5.040651746524361,"d":"5.041"},{"v":68.14848988825952,"d":"68.148"}]
["2010-06-07",72,{"v":156.5707231358174,"d":"157"},{"v":5.053507812923083,"d":"5.054"},{"v":66.74853775965596,"d":"66.749"}]
["2010-06-08",68,{"v":157.5707231358174,"d":"158"},{"v":5.059874393262258,"d":"5.060"},{"v":66.05525356048292,"d":"66.055"}]
["2010-06-09",67,{"v":158.5707231358174,"d":"159"},{"v":5.066200696548128,"d":"5.066"},{"v":65.36635530213812,"d":"65.366"}]
["2010-06-10",66,{"v":159.5707231358174,"d":"160"},{"v":5.072487229190079,"d":"5.072"},{"v":64.68178783953465,"d":"64.682"}]
["2010-06-11",67,{"v":160.5707231358174,"d":"161"},{"v":5.078734488106397,"d":"5.079"},{"v":64.00149706111222,"d":"64.001"}]
["2010-06-12",66,{"v":161.5707231358174,"d":"162"},{"v":5.0849429609599595,"d":"5.085"},{"v":63.32542986317162,"d":"63.325"}]
["2010-06-13",67,{"v":162.5707231358174,"d":"163"},{"v":5.091113126386682,"d":"5.091"},{"v":62.65353412499826,"d":"62.654"}]
["2010-06-14",68,{"v":163.5707231358174,"d":"164"},{"v":5.097245454216933,"d":"5.097"},{"v":61.98575868475086,"d":"61.986"}]
["2010-06-15",66,{"v":164.5707231358174,"d":"165"},{"v":5.1033404056902265,"d":"5.103"},{"v":61.32205331608384,"d":"61.322"}]
["2010-06-16",67,{"v":165.5707231358174,"d":"166"},{"v":5.1093984336633875,"d":"5.109"},{"v":60.662368705477775,"d":"60.662"}]
["2010-06-17",65,{"v":166.5707231358174,"d":"167"},{"v":5.115419982812471,"d":"5.115"},{"v":60.00665643025275,"d":"60.007"}]
["2010-06-18",65,{"v":167.5707231358174,"d":"168"},{"v":5.1214054898286205,"d":"5.121"},{"v":59.35486893723987,"d":"59.355"}]
["2010-06-19",64,{"v":168.5707231358174,"d":"169"},{"v":5.1273553836081165,"d":"5.127"},{"v":58.706959522086436,"d":"58.707"}]
["2010-06-20",60,{"v":169.5707231358174,"d":"170"},{"v":5.13327008543679,"d":"5.133"},{"v":58.062882309173915,"d":"58.063"}]
["2010-06-21",55,{"v":170.5707231358174,"d":"171"},{"v":5.139150009169018,"d":"5.139"},{"v":57.42259223212682,"d":"57.423"}]
["2010-06-22",59,{"v":171.5707231358174,"d":"172"},{"v":5.1449955614014975,"d":"5.145"},{"v":56.78604501488974,"d":"56.786"}]
["2010-06-24",54,{"v":173.5707231358174,"d":"174"},{"v":5.156585142472987,"d":"5.157"},{"v":55.52400589752267,"d":"55.524"}]
["2010-06-25",44,{"v":174.5707231358174,"d":"175"},{"v":5.162329949711206,"d":"5.162"},{"v":54.89842923416927,"d":"54.898"}]
["2010-06-27",45,{"v":176.5707231358174,"d":"177"},{"v":5.173721493768841,"d":"5.174"},{"v":53.65795521537052,"d":"53.658"}]
["2010-06-28",41,{"v":177.5707231358174,"d":"178"},{"v":5.17936896976104,"d":"5.179"},{"v":53.04297736823514,"d":"53.043"}]
["2010-06-29",39,{"v":178.5707231358174,"d":"179"},{"v":5.184984730793808,"d":"5.185"},{"v":52.43145309885722,"d":"52.431"}]
["2010-06-30",38,{"v":179.5707231358174,"d":"180"},{"v":5.19056913108706,"d":"5.191"},{"v":51.82334383471323,"d":"51.823"}]
["2010-07-01",36,{"v":180.5707231358174,"d":"181"},{"v":5.196122518959303,"d":"5.196"},{"v":51.21861164590939,"d":"51.219"}]
["2010-07-02",36,{"v":181.5707231358174,"d":"182"},{"v":5.2016452369580035,"d":"5.202"},{"v":50.6172192309848,"d":"50.617"}]
["2010-07-05",41,{"v":184.5707231358174,"d":"185"},{"v":5.2180327132603646,"d":"5.218"},{"v":48.83271675406763,"d":"48.833"}]
["2010-07-06",40,{"v":185.5707231358174,"d":"186"},{"v":5.223436066184444,"d":"5.223"},{"v":48.24432251332132,"d":"48.244"}]
["2010-07-07",40,{"v":186.5707231358174,"d":"187"},{"v":5.228810379725463,"d":"5.229"},{"v":47.659090495362875,"d":"47.659"}]
["2010-07-08",43,{"v":187.5707231358174,"d":"188"},{"v":5.234155964349871,"d":"5.234"},{"v":47.07698689217091,"d":"47.077"}]
["2010-07-09",43,{"v":188.5707231358174,"d":"189"},{"v":5.239473125571683,"d":"5.239"},{"v":46.49797843501608,"d":"46.498"}]
["2010-07-11",50,{"v":190.5707231358174,"d":"191"},{"v":5.250023375727289,"d":"5.250"},{"v":45.349116512203636,"d":"45.349"}]
["2010-07-12",53,{"v":191.5707231358174,"d":"192"},{"v":5.255257051856216,"d":"5.255"},{"v":44.77919910435321,"d":"44.779"}]
["2010-07-13",48,{"v":192.5707231358174,"d":"193"},{"v":5.260463479168925,"d":"5.260"},{"v":44.2122489367988,"d":"44.212"}]
["2010-07-14",47,{"v":193.5707231358174,"d":"194"},{"v":5.265642939935037,"d":"5.266"},{"v":43.64823527199235,"d":"43.648"}]
["2010-07-15",46,{"v":194.5707231358174,"d":"195"},{"v":5.27079571206073,"d":"5.271"},{"v":43.08712784754027,"d":"43.087"}]
["2010-07-21",45,{"v":200.5707231358174,"d":"201"},{"v":5.301166918395142,"d":"5.301"},{"v":39.77987711956132,"d":"39.780"}]
["2010-07-22",40,{"v":201.5707231358174,"d":"202"},{"v":5.306140303110811,"d":"5.306"},{"v":39.23830395844607,"d":"39.238"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}