{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":89,"n_cols":10,"rows_kept":89,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-07-28T23:35:50.420"]
["2010-03-23",144,{"v":74.52464612780022,"d":"75"},{"v":4.311129891183861,"d":"4.311"},{"v":139.38466643336795,"d":"139.385"},{"v":3451.021127894709,"d":"3451.021"},"Forecast Zero Critical Issues Date(s) ->","2010-08-31T22:21:50.053",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":75.52464612780022,"d":"76"},{"v":4.324459041764245,"d":"4.324"},{"v":138.01028027136817,"d":"138.010"}]
["2010-03-25",146,{"v":76.52464612780022,"d":"77"},{"v":4.3376128605515945,"d":"4.338"},{"v":136.65397280002844,"d":"136.654"},"Date '0' ref",null,"2010-10-16T15:46:14.144",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":77.52464612780022,"d":"78"},{"v":4.3505959003556525,"d":"4.351"},{"v":135.31527457317742,"d":"135.315"},"2010-01-07T11:24:30.575"]
["2010-03-27",137,{"v":78.52464612780022,"d":"79"},{"v":4.363412538923632,"d":"4.363"},{"v":133.99373419557008,"d":"133.994"}]
["2010-03-28",134,{"v":79.52464612780022,"d":"80"},{"v":4.376066987801984,"d":"4.376"},{"v":132.6889174091399,"d":"132.689"},"Min '0' Ref"]
["2010-03-30",131,{"v":81.52464612780022,"d":"82"},{"v":4.400905381007271,"d":"4.401"},{"v":130.12779817638875,"d":"130.128"},"2010-03-22"]
["2010-04-01",131,{"v":83.52464612780022,"d":"84"},{"v":4.425141751511909,"d":"4.425"},{"v":127.62875429224982,"d":"127.629"}]
["2010-04-02",128,{"v":84.52464612780022,"d":"85"},{"v":4.43704316198714,"d":"4.437"},{"v":126.4015842811682,"d":"126.402"}]
["2010-04-04",128,{"v":86.52464612780022,"d":"87"},{"v":4.460429299686985,"d":"4.460"},{"v":123.9902090143458,"d":"123.990"}]
["2010-04-05",130,{"v":87.52464612780022,"d":"88"},{"v":4.471920423734015,"d":"4.472"},{"v":122.80534417387321,"d":"122.805"}]
["2010-04-06",127,{"v":88.52464612780022,"d":"89"},{"v":4.483281000563265,"d":"4.483"},{"v":121.63394022789066,"d":"121.634"}]
["2010-04-07",121,{"v":89.52464612780022,"d":"90"},{"v":4.494513963101484,"d":"4.495"},{"v":120.47569475848229,"d":"120.476"}]
["2010-04-08",120,{"v":90.52464612780022,"d":"91"},{"v":4.505622146533876,"d":"4.506"},{"v":119.33031542599105,"d":"119.330"}]
["2010-04-09",116,{"v":91.52464612780022,"d":"92"},{"v":4.516608292599483,"d":"4.517"},{"v":118.19751952611574,"d":"118.198"}]
["2010-04-11",110,{"v":93.52464612780022,"d":"94"},{"v":4.5382249965093315,"d":"4.538"},{"v":115.96859289327642,"d":"115.969"}]
["2010-04-12",110,{"v":94.52464612780022,"d":"95"},{"v":4.54886060608102,"d":"4.549"},{"v":114.87194127008343,"d":"114.872"}]
["2010-04-13",109,{"v":95.52464612780022,"d":"96"},{"v":4.559384288827806,"d":"4.559"},{"v":113.78683056829988,"d":"113.787"}]
["2010-04-14",110,{"v":96.52464612780022,"d":"97"},{"v":4.569798376023924,"d":"4.570"},{"v":112.7130204071882,"d":"112.713"}]
["2010-04-15",112,{"v":97.52464612780022,"d":"98"},{"v":4.5801051268580695,"d":"4.580"},{"v":111.650277838845,"d":"111.650"}]
["2010-04-18",112,{"v":100.52464612780022,"d":"101"},{"v":4.610402932536408,"d":"4.610"},{"v":108.52623144052836,"d":"108.526"}]
["2010-04-19",115,{"v":101.52464612780022,"d":"102"},{"v":4.6203015879991876,"d":"4.620"},{"v":107.50556812005618,"d":"107.506"}]
["2010-04-20",100,{"v":102.52464612780022,"d":"103"},{"v":4.630103219702307,"d":"4.630"},{"v":106.49490904643056,"d":"106.495"}]
["2010-04-22",95,{"v":104.52464612780022,"d":"105"},{"v":4.6494228917099925,"d":"4.649"},{"v":104.50283237945865,"d":"104.503"}]
["2010-04-24",94,{"v":106.52464612780022,"d":"107"},{"v":4.668376377416602,"d":"4.668"},{"v":102.54851366126798,"d":"102.549"}]
["2010-04-27",97,{"v":109.52464612780022,"d":"110"},{"v":4.69614960272282,"d":"4.696"},{"v":99.68478004937936,"d":"99.685"}]
["2010-04-28",90,{"v":110.52464612780022,"d":"111"},{"v":4.70523853796821,"d":"4.705"},{"v":98.74760804031223,"d":"98.748"}]
["2010-04-29",87,{"v":111.52464612780022,"d":"112"},{"v":4.714245607979034,"d":"4.714"},{"v":97.81887726272925,"d":"97.819"}]
["2010-04-30",85,{"v":112.52464612780022,"d":"113"},{"v":4.723172274342239,"d":"4.723"},{"v":96.89843701048744,"d":"96.898"}]
["2010-05-02",86,{"v":114.52464612780022,"d":"115"},{"v":4.740790049855788,"d":"4.741"},{"v":95.08184511852733,"d":"95.082"}]
["2010-05-06",86,{"v":118.52464612780022,"d":"119"},{"v":4.775120923150316,"d":"4.775"},{"v":91.54194383968593,"d":"91.542"}]
["2010-05-07",84,{"v":119.52464612780022,"d":"120"},{"v":4.7835225938535295,"d":"4.784"},{"v":90.67563657707842,"d":"90.676"}]
["2010-05-08",89,{"v":120.52464612780022,"d":"121"},{"v":4.791854264197769,"d":"4.792"},{"v":89.81654714310355,"d":"89.817"}]
["2010-05-10",86,{"v":122.52464612780022,"d":"123"},{"v":4.80831220262821,"d":"4.808"},{"v":88.11954757081787,"d":"88.120"}]
["2010-05-12",84,{"v":124.52464612780022,"d":"125"},{"v":4.824503657178961,"d":"4.825"},{"v":86.45002550015033,"d":"86.450"}]
["2010-05-13",86,{"v":125.52464612780022,"d":"126"},{"v":4.832502122779574,"d":"4.833"},{"v":85.62529324340085,"d":"85.625"}]
["2010-05-14",82,{"v":126.52464612780022,"d":"127"},{"v":4.840437120240275,"d":"4.840"},{"v":84.8071052696269,"d":"84.807"}]
["2010-05-16",80,{"v":128.52464612780022,"d":"129"},{"v":4.856120684604187,"d":"4.856"},{"v":83.18995242086874,"d":"83.190"}]
["2010-05-18",78,{"v":130.52464612780022,"d":"131"},{"v":4.871562068147951,"d":"4.872"},{"v":81.59777115345071,"d":"81.598"}]
["2010-05-20",77,{"v":132.52464612780022,"d":"133"},{"v":4.8867686366405385,"d":"4.887"},{"v":80.02980197329362,"d":"80.030"}]
["2010-05-25",80,{"v":137.52464612780022,"d":"138"},{"v":4.923803145610058,"d":"4.924"},{"v":76.21112528139145,"d":"76.211"}]
["2010-05-28",82,{"v":140.52464612780022,"d":"141"},{"v":4.9453828906697055,"d":"4.945"},{"v":73.98600952396936,"d":"73.986"}]
["2010-06-01",79,{"v":144.52464612780022,"d":"145"},{"v":4.9734500544466025,"d":"4.973"},{"v":71.09196753165213,"d":"71.092"}]
["2010-06-02",78,{"v":145.52464612780022,"d":"146"},{"v":4.9803454614613205,"d":"4.980"},{"v":70.38097308941576,"d":"70.381"}]
["2010-06-03",78,{"v":146.52464612780022,"d":"147"},{"v":4.9871936472618135,"d":"4.987"},{"v":69.67484768838278,"d":"69.675"}]
["2010-06-04",79,{"v":147.52464612780022,"d":"148"},{"v":4.993995254213361,"d":"4.994"},{"v":68.97352509342863,"d":"68.974"}]
["2010-06-05",73,{"v":148.52464612780022,"d":"149"},{"v":5.000750911662298,"d":"5.001"},{"v":68.27694041182917,"d":"68.277"}]
["2010-06-07",72,{"v":150.52464612780022,"d":"151"},{"v":5.014126832427968,"d":"5.014"},{"v":66.89773171480988,"d":"66.898"}]
["2010-06-08",68,{"v":151.52464612780022,"d":"152"},{"v":5.0207482924299045,"d":"5.021"},{"v":66.2149843076129,"d":"66.215"}]
["2010-06-09",67,{"v":152.52464612780022,"d":"153"},{"v":5.027326196942127,"d":"5.027"},{"v":65.53672796396711,"d":"65.537"}]
["2010-06-10",66,{"v":153.52464612780022,"d":"154"},{"v":5.03386111523186,"d":"5.034"},{"v":64.86290398598408,"d":"64.863"}]
["2010-06-11",67,{"v":154.52464612780022,"d":"155"},{"v":5.040353605478326,"d":"5.040"},{"v":64.19345481907362,"d":"64.193"}]
["2010-06-12",66,{"v":155.52464612780022,"d":"156"},{"v":5.04680421505884,"d":"5.047"},{"v":63.528324022444394,"d":"63.528"}]
["2010-06-13",67,{"v":156.52464612780022,"d":"157"},{"v":5.053213480825753,"d":"5.053"},{"v":62.86745624054777,"d":"62.867"}]
["2010-06-14",68,{"v":157.52464612780022,"d":"158"},{"v":5.059581929374557,"d":"5.060"},{"v":62.2107971754333,"d":"62.211"}]
["2010-06-15",66,{"v":158.52464612780022,"d":"159"},{"v":5.065910077303523,"d":"5.066"},{"v":61.55829355997719,"d":"61.558"}]
["2010-06-16",67,{"v":159.52464612780022,"d":"160"},{"v":5.0721984314651625,"d":"5.072"},{"v":60.90989313195371,"d":"60.910"}]
["2010-06-17",65,{"v":160.52464612780022,"d":"161"},{"v":5.078447489209844,"d":"5.078"},{"v":60.26554460891521,"d":"60.266"}]
["2010-06-18",65,{"v":161.52464612780022,"d":"162"},{"v":5.084657738621834,"d":"5.085"},{"v":59.62519766385424,"d":"59.625"}]
["2010-06-19",64,{"v":162.52464612780022,"d":"163"},{"v":5.090829658748062,"d":"5.091"},{"v":58.98880290161492,"d":"58.989"}]
["2010-06-20",60,{"v":163.52464612780022,"d":"164"},{"v":5.096963719819864,"d":"5.097"},{"v":58.35631183602857,"d":"58.356"}]
["2010-06-21",55,{"v":164.52464612780022,"d":"165"},{"v":5.103060383467967,"d":"5.103"},{"v":57.72767686774705,"d":"57.728"}]
["2010-06-22",59,{"v":165.52464612780022,"d":"166"},{"v":5.109120102930964,"d":"5.109"},{"v":57.1028512627455,"d":"57.103"}]
["2010-06-24",54,{"v":167.52464612780022,"d":"168"},{"v":5.121130481502431,"d":"5.121"},{"v":55.86444540863988,"d":"55.864"}]
["2010-06-25",44,{"v":168.52464612780022,"d":"169"},{"v":5.127082006917094,"d":"5.127"},{"v":55.250775833570174,"d":"55.251"}]
["2010-06-27",45,{"v":170.52464612780022,"d":"171"},{"v":5.138879838346138,"d":"5.139"},{"v":54.03428599350889,"d":"54.034"}]
["2010-06-28",41,{"v":171.52464612780022,"d":"172"},{"v":5.144726965480818,"d":"5.145"},{"v":53.4313810617283,"d":"53.431"}]
["2010-06-29",39,{"v":172.52464612780022,"d":"173"},{"v":5.150540102368786,"d":"5.151"},{"v":52.83198090877397,"d":"52.832"}]
["2010-06-30",38,{"v":173.52464612780022,"d":"174"},{"v":5.156319641908197,"d":"5.156"},{"v":52.23604502240278,"d":"52.236"}]
["2010-07-01",36,{"v":174.52464612780022,"d":"175"},{"v":5.162065970223986,"d":"5.162"},{"v":51.64353358876713,"d":"51.644"}]
["2010-07-02",36,{"v":175.52464612780022,"d":"176"},{"v":5.16777946682266,"d":"5.168"},{"v":51.05440747645446,"d":"51.054"}]
["2010-07-05",41,{"v":178.52464612780022,"d":"179"},{"v":5.184726665233518,"d":"5.185"},{"v":49.30695966722749,"d":"49.307"}]
["2010-07-06",40,{"v":179.52464612780022,"d":"180"},{"v":5.190312502836106,"d":"5.190"},{"v":48.73099664108588,"d":"48.731"}]
["2010-07-07",40,{"v":180.52464612780022,"d":"181"},{"v":5.1958673120960235,"d":"5.196"},{"v":48.15823298796795,"d":"48.158"}]
["2010-07-08",43,{"v":181.52464612780022,"d":"182"},{"v":5.2013914358238384,"d":"5.201"},{"v":47.58863336022739,"d":"47.589"}]
["2010-07-09",43,{"v":182.52464612780022,"d":"183"},{"v":5.206885211180102,"d":"5.207"},{"v":47.0221629927986,"d":"47.022"}]
["2010-07-11",50,{"v":184.52464612780022,"d":"185"},{"v":5.2177830379076315,"d":"5.218"},{"v":45.89847381546792,"d":"45.898"}]
["2010-07-12",53,{"v":185.52464612780022,"d":"186"},{"v":5.223187736444596,"d":"5.223"},{"v":45.341188275463765,"d":"45.341"}]
["2010-07-13",48,{"v":186.52464612780022,"d":"187"},{"v":5.228563381172024,"d":"5.229"},{"v":44.78689851178774,"d":"44.787"}]
["2010-07-14",47,{"v":187.52464612780022,"d":"188"},{"v":5.2339102827871296,"d":"5.234"},{"v":44.23557248804309,"d":"44.236"}]
["2010-07-15",46,{"v":188.52464612780022,"d":"189"},{"v":5.239228747029796,"d":"5.239"},{"v":43.68717867899056,"d":"43.687"}]
["2010-07-21",45,{"v":194.52464612780022,"d":"195"},{"v":5.270558870340821,"d":"5.271"},{"v":40.45668865843436,"d":"40.457"}]
["2010-07-22",40,{"v":195.52464612780022,"d":"196"},{"v":5.275686438629498,"d":"5.276"},{"v":39.92797838104889,"d":"39.928"}]
["2010-07-24",38,{"v":197.52464612780022,"d":"198"},{"v":5.2858633670759945,"d":"5.286"},{"v":38.87862196901233,"d":"38.879"}]
["2010-07-26",39,{"v":199.52464612780022,"d":"200"},{"v":5.295937768187264,"d":"5.296"},{"v":37.8398372847023,"d":"37.840"}]
["2010-07-27",41,{"v":200.52464612780022,"d":"201"},{"v":5.300937162522845,"d":"5.301"},{"v":37.32434319137917,"d":"37.324"}]
["2010-07-28",41,{"v":201.52464612780022,"d":"202"},{"v":5.305911687196408,"d":"5.306"},{"v":36.81141344145692,"d":"36.811"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}