{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":94,"n_cols":10,"rows_kept":94,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-08-03T22:09:12.950"]
["2010-03-23",144,{"v":74.63556645302742,"d":"75"},{"v":4.312617155699698,"d":"4.313"},{"v":139.37902032599374,"d":"139.379"},{"v":3456.822316956509,"d":"3456.822"},"Forecast Zero Critical Issues Date(s) ->","2010-09-04T01:46:05.645",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":75.63556645302742,"d":"76"},{"v":4.325926628283764,"d":"4.326"},{"v":138.00524831348866,"d":"138.005"}]
["2010-03-25",146,{"v":76.63556645302742,"d":"77"},{"v":4.339061282994343,"d":"4.339"},{"v":136.64952058488478,"d":"136.650"},"Date '0' ref",null,"2010-10-17T09:32:49.551",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":77.63556645302742,"d":"78"},{"v":4.352025652768045,"d":"4.352"},{"v":135.31136926127772,"d":"135.311"},"2010-01-07T08:44:47.058"]
["2010-03-27",137,{"v":78.63556645302742,"d":"79"},{"v":4.3648240964905645,"d":"4.365"},{"v":133.9903444288837,"d":"133.990"}]
["2010-03-28",134,{"v":79.63556645302742,"d":"80"},{"v":4.377460807794883,"d":"4.377"},{"v":132.6860132309095,"d":"132.686"},"Min '0' Ref"]
["2010-03-30",131,{"v":81.63556645302742,"d":"82"},{"v":4.402265030404148,"d":"4.402"},{"v":130.12578053969452,"d":"130.126"},"2010-03-22"]
["2010-04-01",131,{"v":83.63556645302742,"d":"84"},{"v":4.426468865659401,"d":"4.426"},{"v":127.62751839903251,"d":"127.628"}]
["2010-04-02",128,{"v":84.63556645302742,"d":"85"},{"v":4.438354585511998,"d":"4.438"},{"v":126.40070274733478,"d":"126.401"}]
["2010-04-04",128,{"v":86.63556645302742,"d":"87"},{"v":4.4617104293269305,"d":"4.462"},{"v":123.98996826039445,"d":"123.990"}]
["2010-04-05",130,{"v":87.63556645302742,"d":"88"},{"v":4.473186925280451,"d":"4.473"},{"v":122.80539172342117,"d":"122.805"}]
["2010-04-06",127,{"v":88.63556645302742,"d":"89"},{"v":4.484533204295751,"d":"4.485"},{"v":121.63425586819915,"d":"121.634"}]
["2010-04-07",121,{"v":89.63556645302742,"d":"90"},{"v":4.495752188238654,"d":"4.496"},{"v":120.47625910670791,"d":"120.476"}]
["2010-04-08",120,{"v":90.63556645302742,"d":"91"},{"v":4.506846701721881,"d":"4.507"},{"v":119.33110988916013,"d":"119.331"}]
["2010-04-09",116,{"v":91.63556645302742,"d":"92"},{"v":4.517819476373775,"d":"4.518"},{"v":118.19852626339383,"d":"118.199"}]
["2010-04-11",110,{"v":93.63556645302742,"d":"94"},{"v":4.539410294780625,"d":"4.539"},{"v":115.96997348888948,"d":"115.970"}]
["2010-04-12",110,{"v":94.63556645302742,"d":"95"},{"v":4.550033372133955,"d":"4.550"},{"v":114.873484784134,"d":"114.873"}]
["2010-04-13",109,{"v":95.63556645302742,"d":"96"},{"v":4.56054478489734,"d":"4.561"},{"v":113.7885218319945,"d":"113.789"}]
["2010-04-14",110,{"v":96.63556645302742,"d":"97"},{"v":4.570946856199393,"d":"4.571"},{"v":112.71484484467715,"d":"112.715"}]
["2010-04-15",112,{"v":97.63556645302742,"d":"98"},{"v":4.58124183741709,"d":"4.581"},{"v":111.65222144042076,"d":"111.652"}]
["2010-04-18",112,{"v":100.63556645302742,"d":"101"},{"v":4.611505738454594,"d":"4.612"},{"v":108.52845376503433,"d":"108.528"}]
["2010-04-19",115,{"v":101.63556645302742,"d":"102"},{"v":4.621393537400495,"d":"4.621"},{"v":107.50785874360429,"d":"107.508"}]
["2010-04-20",100,{"v":102.63556645302742,"d":"103"},{"v":4.6311845242558505,"d":"4.631"},{"v":106.49725643523067,"d":"106.497"}]
["2010-04-22",95,{"v":104.63556645302742,"d":"105"},{"v":4.650483517287454,"d":"4.650"},{"v":104.5052604091756,"d":"104.505"}]
["2010-04-24",94,{"v":106.63556645302742,"d":"107"},{"v":4.669417100109601,"d":"4.669"},{"v":102.55098115331299,"d":"102.551"}]
["2010-04-27",97,{"v":109.63556645302742,"d":"110"},{"v":4.6971618333042,"d":"4.697"},{"v":99.68723597359843,"d":"99.687"}]
["2010-04-28",90,{"v":110.63556645302742,"d":"111"},{"v":4.706241614726305,"d":"4.706"},{"v":98.75004259357792,"d":"98.750"}]
["2010-04-29",87,{"v":111.63556645302742,"d":"112"},{"v":4.715239694990144,"d":"4.715"},{"v":97.82128221222848,"d":"97.821"}]
["2010-04-30",85,{"v":112.63556645302742,"d":"113"},{"v":4.724157531310409,"d":"4.724"},{"v":96.90080441932571,"d":"96.901"}]
["2010-05-02",86,{"v":114.63556645302742,"d":"115"},{"v":4.741758109124369,"d":"4.742"},{"v":95.0841147607374,"d":"95.084"}]
["2010-05-06",86,{"v":118.63556645302742,"d":"119"},{"v":4.776056327382822,"d":"4.776"},{"v":91.54393448502435,"d":"91.544"}]
["2010-05-07",84,{"v":119.63556645302742,"d":"120"},{"v":4.784450175678143,"d":"4.784"},{"v":90.67754148616649,"d":"90.678"}]
["2010-05-08",89,{"v":120.63556645302742,"d":"121"},{"v":4.792774153360761,"d":"4.793"},{"v":89.8183603652866,"d":"89.818"}]
["2010-05-10",86,{"v":122.63556645302742,"d":"123"},{"v":4.809217083005234,"d":"4.809"},{"v":88.12116038936784,"d":"88.121"}]
["2010-05-12",84,{"v":124.63556645302742,"d":"125"},{"v":4.82539401067004,"d":"4.825"},{"v":86.45141650328509,"d":"86.451"}]
["2010-05-13",86,{"v":125.63556645302742,"d":"126"},{"v":4.8333853863450775,"d":"4.833"},{"v":85.62656576825873,"d":"85.627"}]
["2010-05-14",82,{"v":126.63556645302742,"d":"127"},{"v":4.841313405902972,"d":"4.841"},{"v":84.80825450051793,"d":"84.808"}]
["2010-05-16",80,{"v":128.63556645302742,"d":"129"},{"v":4.856983340074819,"d":"4.857"},{"v":83.19084127342637,"d":"83.191"}]
["2010-05-18",78,{"v":130.63556645302742,"d":"131"},{"v":4.872411510953964,"d":"4.872"},{"v":81.59838227671975,"d":"81.598"}]
["2010-05-20",77,{"v":132.63556645302742,"d":"133"},{"v":4.887605265413894,"d":"4.888"},{"v":80.03011918364155,"d":"80.030"}]
["2010-05-25",80,{"v":137.63556645302742,"d":"138"},{"v":4.924609369229345,"d":"4.925"},{"v":76.21064385519321,"d":"76.211"}]
["2010-05-28",82,{"v":140.63556645302742,"d":"141"},{"v":4.946171909357403,"d":"4.946"},{"v":73.98500989717235,"d":"73.985"}]
["2010-06-01",79,{"v":144.63556645302742,"d":"145"},{"v":4.974217243885825,"d":"4.974"},{"v":71.0902373648172,"d":"71.090"}]
["2010-06-02",78,{"v":145.63556645302742,"d":"146"},{"v":4.981107381021758,"d":"4.981"},{"v":70.37905384496844,"d":"70.379"}]
["2010-06-03",78,{"v":146.63556645302742,"d":"147"},{"v":4.987950368847896,"d":"4.988"},{"v":69.67273696440952,"d":"69.673"}]
["2010-06-04",79,{"v":147.63556645302742,"d":"148"},{"v":4.994746848267851,"d":"4.995"},{"v":68.97122057059846,"d":"68.971"}]
["2010-06-05",73,{"v":148.63556645302742,"d":"149"},{"v":5.001497447205635,"d":"5.001"},{"v":68.27443985071648,"d":"68.274"}]
["2010-06-07",72,{"v":150.63556645302742,"d":"151"},{"v":5.014863452509966,"d":"5.015"},{"v":66.8948326656755,"d":"66.895"}]
["2010-06-08",68,{"v":151.63556645302742,"d":"152"},{"v":5.0214800529022465,"d":"5.021"},{"v":66.21188295602815,"d":"66.212"}]
["2010-06-09",67,{"v":152.63556645302742,"d":"153"},{"v":5.028053161503948,"d":"5.028"},{"v":65.5334223652618,"d":"65.533"}]
["2010-06-10",66,{"v":153.63556645302742,"d":"154"},{"v":5.034583346338009,"d":"5.035"},{"v":64.85939226340349,"d":"64.859"}]
["2010-06-11",67,{"v":154.63556645302742,"d":"155"},{"v":5.041071164371564,"d":"5.041"},{"v":64.18973516163419,"d":"64.190"}]
["2010-06-12",66,{"v":155.63556645302742,"d":"156"},{"v":5.047517161801006,"d":"5.048"},{"v":63.52439468286502,"d":"63.524"}]
["2010-06-13",67,{"v":156.63556645302742,"d":"157"},{"v":5.053921874327926,"d":"5.054"},{"v":62.86331553325567,"d":"62.863"}]
["2010-06-14",68,{"v":157.63556645302742,"d":"158"},{"v":5.060285827426274,"d":"5.060"},{"v":62.20644347463849,"d":"62.206"}]
["2010-06-15",66,{"v":158.63556645302742,"d":"159"},{"v":5.066609536601062,"d":"5.067"},{"v":61.55372529781562,"d":"61.554"}]
["2010-06-16",67,{"v":159.63556645302742,"d":"160"},{"v":5.07289350763895,"d":"5.073"},{"v":60.90510879669455,"d":"60.905"}]
["2010-06-17",65,{"v":160.63556645302742,"d":"161"},{"v":5.079138236851005,"d":"5.079"},{"v":60.26054274323087,"d":"60.261"}]
["2010-06-18",65,{"v":161.63556645302742,"d":"162"},{"v":5.085344211307919,"d":"5.085"},{"v":59.619976863149645,"d":"59.620"}]
["2010-06-19",64,{"v":162.63556645302742,"d":"163"},{"v":5.091511909067984,"d":"5.092"},{"v":58.983361812414046,"d":"58.983"}]
["2010-06-20",60,{"v":163.63556645302742,"d":"164"},{"v":5.097641799398075,"d":"5.098"},{"v":58.35064915441694,"d":"58.351"}]
["2010-06-21",55,{"v":164.63556645302742,"d":"165"},{"v":5.103734342987899,"d":"5.104"},{"v":57.72179133786551,"d":"57.722"}]
["2010-06-22",59,{"v":165.63556645302742,"d":"166"},{"v":5.109789992157757,"d":"5.110"},{"v":57.09674167533706,"d":"57.097"}]
["2010-06-24",54,{"v":167.63556645302742,"d":"168"},{"v":5.121792375874812,"d":"5.122"},{"v":55.85788425783301,"d":"55.858"}]
["2010-06-25",44,{"v":168.63556645302742,"d":"169"},{"v":5.12773997499927,"d":"5.128"},{"v":55.24398726325478,"d":"55.244"}]
["2010-06-27",45,{"v":170.63556645302742,"d":"171"},{"v":5.1395300919516,"d":"5.140"},{"v":54.02703951487706,"d":"54.027"}]
["2010-06-28",41,{"v":171.63556645302742,"d":"172"},{"v":5.145373429289987,"d":"5.145"},{"v":53.42390417315721,"d":"53.424"}]
["2010-06-29",39,{"v":172.63556645302742,"d":"173"},{"v":5.151182820300938,"d":"5.151"},{"v":52.82427269038169,"d":"52.824"}]
["2010-06-30",38,{"v":173.63556645302742,"d":"174"},{"v":5.156958657123547,"d":"5.157"},{"v":52.228104590888734,"d":"52.228"}]
["2010-07-01",36,{"v":174.63556645302742,"d":"175"},{"v":5.16270132514108,"d":"5.163"},{"v":51.63536009633685,"d":"51.635"}]
["2010-07-02",36,{"v":175.63556645302742,"d":"176"},{"v":5.168411203135274,"d":"5.168"},{"v":51.04600010977856,"d":"51.046"}]
["2010-07-05",41,{"v":178.63556645302742,"d":"179"},{"v":5.185347788891116,"d":"5.185"},{"v":49.29784612758215,"d":"49.298"}]
["2010-07-06",40,{"v":179.63556645302742,"d":"180"},{"v":5.190930167738109,"d":"5.191"},{"v":48.721646298869246,"d":"48.722"}]
["2010-07-07",40,{"v":180.63556645302742,"d":"181"},{"v":5.196481556549597,"d":"5.196"},{"v":48.14864518769912,"d":"48.149"}]
["2010-07-08",43,{"v":181.63556645302742,"d":"182"},{"v":5.202002297503251,"d":"5.202"},{"v":47.578807475309304,"d":"47.579"}]
["2010-07-09",43,{"v":182.63556645302742,"d":"183"},{"v":5.207492727140588,"d":"5.207"},{"v":47.01209842468677,"d":"47.012"}]
["2010-07-11",50,{"v":184.63556645302742,"d":"185"},{"v":5.218383971186924,"d":"5.218"},{"v":45.88793019354796,"d":"45.888"}]
["2010-07-12",53,{"v":185.63556645302742,"d":"186"},{"v":5.223785431589548,"d":"5.224"},{"v":45.33040433511076,"d":"45.330"}]
["2010-07-13",48,{"v":186.63556645302742,"d":"187"},{"v":5.22915787289303,"d":"5.229"},{"v":44.775873758866396,"d":"44.776"}]
["2010-07-14",47,{"v":187.63556645302742,"d":"188"},{"v":5.234501605239456,"d":"5.235"},{"v":44.22430645268878,"d":"44.224"}]
["2010-07-15",46,{"v":188.63556645302742,"d":"189"},{"v":5.239816933825355,"d":"5.240"},{"v":43.67567091492003,"d":"43.676"}]
["2010-07-21",45,{"v":194.63556645302742,"d":"195"},{"v":5.271128920025475,"d":"5.271"},{"v":40.44372238908818,"d":"40.444"}]
["2010-07-22",40,{"v":195.63556645302742,"d":"196"},{"v":5.276253573653117,"d":"5.276"},{"v":39.91476786568626,"d":"39.915"}]
["2010-07-24",38,{"v":197.63556645302742,"d":"198"},{"v":5.286424761288312,"d":"5.286"},{"v":38.86492213972576,"d":"38.865"}]
["2010-07-26",39,{"v":199.63556645302742,"d":"200"},{"v":5.296493536646075,"d":"5.296"},{"v":37.82564716475372,"d":"37.826"}]
["2010-07-27",41,{"v":200.63556645302742,"d":"201"},{"v":5.301490160176028,"d":"5.301"},{"v":37.30990760263978,"d":"37.310"}]
["2010-07-28",41,{"v":201.63556645302742,"d":"202"},{"v":5.30646194153483,"d":"5.306"},{"v":36.79673219017502,"d":"36.797"}]
["2010-07-29",38,{"v":202.63556645302742,"d":"203"},{"v":5.3114091265211245,"d":"5.311"},{"v":36.28609555660978,"d":"36.286"}]
["2010-07-30",35,{"v":203.63556645302742,"d":"204"},{"v":5.316331957303455,"d":"5.316"},{"v":35.77797270588451,"d":"35.778"}]
["2010-08-01",35,{"v":205.63556645302742,"d":"206"},{"v":5.326105507204974,"d":"5.326"},{"v":34.76917019829284,"d":"34.769"}]
["2010-08-02",33,{"v":206.63556645302742,"d":"207"},{"v":5.3309566931423324,"d":"5.331"},{"v":34.26844235756835,"d":"34.268"}]
["2010-08-03",33,{"v":207.63556645302742,"d":"208"},{"v":5.335784458645861,"d":"5.336"},{"v":33.77013191815797,"d":"33.770"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}