{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":1,"external_links":1,"defined_names":20,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":97,"n_cols":10,"rows_kept":97,"merged":[[0,0,0,1],[0,2,0,5],[0,6,0,9],[1,7,1,8],[2,6,5,6],[2,7,3,8],[2,9,3,9],[4,7,5,8],[4,9,5,9]],"flags":["formulas_cached_only"]}
["Input Data",null,"Calculated Data Used for Regression Analysis",{"$nulls":3},"Regression Analysis Results"]
["Date","# of Critical Issues (y)","Days (x)\n(Date '0' ref = Day 0)","ln(x)","Logarithmic Regression Results (y')","Sum (y-y')2","Today's Date ->","2010-08-06T23:40:01.030"]
["2010-03-23",144,{"v":78.34225998925831,"d":"78"},{"v":4.361087176293089,"d":"4.361"},{"v":139.19760028541953,"d":"139.198"},{"v":3485.6350413507234,"d":"3485.635"},"Forecast Zero Critical Issues Date(s) ->","2010-09-05T05:32:11.157",null,"Linear Regression\ny=mx+b"]
["2010-03-24",141,{"v":79.34225998925831,"d":"79"},{"v":4.37377089954637,"d":"4.374"},{"v":137.84341699547429,"d":"137.843"}]
["2010-03-25",146,{"v":80.34225998925831,"d":"80"},{"v":4.38629575884739,"d":"4.386"},{"v":136.50619488524194,"d":"136.506"},"Date '0' ref",null,"2010-10-15T02:24:56.338",null,"Logarithmic Regression\ny=m*ln(x)+b"]
["2010-03-26",140,{"v":81.34225998925831,"d":"81"},{"v":4.398665684568857,"d":"4.399"},{"v":135.185514326752,"d":"135.186"},"2010-01-03T15:47:08.737"]
["2010-03-27",137,{"v":82.34225998925831,"d":"82"},{"v":4.41088446300491,"d":"4.411"},{"v":133.88097107464614,"d":"133.881"}]
["2010-03-28",134,{"v":83.34225998925831,"d":"83"},{"v":4.422955743328313,"d":"4.423"},{"v":132.5921755233897,"d":"132.592"},"Min '0' Ref"]
["2010-03-30",131,{"v":85.34225998925831,"d":"85"},{"v":4.446669759589407,"d":"4.447"},{"v":130.06033815064058,"d":"130.060"},"2010-03-22"]
["2010-04-01",131,{"v":87.34225998925831,"d":"87"},{"v":4.469834423486993,"d":"4.470"},{"v":127.58715262452205,"d":"127.587"}]
["2010-04-02",128,{"v":88.34225998925831,"d":"88"},{"v":4.48121858869442,"d":"4.481"},{"v":126.37171722073515,"d":"126.372"}]
["2010-04-04",128,{"v":90.34225998925831,"d":"90"},{"v":4.503605346398589,"d":"4.504"},{"v":123.9815851913882,"d":"123.982"}]
["2010-04-05",130,{"v":91.34225998925831,"d":"91"},{"v":4.514613550052668,"d":"4.515"},{"v":122.80628948814814,"d":"122.806"}]
["2010-04-06",127,{"v":92.34225998925831,"d":"92"},{"v":4.525501891430181,"d":"4.526"},{"v":121.64379093356695,"d":"121.644"}]
["2010-04-07",121,{"v":93.34225998925831,"d":"93"},{"v":4.536272952669718,"d":"4.536"},{"v":120.49381384448276,"d":"120.494"}]
["2010-04-08",120,{"v":94.34225998925831,"d":"94"},{"v":4.546929233359495,"d":"4.547"},{"v":119.3560913512606,"d":"119.356"}]
["2010-04-09",116,{"v":95.34225998925831,"d":"95"},{"v":4.557473154019104,"d":"4.557"},{"v":118.23036502606209,"d":"118.230"}]
["2010-04-11",110,{"v":97.34225998925831,"d":"97"},{"v":4.578233221613271,"d":"4.578"},{"v":116.01390728153649,"d":"116.014"}]
["2010-04-12",110,{"v":98.34225998925831,"d":"98"},{"v":4.5884538431032755,"d":"4.588"},{"v":114.92269813432972,"d":"114.923"}]
["2010-04-13",109,{"v":99.34225998925831,"d":"99"},{"v":4.598571059463292,"d":"4.599"},{"v":113.84252908129156,"d":"113.843"}]
["2010-04-14",110,{"v":100.34225998925831,"d":"100"},{"v":4.608586942115779,"d":"4.609"},{"v":112.77317896609242,"d":"112.773"}]
["2010-04-15",112,{"v":101.34225998925831,"d":"101"},{"v":4.618503500857499,"d":"4.619"},{"v":111.71443321189724,"d":"111.714"}]
["2010-04-18",112,{"v":104.34225998925831,"d":"104"},{"v":4.647676457214557,"d":"4.648"},{"v":108.59976969960331,"d":"108.600"}]
["2010-04-19",115,{"v":105.34225998925831,"d":"105"},{"v":4.6572146680614654,"d":"4.657"},{"v":107.58141842475055,"d":"107.581"}]
["2010-04-20",100,{"v":106.34225998925831,"d":"106"},{"v":4.666662760335393,"d":"4.667"},{"v":106.57268869896564,"d":"106.573"}]
["2010-04-22",95,{"v":108.34225998925831,"d":"108"},{"v":4.6852952901677885,"d":"4.685"},{"v":104.58337845901627,"d":"104.583"}]
["2010-04-24",94,{"v":110.34225998925831,"d":"110"},{"v":4.703586989683274,"d":"4.704"},{"v":102.63045711770894,"d":"102.630"}]
["2010-04-27",97,{"v":113.34225998925831,"d":"113"},{"v":4.730412090451431,"d":"4.730"},{"v":99.76646343967445,"d":"99.766"}]
["2010-04-28",90,{"v":114.34225998925831,"d":"114"},{"v":4.739196231157879,"d":"4.739"},{"v":98.82862079491923,"d":"98.829"}]
["2010-04-29",87,{"v":115.34225998925831,"d":"115"},{"v":4.74790388214528,"d":"4.748"},{"v":97.89894460864929,"d":"97.899"}]
["2010-04-30",85,{"v":116.34225998925831,"d":"116"},{"v":4.7565363640224785,"d":"4.757"},{"v":96.97729388548072,"d":"96.977"}]
["2010-05-02",86,{"v":118.34225998925831,"d":"118"},{"v":4.773580934491058,"d":"4.774"},{"v":95.1575228252068,"d":"95.158"}]
["2010-05-06",86,{"v":122.34225998925831,"d":"122"},{"v":4.8068225266637254,"d":"4.807"},{"v":91.60846962115204,"d":"91.608"}]
["2010-05-07",84,{"v":123.34225998925831,"d":"123"},{"v":4.8149630926422615,"d":"4.815"},{"v":90.73933851519087,"d":"90.739"}]
["2010-05-08",89,{"v":124.34225998925831,"d":"124"},{"v":4.823037924558739,"d":"4.823"},{"v":89.87722553526737,"d":"89.877"}]
["2010-05-10",86,{"v":126.34225998925831,"d":"126"},{"v":4.838994573463629,"d":"4.839"},{"v":88.1736068990806,"d":"88.174"}]
["2010-05-12",84,{"v":128.3422599892583,"d":"128"},{"v":4.854700601558461,"d":"4.855"},{"v":86.49674590387326,"d":"86.497"}]
["2010-05-13",86,{"v":129.3422599892583,"d":"129"},{"v":4.862462069108859,"d":"4.862"},{"v":85.66808940827514,"d":"85.668"}]
["2010-05-14",82,{"v":130.3422599892583,"d":"130"},{"v":4.870163759938033,"d":"4.870"},{"v":84.84581500060108,"d":"84.846"}]
["2010-05-16",80,{"v":132.3422599892583,"d":"132"},{"v":4.885391445582262,"d":"4.885"},{"v":83.22002444745112,"d":"83.220"}]
["2010-05-18",78,{"v":134.3422599892583,"d":"134"},{"v":4.900390722603708,"d":"4.900"},{"v":81.61862004133968,"d":"81.619"}]
["2010-05-20",77,{"v":136.3422599892583,"d":"136"},{"v":4.915168341925013,"d":"4.915"},{"v":80.0408810170428,"d":"80.041"}]
["2010-05-25",80,{"v":141.3422599892583,"d":"141"},{"v":4.951184324870677,"d":"4.951"},{"v":76.19561876225862,"d":"76.196"}]
["2010-05-28",82,{"v":144.3422599892583,"d":"144"},{"v":4.972187284922537,"d":"4.972"},{"v":73.95322849769184,"d":"73.953"}]
["2010-06-01",79,{"v":148.3422599892583,"d":"148"},{"v":4.99952217139027,"d":"5.000"},{"v":71.03480732529852,"d":"71.035"}]
["2010-06-02",78,{"v":149.3422599892583,"d":"149"},{"v":5.0062407186741025,"d":"5.006"},{"v":70.31749867051371,"d":"70.317"}]
["2010-06-03",78,{"v":150.3422599892583,"d":"150"},{"v":5.012914428157676,"d":"5.013"},{"v":69.60497714318808,"d":"69.605"}]
["2010-06-04",79,{"v":151.3422599892583,"d":"151"},{"v":5.019543894346751,"d":"5.020"},{"v":68.89717927065249,"d":"68.897"}]
["2010-06-05",73,{"v":152.3422599892583,"d":"152"},{"v":5.026129700001061,"d":"5.026"},{"v":68.19404283430788,"d":"68.194"}]
["2010-06-07",72,{"v":154.3422599892583,"d":"154"},{"v":5.039172603848636,"d":"5.039"},{"v":66.80151147028755,"d":"66.802"}]
["2010-06-08",68,{"v":155.3422599892583,"d":"155"},{"v":5.045630811548335,"d":"5.046"},{"v":66.11199808566948,"d":"66.112"}]
["2010-06-09",67,{"v":156.3422599892583,"d":"156"},{"v":5.052047578292528,"d":"5.052"},{"v":65.426909162887,"d":"65.427"}]
["2010-06-10",66,{"v":157.3422599892583,"d":"157"},{"v":5.058423432527813,"d":"5.058"},{"v":64.74618828210646,"d":"64.746"}]
["2010-06-11",67,{"v":158.3422599892583,"d":"158"},{"v":5.064758892656829,"d":"5.065"},{"v":64.06978009584236,"d":"64.070"}]
["2010-06-12",66,{"v":159.3422599892583,"d":"159"},{"v":5.071054467291188,"d":"5.071"},{"v":63.39763030195218,"d":"63.398"}]
["2010-06-13",67,{"v":160.3422599892583,"d":"160"},{"v":5.077310655496502,"d":"5.077"},{"v":62.72968561747655,"d":"62.730"}]
["2010-06-14",68,{"v":161.3422599892583,"d":"161"},{"v":5.083527947029777,"d":"5.084"},{"v":62.06589375329338,"d":"62.066"}]
["2010-06-15",66,{"v":162.3422599892583,"d":"162"},{"v":5.089706822569493,"d":"5.090"},{"v":61.40620338955341,"d":"61.406"}]
["2010-06-16",67,{"v":163.3422599892583,"d":"163"},{"v":5.095847753938601,"d":"5.096"},{"v":60.750564151871686,"d":"60.751"}]
["2010-06-17",65,{"v":164.3422599892583,"d":"164"},{"v":5.10195120432073,"d":"5.102"},{"v":60.09892658824458,"d":"60.099"}]
["2010-06-18",65,{"v":165.3422599892583,"d":"165"},{"v":5.108017628469823,"d":"5.108"},{"v":59.451242146667255,"d":"59.451"}]
["2010-06-19",64,{"v":166.3422599892583,"d":"166"},{"v":5.114047472913462,"d":"5.114"},{"v":58.80746315342628,"d":"58.807"}]
["2010-06-20",60,{"v":167.3422599892583,"d":"167"},{"v":5.120041176150095,"d":"5.120"},{"v":58.1675427920419,"d":"58.168"}]
["2010-06-21",55,{"v":168.3422599892583,"d":"168"},{"v":5.125999168840387,"d":"5.126"},{"v":57.531435082838925,"d":"57.531"}]
["2010-06-22",59,{"v":169.3422599892583,"d":"169"},{"v":5.131921873992906,"d":"5.132"},{"v":56.899094863121604,"d":"56.899"}]
["2010-06-24",54,{"v":171.3422599892583,"d":"171"},{"v":5.143663076534461,"d":"5.144"},{"v":55.645540211373486,"d":"55.646"}]
["2010-06-25",44,{"v":172.3422599892583,"d":"172"},{"v":5.149482383275936,"d":"5.149"},{"v":55.02423936847367,"d":"55.024"}]
["2010-06-27",45,{"v":174.3422599892583,"d":"174"},{"v":5.1610203786132,"d":"5.161"},{"v":53.7923802232383,"d":"53.792"}]
["2010-06-28",41,{"v":175.3422599892583,"d":"175"},{"v":5.166739835259867,"d":"5.167"},{"v":53.18173991961294,"d":"53.182"}]
["2010-06-29",39,{"v":176.3422599892583,"d":"176"},{"v":5.172426765666459,"d":"5.172"},{"v":52.57457229431054,"d":"52.575"}]
["2010-06-30",38,{"v":177.3422599892583,"d":"177"},{"v":5.178081537691897,"d":"5.178"},{"v":51.970838072711445,"d":"51.971"}]
["2010-07-01",36,{"v":178.3422599892583,"d":"178"},{"v":5.183704512989669,"d":"5.184"},{"v":51.370498642722055,"d":"51.370"}]
["2010-07-02",36,{"v":179.3422599892583,"d":"179"},{"v":5.189296047146621,"d":"5.189"},{"v":50.77351603995646,"d":"50.774"}]
["2010-07-05",41,{"v":182.3422599892583,"d":"182"},{"v":5.2058854704490285,"d":"5.206"},{"v":49.00233896699899,"d":"49.002"}]
["2010-07-06",40,{"v":183.3422599892583,"d":"183"},{"v":5.211354679223546,"d":"5.211"},{"v":48.41841648747334,"d":"48.418"}]
["2010-07-07",40,{"v":184.3422599892583,"d":"184"},{"v":5.216794138386527,"d":"5.217"},{"v":47.83767023830376,"d":"47.838"}]
["2010-07-08",43,{"v":185.3422599892583,"d":"185"},{"v":5.2222041698322235,"d":"5.222"},{"v":47.26006585230891,"d":"47.260"}]
["2010-07-09",43,{"v":186.3422599892583,"d":"186"},{"v":5.227585090258586,"d":"5.228"},{"v":46.685569517092745,"d":"46.686"}]
["2010-07-11",50,{"v":188.3422599892583,"d":"188"},{"v":5.2382608395281265,"d":"5.238"},{"v":45.54576845239217,"d":"45.546"}]
["2010-07-12",53,{"v":189.3422599892583,"d":"189"},{"v":5.243556276772208,"d":"5.244"},{"v":44.980398766717826,"d":"44.980"}]
["2010-07-13",48,{"v":190.3422599892583,"d":"190"},{"v":5.24882382000682,"d":"5.249"},{"v":44.41800719722892,"d":"44.418"}]
["2010-07-14",47,{"v":191.3422599892583,"d":"191"},{"v":5.25406376155927,"d":"5.254"},{"v":43.85856253347197,"d":"43.859"}]
["2010-07-15",46,{"v":192.3422599892583,"d":"192"},{"v":5.2592763891854535,"d":"5.259"},{"v":43.30203405306236,"d":"43.302"}]
["2010-07-21",45,{"v":198.3422599892583,"d":"198"},{"v":5.289994124213877,"d":"5.290"},{"v":40.02244156670827,"d":"40.022"}]
["2010-07-22",40,{"v":199.3422599892583,"d":"199"},{"v":5.295023246834621,"d":"5.295"},{"v":39.485505078888195,"d":"39.486"}]
["2010-07-24",38,{"v":201.3422599892583,"d":"201"},{"v":5.30500624597881,"d":"5.305"},{"v":38.41966578591075,"d":"38.420"}]
["2010-07-26",39,{"v":203.3422599892583,"d":"203"},{"v":5.314890569122117,"d":"5.315"},{"v":37.36436167955367,"d":"37.364"}]
["2010-07-27",41,{"v":204.3422599892583,"d":"204"},{"v":5.3197963330475915,"d":"5.320"},{"v":36.84059563707274,"d":"36.841"}]
["2010-07-28",41,{"v":205.3422599892583,"d":"205"},{"v":5.3246781478941045,"d":"5.325"},{"v":36.319386528537166,"d":"36.319"}]
["2010-07-29",38,{"v":206.3422599892583,"d":"206"},{"v":5.329536246356546,"d":"5.330"},{"v":35.80070951017467,"d":"35.801"}]
["2010-07-30",35,{"v":207.3422599892583,"d":"207"},{"v":5.334370857754817,"d":"5.334"},{"v":35.28454009854522,"d":"35.285"}]
["2010-08-01",35,{"v":209.3422599892583,"d":"209"},{"v":5.343970520151679,"d":"5.344"},{"v":34.259627921942524,"d":"34.260"}]
["2010-08-02",33,{"v":210.3422599892583,"d":"210"},{"v":5.348736013491983,"d":"5.349"},{"v":33.75083793016188,"d":"33.751"}]
["2010-08-03",33,{"v":211.3422599892583,"d":"211"},{"v":5.353478904573851,"d":"5.353"},{"v":33.24446107844096,"d":"33.244"}]
["2010-08-04",29,{"v":212.3422599892583,"d":"212"},{"v":5.358199406786103,"d":"5.358"},{"v":32.74047458422854,"d":"32.740"}]
["2010-08-05",29,{"v":213.3422599892583,"d":"213"},{"v":5.362897730509833,"d":"5.363"},{"v":32.23885598609468,"d":"32.239"}]
["2010-08-06",31,{"v":214.3422599892583,"d":"214"},{"v":5.36757408317467,"d":"5.368"},{"v":31.739583137723912,"d":"31.740"}]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}